## PMR 2023(Original) (hidden)
| COMPANY: PHILIPPINE NATIONAL OIL COMPANY LOCATION: Bldg.6 Energy Center, Rizal Drive, BGC, Taguig SUBJECT: Procurement Monitoring |  |  |  |  | NOTE: 1.
[16 empty] | FAILED |  |  |  | ONGOING
[16 empty] | COMPLETED |  |  |  | AWARDED
| AS OF: | 2024-10-16
PR NO. | Code (PAP) *from APP | Procurement Program/Project | Classification *Goods and Services, Infrastructure or Cosnulting Services | Account Officer *Initials | Date of PR | Date PR Received | Time Received | Date PR Awarded | TAT (days) | PMO/ End-User | Is this an Early Procurement Activity? Y/N | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Winning Bidder | List of Invited Observers | Date of Receipt of Invitation | [7 empty] | Submitted to COA |  | Reason of Failure |  |  |  |  | Payment Oder No./Contract No. | STATUS / REMARKS *Ongoing / Completed | STATUS as of today
[13 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf / Negotiation | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Reso Reco Award | Notice of Award | Contract Signing/ PO | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/Acceptance (if applicable) | Submission to IAO | Submission to OGC |  | Rebid |  | Date of Failure of Bidding | Date of Memo to Proponent (Failure of Bid) | Date Received Memo by Proponent | Date of Submitted CSS Form
GSD-23-001 | 23MO-06B14 | Contract Services for the Preventive Maintenance of Two (2) Units Passenger Elevator at PNOC Bldg.6 for 2023 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-30 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | 2023-01-03 |  |  |  |  | COB | 185327.09 |  |  | 192757.8 | 192757.8 |  | KPI Elevators,Inc. | [11 empty] | 1st - Over ABC | 2022-11-28 | 2022-11-28 | 2022-11-29 | 2023-01-31 |  | Awarded | Received Signed AOB 12.20.22
GSD-23-002 | 23MO-06B18 | Contract Services for the Preventive Maintenance of CCTV Surveillance System at PNOC Bldg.6, 5, Computer Bldg. & Compound Perimeter | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-27 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | 2023-01-03 |  |  |  |  | COB | 89888.04 | 89888.04 |  | 80000 | 80000 |  | Comparts Computer Sales | [15 empty] | 2023-01-31 | 298646 | Awarded | Transmitted to Proponent
GSD-23-003 | 23MO-06B16 | Contract Services for the Maintenance of Fire Protection System at PNOC Bldg. 5&6 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-27 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | 2023-01-03 |  | 2023-02-20 |  |  | COB | 333900 |  |  | 310000 | 310000 |  | Lubricks Maintenance and Construction | [15 empty] | 2023-01-31 |  | Awarded | Signed NTP/Contract by OP
GSD-23-004 | 23MO-06B15 | Contract Services for the Preventive Maintenance of Two (2) Units Passenger Elevator at PNOC Bldg.5 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-20 | 63 | GSD | Y | NP-SVP | N/A | 2022-10-28 | N/A | N/A | N/A | 2022-12-16 | N/A | 2022-12-20 | 2023-01-03 |  |  |  |  | COB | 139920 |  |  | 132000 | 132000 |  | Rockspeed Elevator and Escalator Corporation | [15 empty] | 2023-01-31 |  | Awarded | Contract drafting
GSD-23-005 | 23MO-06B17 | Contract Services for the Water Chemical Treatment for PNOC Bldg. 5&6 | Goods & Services | CDBB | 2022-07-01 | 2022-10-18 | 3:11PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-12-15 | 2023-01-10 |  | 2023-01-30 | Jan-Dec |  | COB | 400898.8 |  |  | 308040 | 308040 |  | Impact One Nation Industrial Corp. | [7 empty] | 2023-02-08 | 2023-02-08 | 2023-02-08 |  | 1st - Non Compliance | 2022-11-15 | 2022-11-15 | 2022-11-15 | 2023-01-31 |  | Awarded | Contract drafting
GSD-23-006 | 23MO-05C13 | Rental of Photocopying Machines for the year 2023 for PNOC Offices @ BGC, Taguig City, ESB & PIP | Goods & Services | GSM | 2022-07-07 | 2022-10-18 | 1:00PM | 2022-11-29 | 42 | GSD | Y | NP-SVP | N/A | 2022-11-27 | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-11-29 | 2023-01-03 |  | 2023-02-23 | Jan-Dec |  | COB | 680000 |  |  | 639000 | 639000 |  | Photopro Trading & General Merchandise Co. | [15 empty] | 2023-01-31 |  | Awarded | Contract drafting
GSD-23-007 | 23MO-02A | Supply and Delivery of Drinking Water | Goods & Services | HDVE | 2022-06-25 | 2022-10-18 | 2:51PM | 2022-11-22 | 35 | GSD | Y | NP-SVP | N/A | 2022-10-29 | N/A | N/A | N/A | 2022-11-08 | N/A | 2022-11-22 | 2023-01-04 | 2023-01-25 | 2023-01-18 | Mar-Dec |  | COB | 360000 |  |  | 278400 | 278400 |  | MSDR Water Refilling Station | [9 empty] | 2023-01-26 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-008 | 23MO-07D8 | 2023 Web Hosting and Maintenance for Document Tracking System | Goods & Services | CDBB | - | 2022-10-18 | 2:51PM | 2022-11-08 | 21 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-04 | N/A | 2022-11-08 | 2023-01-09 | 2023-01-30 | 2023-01-24 | Mar-Dec |  | COB | 239000 | 239000 |  | 238000 | 238000 |  | MYBUSYBEE INC. | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 23-002 | Awarded | Completed/Delivered
GSD-23-009 | 23MO-05C13 | 2023 Messengerial Services | Goods & Services | HDVE | 2022-06-28 | 2022-10-18 | 2:51PM | 2022-12-20 | 63 | GSD | Y | PB | 2022-10-25 | 2022-10-28 | 2022-11-11 | 2022-11-24 | 2022-11-24 | 2022-12-06 | 2022-12-20 | 2022-12-20 | 2022-01-09 | 2023-01-24 | 2023-01-18 | Jan-Dec |  | COB | 2666000 | 2666000 |  | 2592831.24 | 2592831.24 |  | PRC Couirier & Maintenance Services | MBC, COA, PCCI | [7 empty] | 2023-01-25 | 2023-01-27 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-010 | 23MO-06H2 | Pest Control Services | Goods & Services | CDBB |  | 2022-10-18 |  | 2022-11-08 | 21 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-02 | N/A | 2022-11-08 | 2023-01-09 | N/A | N/A | Jan-Dec |  | COB | 103824 | 103824 |  | 100800 | 100800 |  | Rampest Control Services and Supplies Company | [9 empty] | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298647 | Awarded | Completed/Delivered
ESB-23-011 | 23MO-05C12 | Preventive Maintenance of Truck Scale (Quarterly Check up and Calibration with ITDI Certificate) | Goods & Services | CDBB | 2022-07-11 | 2022-10-18 |  | 2022-11-22 | 35 | ESB | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-11-22 | N/A | 2023-01-10 | N/A | 30 days |  | COB | 83000 | 83000 |  | 83000 | 83000 |  | GCH International Mercantile, Inc. | [9 empty] | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298650 | Awarded | Completed/Delivered
GSD-23-012 | 23MO-05A | Janitorial Services | Goods & Services | CFCM | 2022-07-06 | 2022-10-18 | 8:55AM | 2023-01-17 | 91 | GSD | Y | PB | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2022-12-21 | 2023-01-12 | 2023-01-17 | 2023-01-18 |  | 2023-02-27 | Jan-Dec |  | COB | 8680000 | 8680000 |  | 8453970.56 | 8453970.56 |  | Starcom Manpower and Allied Services | MBC, COA, PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [11 empty] | Awarded | rECEived Signed AOB 1.18.23
GSD-23-013 | 23MO-05C7 | Maintenance Services | Goods & Services | CFCM | 2022-07-22 | 2022-10-18 | 3:50PM | 2023-01-17 | 91 | GSD | Y | PB | 2022-11-08 | 2022-11-16 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2022-12-21 | 2023-01-12 | 2023-01-17 | 2023-01-18 |  |  | Jan-Dec |  | COB | 3627000 | 3627000 |  | 3605545.91 | 3605545.91 |  | Servicio Filipino,Inc. | MBC, COA, PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [5 empty] | N/A | N/A | N/A | N/A | 2023-01-31 |  | Awarded | Contract FCE013023-1888
ESB-23-014 | 23MO-04A3 | Engagement of 3rd party Laboratory Service provider to conduct Quarterly Ambient Air Monitoring And Raw Water Testing | Goods & Services | HDVE | 2022-08-10 | 2022-10-18 | 2:10PM | 2022-11-14 | 27 | ESB | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-11-14 | 2023-01-06 |  |  | Mar-Dec |  | COB | 228000 |  |  | 221760 | 221760 |  | Berkman Systems,Inc. | [9 empty] | 2023-03-06 | [5 empty] | 2023-01-31 |  | Awarded | Abstract Routing 11.15.22
GSD-23-015 | Awaiting APP | 2023 Caretaker Services- Tagaytay Property | Goods & Services | HDVE | 2022-07-22 | 2022-10-18 | 2:07PM |  | -44852 | GSD | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-08 | N/A |  | N/A |  | N/A | Jan-Dec |  | COB | 527000 | [24 empty] | Cancelled 11.21.2022
AM-23-016 | 23MO-06H2 | 2023 Pest Control Services - PNOC Staffhouse, Lamo,Limay, Bataan | Goods & Services | CDBB | 2022-08-23 | 2022-10-18 | 9:05AM | 2022-11-14 | 27 | AMD | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-08 | N/A | 2022-11-14 | N/A | 2023-01-09 | N/A | Jan-Dec |  | COB | 45000 | 45000 |  | 34000 | 34000 |  | RAM Pest Control Services & Supplies Phils. Co. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298648 | Awarded | Completed/Delivered
AM-23-017 | Awaiting APP | 2023 Caretaker Services- Staffhouse, Lamao, Limay, Bataan | Goods & Services | HDVE | 2022-09-02 | 2022-10-18 | 9:05AM |  | -44852 | AMD | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-10 | N/A |  | N/A |  | N/A |  |  | COB | 324000 | [17 empty] | 1st- | [6 empty] | Cancelled 11.21.2022
PIP-23-018 | 23MO-05C7 | Provision for Manpower for 2023 Custodial Services/Other General Services at PIP | Goods & Services | CFCM | 2022-08-23 | 2022-10-18 | 1:21PM | 2023-02-06 | 111 | PIP | Y | PB | 2022-11-22 | 2022-11-15 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2023-12-27 | 2023-01-31 | 2023-02-06 | 2023-02-14 |  | 2023-02-27 | Mar-Dec |  | COB | 3794718.27 | 3794718.27 |  | 3794718.27 | 3794718.27 |  | Servicio Filipino, Inc. | MBC,COA,PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [11 empty] | Awarded | Finalization of Contract
AM-23-019 | Awaiting APP | Security Services for PNOC Provincial Properties | Goods & Services | RGV | 2022-08-31 | 2022-10-18 | 2:19PM | 2022-12-20 | 63 | AMD | Y | PB | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-11-15 | 2022-11-15 | 2022-12-19 | 2022-12-19 | 2022-12-20 | 2023-01-26 | 2023-02-20 | 2023-02-15 | Jan-Dec |  | COB | 6188770.36 | 6188770.36 |  | 5941511.28 | 5941511.28 |  | Eliteblue Security Specialists | MBC,COA,PCCI | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 |  | 2023-02-20 | 2023-02-20 | 2023-02-20 | [5 empty] | 2023-01-31 | Contract#012 | Awarded | Contract Finalization 2.2.23
GSD-23-020 | 23MO-05B | Security Services for Head Office, PIP &ESB | Goods & Services | RGV | 2022-08-15 | 2022-10-18 | 9:16PM | 2023-01-12 | 86 | GSD | Y | PB | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-11-15 | 2022-11-15 | 2022-12-06 | 2023-01-05 | 2023-01-12 | 2023-01-26 |  | 2023-02-20 | Jan-Dec |  | COB | 48611344.64 | 48611344.64 |  | 47781296.28 | 47781296.28 |  | Eliteblue Security Specialists | MBC,COA,PCCI | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 | [9 empty] | 2023-01-31 | Contract #23-007/008/009 | Awarded | For Signing of Contract
ESB-23-021 | 23MO-05A | 2023 Custodial and Janitorial Services | Goods & Services | CFCM | 2022-09-14 | 2022-10-18 | 3:40PM | 2023-01-12 | 86 | ESB | Y | PB | 2022-11-03 | 2022-11-08 | 2022-11-15 | 2022-11-29 | 2022-11-29 | 2022-12-21 | 2023-01-12 | 2023-01-12 | 2023-01-31 |  | 2023-02-20 | Jan-Dec |  | COB | 7530000 | 7530000 |  | 7451165.35 | 7451165.35 |  | Stewards Manpower Supply and Services | MBC,COA,PCCI | [14 empty] | 2023-01-31 | Contract #23-014 | Awarded | Abstract Routing 1.12.23
PIP-23-022 | 23MO-05A | Supply of Manpower,Equipment and Supplies for Janitorial Services at PIP | Goods & Services | CFCM | 2022-08-23 | 2022-10-18 | 3:25PM | 2023-02-13 | 118 | PIP | Y | PB | 2022-11-17 | 2022-11-22 | 2022-11-29 | 2022-12-13 | 2022-12-13 | 2022-12-27 | 2023-01-31 | 2023-02-13 | 2023-02-20 |  | 2023-02-28 | Mar-Dec |  | COB | 4304703.82 |  |  | 3916087.08 | 3916087.08 |  | Servicio Filipino,Inc. | [17 empty] | Awarded
PIP-23-023 | 23CA-06A | Supply,Delivery, Testing and Commissioning of Brand New Fire Truck | Goods & Services | CFCM | 2022-10-05 | 2023-01-13 | 9:21AM |  | -44939 | PIP | Y | PB | [5 empty] | 2023-02-20 | [7 empty] | COB | 29200000 |  | 29200000 | [15 empty] | 1st - Non Compliance | 2023-01-10 | 2023-01-11 | 2023-01-12
PIP-23-023 | Awaiting APP | Supply,Delivery, Testing and Commissioning of Brand New Fire Truck | Goods & Services | CFCM | 2022-10-05 | 2022-10-18 | 10:21AM |  | -44852 | PIP | Y | PB | [13 empty] | COB | 29200000 | [17 empty] | 1st - Non Compliance | [6 empty] | Failed Bidding
PIP-23-024 | 23MO-04A3 | Environmental Monitoring for 2023 (Waste Water-Effluent and Marine, Raw Water, Ambient Air Sampling and Laboratory Analysis | Goods & Services | HDVE | 2022-10-20 | 2023-01-19 | 5:01PM |  | -44945 | PIP | Y | PB |  |  | 2022-11-15 | 2023-01-05 | 2023-01-05 | 2023-01-09 | [7 empty] | COB | 1032026.6 | [16 empty] | 2022-12-12 | 1st-Non Comliance in Philgeps/2nd-Non-compliant in tech specs | 1st -12/2/2022/ 2nd- 1/17/2023 | 1st-12/2/2022 | 1st-12/5/22
PP-23-025 | Awaiting APP | Preventive Maintenance of PNOC Gym Equipment | Goods & Services | CDBB | 2022-10-17 | 2022-11-03 | 11:27AM |  | -44868 | PP | Y | NP-SVP | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  |  | COB | 59000 | [17 empty] | 1st&2nd- Non receipt of quotation/ | 1st- 11/15/222nd -12/1/2022 | 1st- 11/15/222nd -12/1/2022 | 1st- 11/15/222nd -12/2/2022 |  |  |  | Failed/Returned to End user 11.15.22
AM-23-026 | Awaiting APP | 2023 Caretaker Services- Staffhouse, Lamao, Limay, Bataan | Goods & Services | HDVE | 2022-11-23 | 2022-11-28 | 8:55AM | 2023-01-05 | 38 | AMD | Y | NP-SVP | N/A | 2022-12-16 | N/A | N/A | N/A |  | 2022-12-21 | 2023-01-05 | 2023-01-10 | 2023-02-14 | 2023-01-25 |  |  | COB | 322700 | 322700 |  | 320612.06 | 320612.06 |  | MMA Competent Manpower and General Services | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-02-23 | [5 empty] | 2023-01-31 | Contract#23-006 | Awarded` | Completed/Delivered
SM-23-027 | 23MO-03AA | 2023 PNOC Internet/Leased Line Connection Upgrade | Goods & Services | CFCM | 2022-11-18 | 2022-11-28 | 8:45AM | 2023-01-26 | 59 | SMO | Y | PB |  | 2022-12-06 | 2022-12-13 | 2022-12-27 | 2022-12-27 | 2023-01-05 | 2023-01-24 | 2023-01-26 | 2023-01-31 |  |  |  |  | COB | 1300000 |  |  | 610980 | 610980 |  | Source Telecommunications, Inc. | MBC,PCCI, COA | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | [9 empty] | 2023-01-31 |  | Awarded | For Contract Draft
PP-23-028 | 23MO-06C10 | Preventive Maintenance of PNOC Gym Equipment | Goods & Services | CDBB | 2022-12-07 | 2022-12-07 | 4:25PM | 2022-12-22 | 15 | PP | Y | NP-SVP | N/A | 2022-12-14 | N/A | N/A | N/A | 2022-12-20 | N/A | 2022-12-22 | N/A | 2023-01-09 | N/A | Jan-Dec |  | COB | 65000 | 65000 |  | 28800 | 28800 |  | The FITCO Inc (Stark Fitness) | [9 empty] | 2023-01-10 |  | Superceded of PP-22-025 |  |  |  | 2023-01-31 | PO#298649 | Awarded | Completed/Delivered
PIP-23-029 | 23MO-01F131 | Supply and Delivery of 2023 Vehicle Sticker for PIP | Goods & Services | GSM | 2022-12-22 | 2022-01-03 | 1:30PM | 2023-02-14 | 407 | PIP | N | NP-SVP | N/A | 2023-01-23 | N/A | N/A | N/A | 2023-02-07 | N/A | 2023-02-14 | N/A | 2023-02-15 | N/A | 30 Days |  | COB | 9000 | 9000 |  | 6712.5 | 6712.5 |  | Forms International Enterprises,Corp. | [16 empty] | PO#298654 | Awarded | PO Signed
ESB-23-030 | Awaiting APP | Supply and Delivery of Various Tires for ESB | Goods & Services |  | 2023-01-03 | 2023-01-05 | 9:20AM |  | -44931 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 66000 | [24 empty] | returned to end-user 1.9.22 thru memo - Emailed by RGV/ over ABC
PSD-23-031 | 23MO-07EB | Supply and Delivery of PNOC's 50th Anniversary T-shirt | Goods & Services | GSM | 2023-12-21 | 2023-01-11 | 10:41AM | 2023-02-09 | 29 | PSD | N | NP-SVP | N/A | 2023-01-17 | N/A | N/A | N/A | 2023-01-31 | N/A | 2023-02-09 | N/A | 2023-02-14 | N/A | 30 days |  | COB | 84000 | 84000 |  | 73500 | 73500 |  | Topsol Enterprises | [16 empty] | PO#298652 | Awarded | PO for Signature
SM-23-032 | 23MO-041D | Hiring of Certifying Body for PNOC QMS and Recertification | Consulting Services | HDVE | 2023-01-09 | 2023-01-12 | 10:55AM |  | -44938 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 300000 | 300000
ESB-23-033 | 23MO-06D5 | Supply and Delivery of Various Tires for ESB | Goods & Services | GSM | 2023-01-03 | 2023-01-13 | 9:26AM | 2023-02-06 | 24 | ESB | N | NP-SVP | N/A | 2023-01-17 | N/A | N/A | N/A | 2023-01-25 | N/A | 2023-02-06 | N/A | 2023-02-08 | N/A |  |  | COB | 66000 | 66000 |  | 55300 | 55300 |  | Fleetserv Inc. | [16 empty] | PO#298651 | Awarded | Signed PO
PIP-23-034 | 23CA-03C2 | Replacement of Fire Engine for Jetty and Controls - 1 Unit | Goods & Services | CDBB | 2023-01-05 | 2023-01-13 | 10:01AM |  | -44939 | PIP | N | PB | 2023-01-19 | 2023-01-24 | 2023-01-31 | 2023-02-14 | 2023-02-14 | [8 empty] | COB | 22150 |  | 22150 | [15 empty] | 1st-Non-submission of bid | 2023-02-14 | 2023-02-14
PIP-23-035 | 23MO-04A2 | Hiring of EIA Report Consultant | Consulting Services | HDVE | 2023-01-11 | 2023-01-16 | 9:08AM | 2023-01-24 | 8 | PIP | N | NP-HT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-25 |  |  |  |  | COB | 170000 | 170000 |  | 170000 | 170000 |  | Engr.Aldwin Camance | [15 empty] | 2023-01-31 |  | Awarded
ESB-23-036 | 23CA-01C | Upgrade and Improvement of Drainage System | Infrastructure | RGV | 2023-01-10 | 2023-01-17 | 1:23PM |  | -44943 | ESB | N | PB | [13 empty] | COB | 4550000 |  | 4550000
SM-23-037 | 23MO-07E11 | Publication of the 50th Commemorative Book | Goods & Services | CFCM | 2023-01-18 | 2023-01-18 | 3:40PM | 2023-02-14 | 27 | SMO | N | NP-SVP | N/A | 2023-01-27 | N/A | N/A | N/A | 2023-02-08 | N/A | 2023-02-14 | N/A |  |  |  |  | COB | 1000000 | 1000000 |  | 978000 | 978000 |  | VJ Graphics Arts,Inc. | [17 empty] | Awarded
PIP-23-038 |  | Assessment of Jetty Facility and Hydrographic Survey | Consulting Services | RGV | 2023-01-19 | 2023-01-19 | 2:08PM |  | -44945 | PIP | N | PB | [13 empty] | COB
PIP-23-039 | 23MO-05C9 | Annual Physical Examination (APE) for PIP | Goods & Services | GSM | 2023-01-19 | 2023-01-23 | 10:12AM | 2023-02-21 | 29 | PIP | N | NP-SVP | N/A | 2023-01-26 | N/A | N/A | N/A | 2023-02-15 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 95000 | 95000 |  | 44227.5 | 44227.5 |  | EDGT-LAB-Tech Diagnostic Center | [16 empty] | PO#298658 | Awarded | For Signing PO
AS-23-040 |  | Hiring of Musical director for 2023 | Goods & Services | HDVE |  | 2023-01-24 |  | 2023-01-24 | 0 | ASD | N | NP-SVP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-26 |  |  | Feb-Dec |  | COB | 420000 | 420000 |  | 385000 | 385000 |  | Anthony Go Villanueva | [15 empty] | 2023-01-31 |  | Awarded | For Signing of Contract
PIP-23-041 | 23CA-01B | Fencing of Alberba Area (250m Length) | Infrastructure | CDBB | 2023-01-04 | 2023-01-24 | 3:14PM |  | -44950 | PIP | N | PB | N/A | 2023-01-31 | 2023-02-07 | [10 empty] | COB | 3460000 |  | 3460000 |  |  |  |  | MBC,COA,PCCI | 2023-01-30
ESB-23-042 | 23MO-01H2A | Supply, Delivery and Printing of Calling Cards (CBP) | Goods & Services | GSM | 2023-01-16 | 2023-01-31 | 2:30PM | 2023-02-21 | 21 | ESB | N | NP-SVP | N/A | 2023-02-06 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 3000 | 3000 |  | 2550 | 2550 |  | Forms International Enterprises Corporation | [16 empty] | PO#298659 | Awarded | For Signing PO
PIP-23-043 | 23CA-04B3 | Supply, Delivery and Installation of Load Break Switch | Goods & Services | GSM | 2023-01-10 | 2023-01-30 | 8:49AM | 2023-02-28 | 29 | PIP | N | NP-SVP | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-21 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 489000 |  | 489000 | 439000 |  | 439000 | Pablo S. Labasbas Construction Corporation | [17 empty] | Awarded
PSD-23-044 | 23MO-01D | Supply and Delivery of COVID Supplies (Face Mask) for MAR-JUN | Goods & Services | CDBB | 2023-01-30 | 2023-01-31 | 2:30PM | 2023-02-14 | 14 | PSD | N | NP-SVP | N/A | 2023-02-01 | N/A | N/A | N/A | 2023-02-09 | N/A | 2023-02-14 | N/A | 2023-02-15 | N/A |  |  | COB | 40000 | 40000 |  | 37584 | 37584 |  | SGS Healthcare Co. | [9 empty] | 2023-02-17 | [6 empty] | PO#298653 | Awarded
PP-23-045 | 23MO-01H2B | Supply and Delivery Various Tissue | Goods & Services | CDBB | 2023-02-01 | 2023-02-02 | 11:03AM | 2023-02-16 | 14 | PRM | N | NP-SVP | N/A | 2023-02-03 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-02-16 | N/A |  | N/A |  |  | COB | 19076 | 19076 |  | 18600 | 18600 |  | Eco-Hygiene Institutional Sals Corp/Sanitary Care Products Asia,Inc. | [9 empty] | 2023-02-20 | [6 empty] | PO#298656/PO#298657 | Awarded
ESB-23-046 | 23CA-MYB1A | Flattening of the Hilly Area | Infrastructure |  | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | [13 empty] | COB | 53540000 |  | 53540000
ESB-23-047 | 23CA-MYB3A1 | Construction of New Pier | Infrastructure |  | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | [13 empty] | COB | 1402039.17 |  | 1402039.17
ESB-23-048 | 23CA-MYB3A2 | Construction Management for the Flattening of the Hilly Area/Construction of New Pier | Consulting Services |  | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | [13 empty] | COB | 43951025 |  | 43951025
BR-23-049 | 23MO-01H2A | Supply, Delivery and Printing of Calling Cards (MRCR) | Goods & Services | GSM | 2023-02-02 | 2023-02-02 | 3:20PM | 2023-02-21 | 19 | BRDD | N | NP-SVP | N/A | 2023-02-06 | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 1000 | 1000 |  | 850 | 850 |  | Forms International Enterprises Corporation | [16 empty] | PO#298659 | Awarded | For Signing PO
PIP-23-050 | 23MO-01D | Anti-Venom | Goods & Services | CDBB | 2023-01-25 | 2023-02-16 | 1:06PM |  | -44973 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 9600 | 9600 | [16 empty] | 1st-non receipt quotation | 2023-02-14 | 2023-02-14 | 2023-02-14 |  |  |  | Emailed to EGC 3:30PM
GSD-23-051 | 23MO-01E1 | Supply and Delivery of Biometric Scanner | Goods & Services | CDBB | 2023-02-01 | 2023-02-03 | 1:37PM | 2023-02-16 | 13 | GSD | N | NP-SVP | N/A | 2023-02-07 | N/A | N/A | N/A | 2023-02-15 | N/A | 2023-02-16 | N/A | 2/17/23 | N/A | 30 days |  | COB | 20000 | 20000 |  | 20000 | 20000 |  | Comparts Computer Sales | [9 empty] | 2023-02-20 | [6 empty] | PO#298655 | Awarded | For Signing of PO
PIP-23-052 | 23MO-01H2J | Supply and Delivery of Various Fire Extinguisher | Goods & Services | CDBB | 2023-01-25 | 2023-02-03 | 11:47AM |  | -44960 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 100000 | 100000
PIP-23-053 | 23MO-05C3 | Hauling and Disposal of Generated Non-hazardous Solid Wastes by PNOC Industrial Park | Goods & Services | GSM | 2023-01-31 | 2023-02-03 | 11:47AM |  | -44960 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 60000 | 60000 | [16 empty] | 1st-non-receipt of bids | 2023-02-15 | 2023-02-21
PIP-23-054 | 23MO-01H2I | Life Ring | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 16000 | 16000 |  | 33317.5 | 33317.5 |  | Safetyko Industrial Supplies | [17 empty] | Awarded
PIP-23-055 | 23MO-01H2F | Cotton Gloves | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 2000 | 2000 | [22 empty] | Awarded
PIP-23-056 | 23MO-01H2G | Hi-Visibility Vest/ Reflective Vest | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 3000 | 3000 | [22 empty] | Awarded
PIP-23-057 | 23MO-01H2E | Safety Shoes | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 25000 | 25000 | [22 empty] | Awarded
BR-23-058 | Approved Budget Realignment | Engagement of an individual consultant for the development of decentralized energy systems (DES)- solar PV Rooftop system in PNOC (ESB) | Consulting Services | CFCM | 2023-02-03 | 2023-02-06 | 8:38AM |  | -44963 | BRDD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 500000 | 500000 | [16 empty] | 1st-Non Receipt of Quotation | 2023-03-01 | 2023-03-01 | 2023-03-01
GSD-23-059 | 23MO-01E4 | Supply and Delivery of Compressor Motor for Aircon at PNOC Records Bldg. | Goods & Services | GSM | 2023-02-02 | 2023-02-07 | 1:33PM | 2023-02-28 | 21 | GSD | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-20 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 32000 | 32000 |  | 24990 | 24990 |  | Pumpcraft Industrial Sales | [17 empty] | Awarded
IA-23-060 | 23MO-01 | Supply and Delivery of 1 unit Maintenance Box for Epson Printer L6160 | Goods & Services |  | 2023-02-02 | 2023-02-08 | 2:31PM |  | -44965 | IAO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 1000 | 1000 | [23 empty] | Returned to End - user
SM-23-061 | 23MO-07D4 | Cloud Based Email Hosting | Goods & Services | CDBB |  | 2023-02-09 | 10:00AM |  | -44966 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 330000 | 330000 | [16 empty] | 1st-Non Receipt of quotations | 2023-02-21 | 2023-02-22
PIP-23-062 | 23MO-06C1 | Calibration of Various Meters | Goods & Services | GSM | 2023-02-08 | 2023-02-10 | 1:15PM | 2023-03-02 | 20 | PIP | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-23 | N/A | 2023-03-02 | N/A |  | N/A |  |  | COB | 49000 | 49000 |  | 48300 | 48300 |  | Premier Physic Metrologie Co. | [17 empty] | Awarded
PIP-23-063 | 23MO-04B1N | Conduct of Work Measure Environment | Goods & Services | GSM | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-02 | 20 | PIP | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-28 | N/A | 2023-03-02 | N/A |  | N/A |  |  | COB | 30000 | 30000 |  | 29456 | 29456 |  | CRL Calabarquez Corp. | [17 empty] | Awarded
PIP-23-064 | 23MO-01H2H | Supply and Delivery of Dust Mask | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM |  | -44967 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 3000 | 3000
PIP-23-065 | 23MO-01H2M | Supply and Delivery of various Other Supplies for Safety | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM |  | -44967 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 68000 | 68000
PIP-23-066 | 23MO-07E5 | Supply and Delivery of Materials for the Coastal Clean-Up 2023 | Goods & Services | GSM | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-02-28 | 18 | PIP | N | NP-SVP | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-23 | N/A | 2023-02-28 | N/A | 2023-03-01 | N/A | 30 Days |  | COB | 35000 | 35000 |  | 29820 | 29820 |  | Ceboom Enterprises/Syner Graphics Co./ Safetyko | [16 empty] | PO#298660/298661 | Awarded
PIP-23-067 | 23MO-06C10 | Supply and Delivery of 100Watts LED Street Light | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM |  | -44967 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 200000 | 200000
PIP-23-068 | 23MO-01H2L | Supply and Delivery of Safety Hazards | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM |  | -44967 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 22000 | 22000
PSD-23-069 | 23MO-01H1C | Supply and Delivery of CY 2023 Token for Loyalty Service Awardees | Goods & Services | GSM | 2023-02-08 | 2023-02-13 | 10:31AM |  | -44970 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 160000 | 160000
PIP-23-070 | 23MO-06C12 | Preventive Maintenance Services of CCTV System for PIP | Goods & Services | GSM | 2023-02-02 | 2023-02-13 | 10:12AM |  | -44970 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 171000 | 171000
PSD-23-071 | 23MO-01H1F/01H1D/01H1G | Supply and Delivery of CY 2023 Token for Loyalty Service Awardees & Retirees | Goods & Services | GSM | 2023-02-08 | 2023-02-15 | 3:57PM |  | -44972 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 48000 | 48000
PSD-23-072 | 23MO-01D | Supply and Delivery of Fluquadri Vaccine (Adult) | Goods & Services | CDBB | 2023-02-13 | 2023-02-14 | 4:07PM | 2023-03-02 | 16 | PSD | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-28 | N/A | 2023-03-02 | N/A |  | N/A |  |  | COB | 90000 | 90000 |  | 71003 | 71003 |  | Pharma Quest Co. | [17 empty] | Awarded
GAD-23-073 | 23MO-07E2 | Supply and Delivery of T-shirts for 2023 National Women's Month Celebration | Goods & Services | GSM |  | 2023-02-15 | 7:50AM |  | -44972 | GAD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 39300 | 39300
SM-23-074 | 23MO-01A | Supply and Delivery of Stamp with Inscription | Goods & Services | GSM |  | 2023-02-16 |  |  | -44973 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 3500 | 3500
GSD-23-075 | 23CA-03D | Exterior Repainting of Bldg.5 | Infrastructure | CFCM | 2023-02-10 | 2023-02-16 | 2:40PM |  | -44973 | GSD | N | PB | [13 empty] | COB | 4500000 |  | 4500000
PP-23-076 | 23MO-01A | Supply and Delivery of Consolidated Computer Supplies, for 1st QTR year 2023 | Goods & Services | GSM | 2023-02-17 | 2023-02-17 | 3:05PM |  | -44974 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 907538.92 | 907538.92
SM-23-077 | 23MO-06E1 | Repair of Printer HP Laser Printer M451NW | Goods & Services | GSM |  | 2023-02-23 | 10:10AM |  | -44980 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 2500 | 2500
PP-23-078 | 23MO-01A | Supply and Delivery of Consolidated Commonly Used Supplies, 1st QTR | Goods & Services | GSM | 2023-02-22 | 2023-02-23 | 3:10PM |  | -44980 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 265541.82 | 265541.82
PIP-23-079 | 23MO-01A | Supply and Delivery of Laserjet Ink | Goods & Services |  | 2023-02-17 | 2023-02-27 | 9:30PM |  | -44984 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 30000 | 30000
PSD-23-080 | Approved Budget Realignment | Supply and Delivery of 2023 Wellness Tshirts | Goods & Services | GSM | 2023-02-16 | 2023-02-27 | 3:40PM |  | -44984 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 45900 | 45900
GAD-23-081 | 23MO-07E2 | Supply and Delivery of Tote Bags for 2023 National Womens Month Celebration | Goods & Services | GSM | 2023-02-27 | 2023-02-27 | 3:58PM |  | -44984 | GAD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 16000 | 16000
PIP-23-082 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station | Goods & Services |  | 2023-01-17 | 2023-03-02 | 9:30AM |  | -44987 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 142200 |  | 142200
PIP-23-083 | 23MO-06D2 | Supply and Delivery of Tires and Windshield Wipers | Goods & Services |  | 2023-02-22 | 2023-03-02 | 9:30AM |  | -44987 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 166800 | 166800
PSD-23-084 | 23MO-01H1A | Supply and Delivery of CY2023 Token For 30 Years Loyalty Service Awardees(Swiss Watch) | Goods & Services |  | 2023-02-28 | 2023-03-02 | 11:30AM |  | -44987 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 550000 | 550000
-23-085 | [8 empty] | 0
-23-086 | [8 empty] | 0
-23-087 | [8 empty] | 0
-23-088 | [8 empty] | 0
-23-089 | [8 empty] | 0
-23-090 | [8 empty] | 0
-23-091 | [8 empty] | 0
-23-092 | [8 empty] | 0
-23-093 | [8 empty] | 0
-23-094 | [8 empty] | 0
-23-095 | [8 empty] | 0
-23-096 | [8 empty] | 0
-23-097 | [8 empty] | 0
-23-098 | [8 empty] | 0
-23-099 | [8 empty] | 0
-23-100 | [8 empty] | 0
-23-101 | [8 empty] | 0
-23-102 | [8 empty] | 0
-23-103 | [8 empty] | 0
-23-104 | [8 empty] | 0
-23-105 | [8 empty] | 0
-23-106 | [8 empty] | 0
-23-107 | [8 empty] | 0
-23-108 | [8 empty] | 0
-23-109 | [8 empty] | 0
-23-110 | [8 empty] | 0
-23-111 | [8 empty] | 0
-23-112 | [8 empty] | 0
-23-113 | [8 empty] | 0
-23-114 | [8 empty] | 0
-23-115 | [8 empty] | 0
-23-116 | [8 empty] | 0
-23-117 | [8 empty] | 0
-23-118 | [8 empty] | 0
-23-119 | [8 empty] | 0
-23-120 | [8 empty] | 0
-23-121 | [8 empty] | 0
-23-122 | [8 empty] | 0
-23-123 | [8 empty] | 0
-23-124 | [8 empty] | 0
-23-125 | [8 empty] | 0
-23-126 | [8 empty] | 0
-23-127 | [8 empty] | 0
-23-128 | [8 empty] | 0
-23-129 | [8 empty] | 0
-23-130 | [8 empty] | 0
-23-131 | [8 empty] | 0
-23-132 | [8 empty] | 0
-23-133 | [8 empty] | 0
-23-134 | [8 empty] | 0
-23-135 | [8 empty] | 0
-23-136 | [8 empty] | 0
-23-137 | [8 empty] | 0
-23-138 | [8 empty] | 0
-23-139 | [8 empty] | 0
-23-140 | [8 empty] | 0
-23-141 | [8 empty] | 0
-23-142 | [8 empty] | 0
-23-143 | [8 empty] | 0
-23-144 | [8 empty] | 0
-23-145 | [8 empty] | 0
-23-146 | [8 empty] | 0
-23-147 | [8 empty] | 0
-23-148 | [8 empty] | 0
-23-149 | [8 empty] | 0
-23-150 | [8 empty] | 0
|  | PP-22-084 | 2022-05-11
51
Formulas:
Date PR Awarded = [Date of BAC Reso Reco Award]
Sub/Open of Bids = [Eligibility Check]
Date of BAC Reso Reco Award = [Date PR Awarded]
Eligibility Check = [Sub/Open of Bids]

## gppb (hidden)
| COMPANY: PHILIPPINE NATIONAL OIL COMPANY LOCATION: Bldg.6 Energy Center, Rizal Drive, BGC, Taguig SUBJECT: Procurement Monitoring |  |  |  |  | NOTE: 1.
[16 empty] | FAILED |  |  |  | ONGOING
[16 empty] | COMPLETED |  |  |  | AWARDED
| AS OF: | 2024-10-16
PR NO. | Code (PAP) *from APP | Procurement Program/Project | Classification *Goods and Services, Infrastructure or Cosnulting Services | Account Officer *Initials | Date of PR | Date PR Received | Time Received | Date PR Awarded | TAT (days) | PMO/ End-User | Is this an Early Procurement Activity? Y/N | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Winning Bidder | List of Invited Observers | Date of Receipt of Invitation | [7 empty] | Submitted to COA |  | Reason of Failure |  |  |  |  | Payment Oder No./Contract No. | STATUS / REMARKS *Ongoing / Completed | STATUS as of today
[13 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf / Negotiation | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Reso Reco Award | Notice of Award | Contract Signing/ PO | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/Acceptance (if applicable) | Submission to IAO | Submission to OGC |  | Rebid |  | Date of Failure of Bidding | Date of Memo to Proponent (Failure of Bid) | Date Received Memo by Proponent | Date of Submitted CSS Form
AWARDED
GSD-23-001 | 23MO-06B14 | Contract Services for the Preventive Maintenance of Two (2) Units Passenger Elevator at PNOC Bldg.6 for 2023 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-30 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | 2023-01-03 |  | 2023-02-23 | Jan-Dec |  | COB | 185327.09 | 185327.09 |  | 192757.8 | 192757.8 |  | KPI Elevators,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 1st - Over ABC | 2022-11-28 | 2022-11-28 | 2022-11-29 | 2023-01-31 |  | Awarded | Contract for pick up of Supplier
GSD-23-002 | 23MO-06B18 | Contract Services for the Preventive Maintenance of CCTV Surveillance System at PNOC Bldg.6, 5, Computer Bldg. & Compound Perimeter | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-27 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | N/A | 2023-01-03 | N/A | Jan-Dec |  | COB | 89888.04 | 89888.04 |  | 66666.67 | 66666.67 |  | Comparts Computer Sales | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [8 empty] | 2023-01-31 | PO#298646 | Awarded | Completed/Delivered
GSD-23-003 | 23MO-06B16 | Contract Services for the Maintenance of Fire Protection System at PNOC Bldg. 5&6 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-27 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | 2023-01-03 | 2023-05-02 | 2023-02-20 | Jan-Dec |  | COB | 333900 | 333900 |  | 310000 | 310000 |  | Lubricks Maintenance and Construction | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [8 empty] | 2023-01-31 | Contract #23-017 | Awarded | Completed/Delivered
GSD-23-004 | 23MO-06B15 | Contract Services for the Preventive Maintenance of Two (2) Units Passenger Elevator at PNOC Bldg.5 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-20 | 63 | GSD | Y | NP-SVP | N/A | 2022-10-28 | N/A | N/A | N/A | 2022-12-16 | N/A | 2022-12-20 | 2023-01-03 |  | 2023-02-23 | Jan-Dec |  | COB | 139920 | 139920 |  | 132000 | 132000 |  | Rockspeed Elevator and Escalator Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [8 empty] | 2023-01-31 |  | Awarded | Contract for pick up of Supplier
GSD-23-005 | 23MO-06B17 | Contract Services for the Water Chemical Treatment for PNOC Bldg. 5&6 | Goods & Services | CDBB | 2022-07-01 | 2022-10-18 | 3:11PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-12-15 | 2023-01-10 | 2023-02-06 | 2023-01-30 | Jan-Dec |  | COB | 400898.8 | 400898.8 |  | 308040 | 308040 |  | Impact One Nation Industrial Corp. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-08 | 2023-02-08 | 2023-02-08 |  | 1st - Non Compliance | 2022-11-15 | 2022-11-15 | 2022-11-15 | 2023-01-31 |  | Awarded | Contract drafting
GSD-23-006 | 23MO-05C13 | Rental of Photocopying Machines for the year 2023 for PNOC Offices @ BGC, Taguig City, ESB & PIP | Goods & Services | GSM | 2022-07-07 | 2022-10-18 | 1:00PM | 2022-11-29 | 42 | GSD | Y | NP-SVP | N/A | 2022-11-27 | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-11-29 | 2023-01-03 | 2023-03-15 | 2023-02-23 | Jan-Dec |  | COB | 680000 | 680000 |  | 639000 | 639000 |  | Photopro Trading & General Merchandise Co. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-04-12 | [5 empty] | 2023-01-31 | Contract #23-018 | Awarded | Completed/Delivered
GSD-23-007 | 23MO-02A | Supply and Delivery of Drinking Water | Goods & Services | HDVE | 2022-06-25 | 2022-10-18 | 2:51PM | 2022-11-22 | 35 | GSD | Y | NP-SVP | N/A | 2022-10-29 | N/A | N/A | N/A | 2022-11-08 | N/A | 2022-11-22 | 2023-01-04 | 2023-01-25 | 2023-01-18 | Mar-Dec |  | COB | 360000 | 360000 |  | 278400 | 278400 |  | MSDR Water Refilling Station | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-01-26 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-008 | 23MO-07D8 | 2023 Web Hosting and Maintenance for Document Tracking System | Goods & Services | CDBB | - | 2022-10-18 | 2:51PM | 2022-11-08 | 21 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-04 | N/A | 2022-11-08 | 2023-01-09 | 2023-01-30 | 2023-01-24 | Mar-Dec |  | COB | 239000 | 239000 |  | 238000 | 238000 |  | MYBUSYBEE INC. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 23-002 | Awarded | Completed/Delivered
GSD-23-009 | 23MO-05C13 | 2023 Messengerial Services | Goods & Services | HDVE | 2022-06-28 | 2022-10-18 | 2:51PM | 2022-12-20 | 63 | GSD | Y | PB | 2022-10-25 | 2022-10-28 | 2022-11-11 | 2022-11-24 | 2022-11-24 | 2022-12-06 | 2022-12-20 | 2022-12-20 | 2022-01-09 | 2023-01-24 | 2023-01-18 | Jan-Dec |  | COB | 2666000 | 2666000 |  | 2592831.24 | 2592831.24 |  | PRC Couirier & Maintenance Services | MBC, COA, PCCI | [7 empty] | 2023-01-25 | 2023-01-27 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-010 | 23MO-06H2 | Pest Control Services | Goods & Services | CDBB |  | 2022-10-18 |  | 2022-11-08 | 21 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-02 | N/A | 2022-11-08 | 2023-01-09 | N/A | N/A | Jan-Dec |  | COB | 103824 | 103824 |  | 100800 | 100800 |  | Rampest Control Services and Supplies Company | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298647 | Awarded | Completed/Delivered
ESB-23-011 | 23MO-05C12 | Preventive Maintenance of Truck Scale (Quarterly Check up and Calibration with ITDI Certificate) | Goods & Services | CDBB | 2022-07-11 | 2022-10-18 |  | 2022-11-22 | 35 | ESB | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-11-22 | N/A | 2023-01-10 | N/A | 30 days |  | COB | 83000 | 83000 |  | 83000 | 83000 |  | GCH International Mercantile, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298650 | Awarded | Completed/Delivered
GSD-23-012 | 23MO-05A | Janitorial Services | Goods & Services | CFCM | 2022-07-06 | 2022-10-18 | 8:55AM | 2023-01-17 | 91 | GSD | Y | PB | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2022-12-21 | 2023-01-12 | 2023-01-17 | 2023-01-18 | 2023-02-28 | 2023-02-27 | Jan-Dec |  | COB | 8680000 | 8680000 |  | 8453970.56 | 8453970.56 |  | Starcom Manpower and Allied Services | MBC, COA, PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [10 empty] | Contract#23-019 | Awarded | Completed/Delivered
GSD-23-013 | 23MO-05C7 | Maintenance Services | Goods & Services | CFCM | 2022-07-22 | 2022-10-18 | 3:50PM | 2023-01-17 | 91 | GSD | Y | PB | 2022-11-08 | 2022-11-16 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2022-12-21 | 2023-01-12 | 2023-01-17 | 2023-01-18 |  |  | Jan-Dec |  | COB | 3627000 | 3627000 |  | 3605545.91 | 3605545.91 |  | Servicio Filipino,Inc. | MBC, COA, PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [5 empty] | N/A | N/A | N/A | N/A | 2023-01-31 |  | Awarded | Completed/Delivered
ESB-23-014 | 23MO-04A3 | Engagement of 3rd party Laboratory Service provider to conduct Quarterly Ambient Air Monitoring And Raw Water Testing | Goods & Services | HDVE | 2022-08-10 | 2022-10-18 | 2:10PM | 2022-11-14 | 27 | ESB | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-11-14 | 2023-01-06 | 2023-02-02 | 2023-01-26 | Mar-Dec |  | COB | 228000 | 228000 |  | 221760 | 221760 |  | Berkman Systems,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-06 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
AM-23-016 | 23MO-06H2 | 2023 Pest Control Services - PNOC Staffhouse, Lamo,Limay, Bataan | Goods & Services | CDBB | 2022-08-23 | 2022-10-18 | 9:05AM | 2022-11-14 | 27 | AMD | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-08 | N/A | 2022-11-14 | N/A | 2023-01-09 | N/A | Jan-Dec |  | COB | 45000 | 45000 |  | 34000 | 34000 |  | RAM Pest Control Services & Supplies Phils. Co. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298648 | Awarded | Completed/Delivered
PIP-23-018 | 23MO-05C7 | Provision for Manpower for 2023 Custodial Services/Other General Services at PIP | Goods & Services | CFCM | 2022-08-23 | 2022-10-18 | 1:21PM | 2023-02-06 | 111 | PIP | Y | PB | 2022-11-22 | 2022-11-15 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2023-12-27 | 2023-01-31 | 2023-02-06 | 2023-02-14 | 2023-04-05 | 2023-02-27 | Mar-Dec |  | COB | 3794718.27 | 3794718.27 |  | 3794718.27 | 3794718.27 |  | Servicio Filipino, Inc. | MBC,COA,PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [11 empty] | Awarded | Completed/Delivered
AM-23-019 | Awaiting APP | Security Services for PNOC Provincial Properties | Goods & Services | RGV | 2022-08-31 | 2022-10-18 | 2:19PM | 2022-12-20 | 63 | AMD | Y | PB | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-11-15 | 2022-11-15 | 2022-12-19 | 2022-12-19 | 2022-12-20 | 2023-01-26 | 2023-02-20 | 2023-02-15 | Jan-Dec |  | COB | 6188770.36 | 6188770.36 |  | 5941511.28 | 5941511.28 |  | Eliteblue Security Specialists | MBC,COA,PCCI | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 |  | 2023-02-20 | 2023-02-20 | 2023-02-20 | [5 empty] | 2023-01-31 | Contract#012 | Awarded | Completed/Delivered
GSD-23-020 | 23MO-05B | Security Services for Head Office, PIP &ESB | Goods & Services | RGV | 2022-08-15 | 2022-10-18 | 9:16PM | 2023-01-12 | 86 | GSD | Y | PB | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-11-15 | 2022-11-15 | 2022-12-06 | 2023-01-05 | 2023-01-12 | 2023-01-26 | 2023-02-20 | 2023-02-20 | Jan-Dec |  | COB | 48611344.64 | 48611344.64 |  | 47781296.28 | 47781296.28 |  | Eliteblue Security Specialists | MBC,COA,PCCI | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 |  | 2023-03-20 | 2023-03-20 | 2023-03-20 | [5 empty] | 2023-01-31 | Contract #23-007/008/009 | Awarded | Completed/Delivered
ESB-23-021 | 23MO-05A | 2023 Custodial and Janitorial Services | Goods & Services | CFCM | 2022-09-14 | 2022-10-18 | 3:40PM | 2023-01-12 | 86 | ESB | Y | PB | 2022-11-03 | 2022-11-08 | 2022-11-15 | 2022-11-29 | 2022-11-29 | 2022-12-21 | 2023-01-12 | 2023-01-12 | 2023-01-31 | 2023-02-22 | 2023-02-20 | Jan-Dec |  | COB | 7530000 | 7530000 |  | 7451165.35 | 7451165.35 |  | Stewards Manpower Supply and Services | MBC,COA,PCCI | 2022-10-15 | 2022-10-15 | 2022-10-15 | 2022-10-15 | 2022-10-15 |  | 2023-05-05 | 2023-05-05 | 2023-05-05 | [5 empty] | 2023-01-31 | Contract #23-014 | Awarded | Completed/Delivered
PIP-23-022 | 23MO-05A | Supply of Manpower,Equipment and Supplies for Janitorial Services at PIP | Goods & Services | CFCM | 2022-08-23 | 2022-10-18 | 3:25PM | 2023-02-13 | 118 | PIP | Y | PB | 2022-11-17 | 2022-11-22 | 2022-11-29 | 2022-12-13 | 2022-12-13 | 2022-12-27 | 2023-01-31 | 2023-02-13 | 2023-02-20 | 2023-04-05 | 2023-02-28 | Mar-Dec |  | COB | 4304703.82 | 4304703.82 |  | 3916087.08 | 3916087.08 |  | Servicio Filipino,Inc. | MBC,COA,PCCI | 2022-11-18 | 2022-11-19 | 2022-11-20 | 2022-11-21 | 2022-11-22 | [10 empty] | Contract #23-021 | Awarded | Completed/Delivered
PIP-23-023 | 23CA-06A | Supply,Delivery, Testing and Commissioning of Brand New Fire Truck | Goods & Services | CFCM | 2022-10-05 | 2023-01-13 | 9:21AM | 2023-04-20 | 97 | PIP | Y | PB | 2023-01-19 | 2023-01-24 | 2023-01-31 | 2023-02-14 | 2023-02-14 | 2023-02-20 | 2023-03-30 | 2023-03-30 | 2023-04-27 |  |  | 180 days |  | COB | 29200000 |  | 29200000 | 28888888 |  | 28888888 | Boston Home Incorporated | MBC,COA,PCCI | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-01-31 | [5 empty] | 1st - Non Compliance | 2023-01-10 | 2023-01-11 | 2023-01-12 |  |  |  | Completed/Delivered
PIP-23-024 | 23MO-04A3 | Environmental Monitoring for 2023 (Waste Water-Effluent and Marine, Raw Water, Ambient Air Sampling and Laboratory Analysis | Goods & Services | CDBB | 2022-10-20 | 2023-01-19 | 5:01PM | 2023-03-16 | 56 | PIP | Y | PB |  |  | 2022-11-15 | 2023-01-05 | 2023-01-05 | 2023-01-09 | N/A | 2023-03-16 | 2023-03-16 | 2023-05-12 | 2023-03-21 | 1st -4th QTR |  | COB | 1032026.6 | 1032026.6 |  | 1002400 | 1002400 |  | CRL Environmental Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2022-12-12 | 1st-Non Comliance in Philgeps/2nd-Non-compliant in tech specs | 1st -12/2/2022/ 2nd- 1/17/2023 | 1st-12/2/2022 | 1st-12/5/22 |  | Contract #23-023 | Awarded | Completed/Delivered
AM-23-026 | Awaiting APP | 2023 Caretaker Services- Staffhouse, Lamao, Limay, Bataan | Goods & Services | HDVE | 2022-11-23 | 2022-11-28 | 8:55AM | 2023-01-05 | 38 | AMD | Y | NP-SVP | N/A | 2022-12-16 | N/A | N/A | N/A | 2023-12-21 | 2022-12-21 | 2023-01-05 | 2023-01-10 | 2023-02-14 | 2023-01-25 | Feb-Dec |  | COB | 322700 | 322700 |  | 320612.06 | 320612.06 |  | MMA Competent Manpower and General Services | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-02-23 | [5 empty] | 2023-01-31 | Contract#23-006 | Awarded` | Completed/Delivered
SM-23-027 | 23MO-03AA | 2023 PNOC Internet/Leased Line Connection Upgrade | Goods & Services | CFCM | 2022-11-18 | 2022-11-28 | 8:45AM | 2023-01-26 | 59 | SMO | Y | PB |  | 2022-12-06 | 2022-12-13 | 2022-12-27 | 2022-12-27 | 2023-01-05 | 2023-01-24 | 2023-01-26 | 2023-01-31 | 2023-02-17 | 2023-02-13 | Mar-Dec |  | COB | 1300000 | 1300000 |  | 610980 | 610980 |  | Source Telecommunications, Inc. | MBC,COA,PCCI | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 |  | 2023-05-17 | 2023-05-17 | 2023-05-17 | [5 empty] | 2023-01-31 | Contract #23-013 | Awarded | Completed/Delivered
PP-23-028 | 23MO-06C10 | Preventive Maintenance of PNOC Gym Equipment | Goods & Services | CDBB | 2022-12-07 | 2022-12-07 | 4:25PM | 2022-12-22 | 15 | PP | Y | NP-SVP | N/A | 2022-12-14 | N/A | N/A | N/A | 2022-12-20 | N/A | 2022-12-22 | N/A | 2023-01-09 | N/A | Jan-Dec |  | COB | 65000 | 65000 |  | 28800 | 28800 |  | The FITCO Inc (Stark Fitness) | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-01-10 |  | Superceded of PP-22-025 |  |  |  | 2023-01-31 | PO#298649 | Awarded | Completed/Delivered
PIP-23-029 | 23MO-01F131 | Supply and Delivery of 2023 Vehicle Sticker for PIP | Goods & Services | GSM | 2022-12-22 | 2022-01-03 | 1:30PM | 2023-02-14 | 407 | PIP | N | NP-SVP | N/A | 2023-01-23 | N/A | N/A | N/A | 2023-02-07 | N/A | 2023-02-14 | N/A | 2023-02-15 | N/A | 30 Days |  | COB | 9000 | 9000 |  | 6712.5 | 6712.5 |  | Forms International Enterprises,Corp. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-27 | [6 empty] | PO#298654 | Awarded | Completed/Delivered
PSD-23-031 | 23MO-07EB | Supply and Delivery of PNOC's 50th Anniversary T-shirt | Goods & Services | GSM | 2023-12-21 | 2023-01-11 | 10:41AM | 2023-02-09 | 29 | PSD | N | NP-SVP | N/A | 2023-01-17 | N/A | N/A | N/A | 2023-01-31 | N/A | 2023-02-09 | N/A | 2023-02-14 | N/A | 30 days |  | COB | 84000 | 84000 |  | 73500 | 73500 |  | Topsol Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298652 | Awarded | PO for Signature
SM-23-032 | 23MO-041D | Hiring of Certifying Body for PNOC QMS and Recertification | Consulting Services | CDBB | 2023-01-16 | 2023-01-12 | 10:55AM | 2023-05-16 | 124 | SMO | N | NP-SVP | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-05-12 | N/A | 2023-05-16 | N/A | 2023-05-18 | N/A |  |  | COB | 300000 | 300000 |  | 748440 | 748440 |  | SOCOTEC Certification Philippines,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 1st -2nd - Non Receipt of Quotation | 2nd : 4/19/2023 | 2nd : 4/19/2023 | 2nd : 4/19/2023 |  |  | Awarded | Contract for Signature of SOCOTEC
ESB-23-090 | 23MO-04B1C | Hiring of Certifying Body for PNOC ESB ISO 9001:2015 and ISO 45001:2018 and Recertification | Consulting Services | CDBB | 2023-01-16 | 2023-03-03 | 3:20PM | 2023-05-16 | 74 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | 2023-05-16 | N/A |  | N/A |  |  | COB | 500000 | 500000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A
ESB-23-033 | 23MO-06D5 | Supply and Delivery of Various Tires for ESB | Goods & Services | GSM | 2023-01-03 | 2023-01-13 | 9:26AM | 2023-02-06 | 24 | ESB | N | NP-SVP | N/A | 2023-01-17 | N/A | N/A | N/A | 2023-01-25 | N/A | 2023-02-06 | N/A | 2023-02-08 | N/A | 30 days |  | COB | 66000 | 66000 |  | 55300 | 55300 |  | Fleetserv Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-03 | [6 empty] | PO#298651 | Awarded | Completed/Delivered
PIP-23-035 | 23MO-04A2 | Hiring of EIA Report Consultant | Consulting Services | HDVE | 2023-01-11 | 2023-01-16 | 9:08AM | 2023-01-24 | 8 | PIP | N | NP-HT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-04-13 | 2023-03-31 |  |  | COB | 170000 | 170000 |  | 170000 | 170000 |  | Engr.Aldwin Camance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-04-13 | 2023-04-13 | 2023-04-13 | [5 empty] | 2023-01-31 | Contract #23-011 | Awarded | Completed/Delivered
ESB-23-036 | 23CA-01C | Upgrade and Improvement of Drainage System | Infrastructure | RGV | 2023-01-10 | 2023-01-17 | 1:23PM | 2023-03-14 | 56 | ESB | N | PB | 2023-01-24 | 2023-01-26 | 2023-02-02 | 2023-02-16 | 2023-02-16 | 2023-02-21 | 2023-03-13 | 2023-03-14 | 2023-03-15 | N/A | 2023-05-04 | 180 days |  | COB | 4550000 |  | 4550000 | 4532619.06 |  | 4532619.06 | RM Joyce Construction | MBC,COA,PCCI | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | [10 empty] | Contract #23-022 | Awarded | Completed/Delivered
SM-23-037 | 23MO-07E11 | Publication of the 50th Commemorative Book | Goods & Services | CFCM | 2023-01-18 | 2023-01-18 | 3:40PM | 2023-02-14 | 27 | SMO | N | NP-SVP | N/A | 2023-01-27 | N/A | N/A | N/A | 2023-02-08 | N/A | 2023-02-14 | 2023-02-15 | 2023-03-13 | 2023-03-08 | September |  | COB | 1000000 | 1000000 |  | 978000 | 978000 |  | VJ Graphics Arts,Inc. | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-05-22 | 2023-05-22 | 2023-05-22 |  |  | n |  |  |  |  | Awarded | Completed/Delivered
PIP-23-038 | 23MO-04A6 | Assessment of Jetty Facility and Hydrographic Survey | Consulting Services | RGV | 2023-01-19 | 2023-01-19 | 2:08PM | 2023-03-28 | 68 | PIP | N | PB |  | 2023-02-21 | 2023-02-28 | 2023-03-09 | 2023-03-09 | 2023-03-20 | n/A | 2023-03-28 | 2023-03-28 | 2023-05-10 | 2023-05-03 | 120 days |  | COB | 4800000 | 4800000 |  | 4799984 | 4799984 |  | A.C. Ong Consulting. Inc. | MBC,COA,PCCI | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 |  | 2023-05-12 | 2023-05-12 | [7 empty] | Contract #23-026 | Awarded | Completed/Delivered
PIP-23-039 | 23MO-05C9 | Annual Physical Examination (APE) for PIP | Goods & Services | GSM | 2023-01-19 | 2023-01-23 | 10:12AM | 2023-02-21 | 29 | PIP | N | NP-SVP | N/A | 2023-01-26 | N/A | N/A | N/A | 2023-02-15 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 95000 | 95000 |  | 44227.5 | 44227.5 |  | EDGT-LAB-Tech Diagnostic Center | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-07 | [6 empty] | PO#298658 | Awarded | Completed/Delivered
AS-23-040 | 23MO-041B1U | Hiring of Musical Director for 2023 | Goods & Services | HDVE |  | 2023-01-24 |  | 2023-01-24 | 0 | ASD | N | NP-SVP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-26 | 2023-03-10 | 2023-01-31 | Feb-Dec |  | COB | 420000 | 420000 |  | 385000 | 385000 |  | Anthony Go Villanueva | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-13 | [5 empty] | 2023-01-31 | #23-015 | Awarded | Completed/Delivered
PIP-23-041 | 23CA-01B | Fencing of Alberba Area (250m Length) | Infrastructure | CDBB | 2023-01-04 | 2023-01-24 | 3:14PM | 2023-04-25 | 91 | PIP | N | PB | N/A | 2023-01-31 | 2023-02-07 | 2023-02-21 | 2023-02-21 | 2023-04-04 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-05-30 | 2023-05-29 | 30 days |  | COB | 3460000 |  | 3460000 | 3074702.15 | 3074702.15 |  | AR. Esbi Construction | MBC,COA,PCCI | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | [10 empty] | 23-032 | Awarded | Completed/Delivered
ESB-23-042 | 23MO-01H2A | Supply, Delivery and Printing of Calling Cards (CBP) | Goods & Services | GSM | 2023-01-16 | 2023-01-31 | 2:30PM | 2023-02-21 | 21 | ESB | N | NP-SVP | N/A | 2023-02-06 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 3000 | 3000 |  | 2550 | 2550 |  | Forms International Enterprises Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298659 | Awarded | Completed/Delivered
PIP-23-043 | 23CA-04B3 | Supply, Delivery and Installation of Load Break Switch | Goods & Services | GSM | 2023-01-10 | 2023-01-30 | 8:49AM | 2023-02-28 | 29 | PIP | N | NP-SVP | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-21 | N/A | 2023-02-28 | 2023-03-01 | 2023-05-08 | 2023-04-26 | 30 days |  | COB | 489000 |  | 489000 | 439000 |  | 439000 | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | Contract #23-028 | Awarded | Completed/Delivered
PSD-23-044 | 23MO-01D | Supply and Delivery of COVID Supplies (Face Mask) for MAR-JUN | Goods & Services | CDBB | 2023-01-30 | 2023-01-31 | 2:30PM | 2023-02-14 | 14 | PSD | N | NP-SVP | N/A | 2023-02-01 | N/A | N/A | N/A | 2023-02-09 | N/A | 2023-02-14 | N/A | 2023-02-15 | N/A | 30 days |  | COB | 40000 | 40000 |  | 37584 | 37584 |  | SGS Healthcare Co. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-02-17 | [6 empty] | PO#298653 | Awarded | Completed/Delivered
PP-23-045 | 23MO-01H2B | Supply and Delivery Various Tissue | Goods & Services | CDBB | 2023-02-01 | 2023-02-02 | 11:03AM | 2023-02-16 | 14 | PRM | N | NP-SVP | N/A | 2023-02-03 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-02-16 | N/A | 2023-02-17 | N/A | 30 days |  | COB | 19076 | 19076 |  | 18600 | 18600 |  | Eco-Hygiene Institutional Sals Corp/Sanitary Care Products Asia,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-02-20 | [6 empty] | PO#298656/PO#298657 | Awarded | Completed/Delivered
BR-23-049 | 23MO-01H2A | Supply, Delivery and Printing of Calling Cards (MRCR) | Goods & Services | GSM | 2023-02-02 | 2023-02-02 | 3:20PM | 2023-02-21 | 19 | BRDD | N | NP-SVP | N/A | 2023-02-06 | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 1000 | 1000 |  | 850 | 850 |  | Forms International Enterprises Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298659 | Awarded | Completed/Delivered
GSD-23-051 | 23MO-01E1 | Supply and Delivery of Biometric Scanner | Goods & Services | CDBB | 2023-02-01 | 2023-02-03 | 1:37PM | 2023-02-16 | 13 | GSD | N | NP-SVP | N/A | 2023-02-07 | N/A | N/A | N/A | 2023-02-15 | N/A | 2023-02-16 | N/A | 2/17/23 | N/A | 30 days |  | COB | 20000 | 20000 |  | 20000 | 20000 |  | Comparts Computer Sales | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-02-20 | [6 empty] | PO#298655 | Awarded | Completed/Delivered
PIP-23-052 | 23MO-01H2J | Supply and Delivery of Various Fire Extinguisher | Goods & Services | CDBB | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-03-07 | 32 | PIP | N | NP-SVP | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-03-03 | N/A | 2023-03-07 | N/A | 2023-03-08 | N/A | 30 days |  | COB | 100000 | 100000 |  | 41750 | 41750 |  | A.D. Ramos Building Construction & Engineering Services | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-13 | [6 empty] | PO#298667 | Awarded | Completed/Delivered
PIP-23-054 | 23MO-01H2I | Life Ring | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A | 2023-03-03 | N/A | 30 days |  | COB | 16000 | 16000 |  | 33317.5 | 33317.5 |  | Safetyko Industrial Supplies | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-05-19 | [6 empty] | PO#298666 | Awarded | Completed/Delivered
PIP-23-055 | 23MO-01H2F | Cotton Gloves | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A | 30 days |  | COB | 2000 | 2000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/Delivered
PIP-23-056 | 23MO-01H2G | Hi-Visibility Vest/ Reflective Vest |  | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A | 30 days |  | COB | 3000 | 3000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/Delivered
PIP-23-057 | 23MO-01H2E | Safety Shoes | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A | 30 days |  | COB | 25000 | 25000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/Delivered
BR-23-058 | Approved Budget Realignment | Engagement of an individual consultant for the development of decentralized energy systems (DES)- solar PV Rooftop system in PNOC (ESB) | Consulting Services | CFCM | 2023-02-03 | 2023-02-06 | 8:38AM | 2023-03-24 | 46 | BRDD | N | NP-SVP | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-03-24 | 2023-03-24 | 2023-04-20 | 2023-04-18 | 30 days |  | COB | 500000 | 500000 |  | 421000 | 421000 |  | Engr. Adrian L. Rey | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st-Non Receipt of Quotation | 2023-03-01 | 2023-03-01 | 2023-03-01 |  | Contract #23-024 | Awarded | Completed/Delivered
GSD-23-059 | 23MO-01E4 | Supply and Delivery of Compressor Motor for Aircon at PNOC Records Bldg. | Goods & Services | GSM | 2023-02-02 | 2023-02-07 | 1:33PM | 2023-02-28 | 21 | GSD | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-20 | N/A | 2023-02-28 | N/A | 2023-03-03 | N/A |  |  | COB | 32000 | 32000 |  | 24990 | 24990 |  | Pumpcraft Industrial Sales | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298665 | Awarded | Completed/Delivered
PIP-23-062 | 23MO-06C1 | Calibration of Various Meters | Goods & Services | GSM | 2023-02-08 | 2023-02-10 | 1:15PM | 2023-03-02 | 20 | PIP | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-23 | N/A | 2023-03-02 | N/A | 2023-03-03 | N/A | 30 days |  | COB | 49000 | 49000 |  | 48300 | 48300 |  | Premier Physic Metrologie Co. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-16 | [6 empty] | PO#298664 | Awarded | Completed/Delivered
PIP-23-063 | 23MO-04B1N | Conduct of Work Measure Environment | Goods & Services | GSM | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-02 | 20 | PIP | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-28 | N/A | 2023-03-02 | N/A | 2023-03-03 | N/A |  |  | COB | 30000 | 30000 |  | 29456 | 29456 |  | CRL Calabarquez Corp. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-10 | [5 empty] | 2023-06-06 | PO#298663 | Awarded | Completed/Delivered
PIP-23-064 | 23MO-01H2H | Supply and Delivery of Dust Mask | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-09 | 27 | PIP | N | NP-SVP | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-09 | N/A | 2023-03-13 | N/A |  |  | COB | 3000 | 3000 |  | 2040 | 2040 |  | See More Enterprise Co | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-14 | [6 empty] | PO#298670 | Awarded | Completed/Delivered
PIP-23-065 | 23MO-01H2M | Supply and Delivery of various Other Supplies for Safety | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-09 | 27 | PIP | N | NP-SVP | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-09 | N/A | 2023-03-13 | N/A |  |  | COB | 68000 | 68000 |  | 32125 | 32125 |  | See More Enterprise Co/Villaflores Industrial Supply | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-14 | [6 empty] | PO#298670/298671 | Awarded | Completed/Delivered
PIP-23-066 | 23MO-07E5 | Supply and Delivery of Materials for the Coastal Clean-Up 2023 | Goods & Services | GSM | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-02-28 | 18 | PIP | N | NP-SVP | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-23 | N/A | 2023-02-28 | N/A | 2023-03-01 | N/A | 30 Days |  | COB | 35000 | 35000 |  | 29820 | 29820 |  | Ceboom Enterprises/Syner Graphics Co./ Safetyko | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298660/298661 | Awarded | Completed/Delivered
PIP-23-067 | 23MO-06C10 | Supply and Delivery of 100Watts LED Street Light | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-07 | 25 | PIP | N | NP-SVP | N/A | 2023-02-15 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-07 | N/A | 2023-03-08 | N/A | 30 Days |  | COB | 200000 | 200000 |  | 140000 | 140000 |  | West Point Engineering Supplies Incorporated | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-10 | [6 empty] | PO#298668 | Awarded | Completed/Delivered
PIP-23-068 | 23MO-01H2L | Supply and Delivery of Safety Hazards | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-09 | 27 | PIP | N | NP-SVP | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-09 | N/A | 2023-03-13 | N/A |  |  | COB | 22000 | 22000 |  | 16100 | 16100 |  | Villaflores Industrial Supply | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-14 | [6 empty] | PO#298671 | Awarded | Completed/Delivered
PSD-23-069 | 23MO-01H1C | Supply and Delivery of CY 2023 Token for Loyalty Service Awardees | Goods & Services | GSM | 2023-02-08 | 2023-02-13 | 10:31AM | 2023-03-23 | 38 | PSD | N | NP-SVP | N/A | 2023-02-28 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-03-23 | N/A | 2023-03-27 | N/A | 30 Days |  | COB | 160000 | 160000 |  | 88000 | 88000 |  | 3D Image Works and Design House | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298675 | Awarded | Completed/Delivered
PIP-23-070 | 23MO-06C12 | Preventive Maintenance Services of CCTV System for PIP | Goods & Services | GSM | 2023-02-22 | 2023-03-03 | 2:00PM | 2023-03-21 | 18 | PIP | N | NP-SVP | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-03-21 | 2023-03-27 | 2023-05-22 | 2023-03-28 | 30 days |  | COB | 171000 | 171000 |  | 112500 | 112500 |  | Compass Integrated Solutions,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | Contract #23-030 | Awarded | Completed/Delivered
PSD-23-071 | 23MO-01H1F/01H1D/01H1G | Supply and Delivery of CY 2023 Token for Loyalty Service Awardees & Retirees | Goods & Services | GSM | 2023-02-08 | 2023-02-15 | 3:57PM | 2023-03-21 | 34 | PSD | N | NP-SVP | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-03-21 | N/A | 2023-03-27 | N/A | 30 Days |  | COB | 48000 | 48000 |  | 46000 | 46000 |  | Ad-Man Resources Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298678/677 | Awarded | Completed/Delivered
PSD-23-072 | 23MO-01D | Supply and Delivery of Fluquadri Vaccine (Adult) | Goods & Services | CDBB | 2023-02-13 | 2023-02-14 | 4:07PM | 2023-03-02 | 16 | PSD | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-28 | N/A | 2023-03-02 | N/A | 2023-03-03 | N/A | 30 days |  | COB | 90000 | 90000 |  | 71003 | 71003 |  | Pharma Quest Co. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-06 | [6 empty] | PO#298662 | Awarded | Completed/Delivered
GAD-23-073 | 23MO-07E2 | Supply and Delivery of T-shirts for 2023 National Women's Month Celebration | Goods & Services | GSM |  | 2023-02-15 | 7:50AM | 2023-03-14 | 27 | GAD | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-27 | N/A | 2023-03-14 | N/A | 2023-03-14 | N/A |  |  | COB | 39300 | 39300 |  | 29260 | 29260 |  | Ceboom Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [8 empty] | 2023-05-25 | PO#298672 | Awarded | Completed/Delivered
SM-23-074 | 23MO-01A | Supply and Delivery of Stamp with Inscription | Goods & Services | GSM |  | 2023-02-16 |  | 2023-03-09 | 21 | SMO | N | NP-SVP | N/A | 2023-02-23 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-03-09 | N/A | 2023-03-10 | N/A | 30 days |  | COB | 3500 | 3500 |  | 3500 | 3500 |  | ZAB Enterprises Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-04-28 | [6 empty] | PO#298669 | Awarded | Completed/Delivered
GSD-23-075 | 23CA-03D | Exterior Repainting of Bldg.5 | Infrastructure | CFCM | 2023-02-10 | 2023-02-16 | 2:40PM | 2023-05-02 | 75 | GSD | N | PB | 2023-02-28 | 2023-03-02 | 2023-03-09 | 2023-03-23 | 2023-03-23 | 2023-03-30 | 2023-04-28 | 2023-05-02 | 2023-05-03 | 2023-06-05 | 2023-05-30 | 60 days |  | COB | 4500000 |  | 4500000 | 4217025 |  | 4217025 | Pablo S. Labasbas Construction Corporation | MBC,PCCI, COA | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-02-28 |  | 2023-06-23 | 2023-06-23 | 2023-06-23 | [6 empty] | Contract#23-034 | Awarded | Completed/Delivered
PP-23-076 | 23MO-01A | Supply and Delivery of Consolidated Computer Supplies, for 1st QTR year 2023 | Goods & Services | GSM | 2023-02-17 | 2023-02-17 | 3:05PM | 2023-05-02 | 74 | PRM | N | NP-SVP | N/A | 2023-03-25 | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-05-08 | N/A |  |  | COB | 907538.92 | 907538.92 |  | 700234.96 | 700234.96 |  | Accessories & Supplies Depot,Inc (ASDI)/PBT Technology Solutions,Inc/Philcopy Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298685/686/687 | Awarded | Completed/Delivered
PP-23-078 | 23MO-01A | Supply and Delivery of Consolidated Commonly Used Supplies, 1st QTR | Goods & Services | GSM | 2023-02-22 | 2023-02-23 | 3:10PM | 2023-06-27 | 124 | PRM | N | NP-SVP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | N/A |  | N/A |  |  | COB | 265541.82 | 265541.82 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/Delivered
PIP-23-079 | 23MO-01A | Supply and Delivery of Laserjet Ink | Goods & Services | GSM | 2023-02-17 | 2023-02-27 | 9:30PM | 2023-04-11 | 43 | PIP | N | NP-SVP | N/A | 2023-03-15 | N/A | N/A | N/A | 2023-03-29 | N/A | 2023-04-11 | N/A | 2023-04-13 | N/A | 30 Days |  | COB | 30000 | 30000 |  | 23664 | 23664 |  | Accessories & Supplies Depot,Inc (ASDI) | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298682 | Awarded | Completed/Delivered
PSD-23-080 | Approved Budget Realignment | Supply and Delivery of 2023 Wellness Tshirts | Goods & Services | GSM | 2023-02-16 | 2023-02-27 | 3:40PM | 2023-03-21 | 22 | PSD | N | NP-SVP | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-15 | N/A | 2023-03-21 | N/A | 2023-03-27 | N/A | 30 days |  | COB | 45900 | 45900 |  | 26010 | 26010 |  | Ceboom Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298679 | Awarded | Completed/Delivered
GAD-23-081 | 23MO-07E2 | Supply and Delivery of Tote Bags for 2023 National Womens Month Celebration | Goods & Services | GSM | 2023-02-27 | 2023-02-27 | 3:58PM | 2023-03-14 | 15 | GAD | N | NP-SVP | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-09 | N/A | 2023-03-14 | N/A | 2023-03-14 | N/A | 30 days |  | COB | 16000 | 16000 |  | 13440 | 13440 |  | King of Kings Trading | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [8 empty] | 2023-05-25 | PO#298673 | Awarded | Completed/Delivered
PIP-23-083 | 23MO-06D2 | Supply and Delivery of Tires and Windshield Wipers | Goods & Services | CDBB | 2023-02-22 | 2023-03-02 | 9:30AM | 2023-03-16 | 14 | PIP | N | NP-SVP | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-15 | N/A | 2023-03-16 | N/A | 2023-03-17 | N/A | 30 days |  | COB | 166800 | 166800 |  | 115800 | 115800 |  | MENDO Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-03-23 | [6 empty] | PO#298674 | Awarded | Completed/Delivered
PSD-23-084 | 23M0 -01H1A | Supply and Delivery of CY2023 Token For 30 Years Loyalty Service Awardees(Wrist Watch) | Goods & Services | GSM | 2023-02-28 | 2023-03-02 | 11:30AM | 2023-05-11 | 70 | PSD | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-11 | N/A | 2023-05-19 | N/A | 30 days |  | COB | 550000 | 550000 |  | 598080 | 598080 |  | Neuchatel, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298688 | Awarded | Completed/Delivered
PIP-23-086 | 23MO-01H2D | Supply and Delivery of Flags & Accessories | Goods & Services | GSM | 2023-02-27 | 2023-03-03 | 9:08AM | 2023-03-21 | 18 | PIP | N | NP-SVP | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-03-21 | N/A | 2023-03-27 | N/A | 30days |  | COB | 30000 | 30000 |  | 14070 | 14070 |  | Flags of All Nations | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298676 | Awarded | Completed/Delivered
SM-23-087 | 23MO-07D4 | Cloud Based Email Hosting | Goods & Services | CDBB |  | 2023-03-03 | 3:50PM | 2023-04-11 | 39 | SMO | N | NP-SVP | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-04-11 | 2023-04-12 | 2023-04-26 | 2023-04-25 | 29 days |  | COB | 330000 | 330000 |  | 298000 | 298000 |  | Tierra Networks Technologies Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | Superceded by SM-23-061 |  |  | Contract#23-025 | Awarded | Completed/Delivered
PSD-23-088 | 23MO-05C6 | Temporary Office Services | Goods & Services | CDBB | 2023-03-02 | 2023-03-06 | 9:25PM | 2023-03-21 | 15 | PSD | N | NP-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 |  | 2023-03-27 | April- December |  | COB | 5000000 | 5000000 |  | 4812586.65 | 4812586.65 |  | LBP Resources and Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded
GSD-23-089 | 23MO-01E3 | Audio/Video Player w/ Wireless Microphone | Goods & Services | GSM | 2023-03-03 | 2023-03-07 | 11:20PM | 2023-03-30 | 23 | GSD | N | NP-SVP | N/A | 2023-03-15 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-03-30 | N/A | 2023-04-03 | N/A | 30 days |  | COB | 28000 | 28000 |  | 27995 | 27995 |  | Uly Tech Trading | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2023-04-13 | [6 empty] | PO#29861 | Awarded | Completed/Delivered
ESB-23-091 | Approved Budget Realignment | Engagement of Consultancy Firm for the Preparation of Engineering Geological and Geohazard Assessment Report | Consulting Services | CFCM | 2023-02-01 | 2023-04-18 | 10:55PM | 2023-05-23 | 35 | ESB | N | NP-SVP | N/A | 2023-04-20 | N/A | N/A | N/A | 2023-05-18 | N/A | 2023-05-23 | 2023-05-24 |  | 2023-06-23 | 30 days |  | COB | 200000 | 200000 |  | 199200 | 199200 |  | Woodfields Consultants, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st&2nd -Non Receipt/3rd - deferred lack of detailed Presentation | 3/28/2023- 4/17/23 | 3/28/2023- 4/17/23 | 3/28/2023- 4/17/23 |  |  | Awarded | Completed/Delivered
PIP-23-092 | 23MO-06C16 | Supply and Delivery of Various Paints | Goods & Services | GSM | 2023-01-24 | 2023-03-10 | 3:40PM | 2023-05-25 | 76 | PIP | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-19 | N/A | 2023-05-25 | N/A | 2023-05-29 | N/A | 30 days |  | COB | 99555 | 99555 |  | 99376.1 | 99376.1 |  | Shigan Construction Supplies Trading | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 1st - Over ABC | 2023-03-27 | 2023-03-27 | 2023-03-28 |  | PO#298693 | Awarded | Completed/Delivered
PIP-23-093 | 23MO-06C9 | Supply and Delivery of Mechanical Consumables for Booster Pumps | Goods & Services | GSM | 2023-01-24 | 2023-03-10 | 3:40PM | 2023-05-30 | 81 | PIP | N | NP-SVP | N/A | 2023-03-18 | N/A | N/A | N/A | 2023-05-26 | N/A | 2023-05-30 | N/A | 2023-06-01 | N/A | 30 days |  | COB | 324632.79 | 324632.79 |  | 157718 | 157718 |  | Manara Marketing | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298696 | Awarded | Completed/Delivered
GSD-23-094 | 23MO-06C16 | Supply and Replacement of 1125kva Caterpillar Genset Motor Starter at PNOC Bldg.5 | Goods & Services | GSM | 2023-02-27 | 2023-03-15 | 3:30PM | 2023-04-13 | 29 | GSD | N | NP-SVP | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-04-13 | 2023-04-17 | 2023-05-31 | 2023-05-18 | 30 days |  | COB | 482000 | 482000 |  | 399764.46 | 399764.46 |  | Tabuko Energy Network Corp. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | Contract #23-029 | Awarded | Completed/Delivered
PP-23-096 | 23CA-04A10 | Supply, Design, Develop and Installation of PNOC Asset Inventory Management System | Goods & Services | CDBB | 2023-03-13 | 2023-03-16 | 1:27PM | 2023-03-23 | 7 | PRM | N | PB-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-24 | Contract draft |  |  |  | COB | 3640000 | 3640000 |  | 28000000 |  | 28000000 | DBP DATA Center Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/Delivered
PSD -23-097 | 23MO-04B1R | Engagement of Retainer Physician for PNOC Head Office | Goods & Services | GSM | 2023-03-13 | 2023-03-21 | 9:30AM | 2023-03-30 | 9 | PSD | N | NP-SVP | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-03-30 | N/A | 2023-03-30 | 2023-03-30 | 2023-05-04 | 2023-03-31 | April- December |  | COB | 399999.78 | 399999.78 |  | 399000 | 399000 |  | Dra. Marie Yvette Soriano-Jarmillo,MD,FPCOM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | Contract#23-027 | Awarded | Completed/Delivered
PIP-23-098 | 23CA-05B | Purchase, Supply and Delivery of Three Wheel Electric Motorcycle | Goods & Services | GSM | 2023-03-17 | 2023-03-22 | 9:43AM | 2023-04-11 | 20 | PIP | N | NP-SVP | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-04-04 | N/A | 2023-04-11 | N/A | 2023-04-13 | N/A | 29 days |  | COB | 195000 | 195000 |  | 194640 |  | 194640 | Marquay Trading OPC | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#28683 | Awarded | Completed/Delivered
AM-23-099 | 23CA-03T | PNOC Staffhouse Buildings Repair (Re-roofing and re-painting | Infrastructure | CDBB | 2023-03-21 | 2023-03-24 | 11:29AM | 2023-05-30 | 67 | AMD | N | PB |  | 2023-04-11 | 2023-04-18 | 2023-05-04 | 2023-05-04 | 2023-05-17 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-23 | 2023-06-20 | 30 days |  | COB | 1499099.77 | 1499099.77 |  | 1472193.8 |  | 1472193.8 | De Jesus Construction | COA,MBC,PCCI | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | Awarded | Completed/Delivered
PIP-23-100 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station | Goods & Services | CDBB | 2023-03-15 | 2023-04-11 | 4:42PM | 2023-05-11 | 30 | PIP | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-05-02 | N/A |  | N/A |  |  | COB | 142200 |  | 142200 | 39132.5 |  | 39132.5 | RBC (Mariveles)hardware, Inc./UpTown Industrial Sales, Inc, | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | Superceded by PIP-23-082 | 2nd- Non receipt | 2023-04-05 | 2023-04-05 | 2023-04-11 | 2023-06-06 | PO#298689/690 | Awarded | Not all Items are Awarded
PSD-23-101 | Approved Budget Reallocation | Conduct of QMS Appreciation Tranings | Goods & Services | GSM | 2023-03-22 | 2023-03-27 | 3:40pm | 2023-05-02 | 36 | PSD | N | NP-SVP | N/A | 2023-04-01 | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-05-02 | 2023-05-04 | 2023-05-22 | 2023-05-19 |  |  | COB | 151200 | 151200 |  | 120000 | 120000 |  | JBDC Occupational Health Safety and Environmental Consultancy | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | Contract # 23-031 | Awarded | Completed/Delivered
SM-23-102 | 23CA-04A2 | Supply and Delivery of Desktop Computer | Goods & Services | CDBB |  | 2023-03-29 | 3:31PM | 2023-03-30 | 1 | SMO | N | NP-SVP | N/A | [5 empty] | N/A |  | N/A | 2023-03-31 | N/A |  |  | COB | 689000 |  | 689000 | 689000 |  | 689000 | Columbia Technologies Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298680 | Awarded | Completed/Delivered
PSD-23-103 | 23MO-07E10 | Venue Rental for PNOC 50th Anniversary | Goods & Services | CDBB | 2023-03-29 | 2023-04-03 | 4:14PM | 2023-05-16 | 43 | PSD | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-10 | N/A | 2023-05-16 | 2023-05-19 |  |  | 1 day |  | COB | 703000 | 703000 |  | 702744 | 702744 |  | The Marquiz Events Place | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/Delivered
AM-23-105 | 23MO-01E7 | Supply and Delivery of Electronic Typewriter | Goods & Services | GSM | 2023-03-30 | 2023-06-13 | 10:05AM | 2023-07-04 | 21 | AMD | N | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-06-27 | N/A | 2023-07-04 | N/A |  | N/A | 30 days | COB | 45000 | 45000 |  | 82380 | 82380 |  | Business Machine Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 1st -Over ABC | 2023-06-06 | 2023-06-06 | 2023-06-06 |  |  | Awarded | For PO
TD-23-150 | Approved Budget Realignment | Supply and Delivery of Electronic Typewriter and its comsumable | Goods & Services | GSM | 2023-06-09 | 2023-06-13 | 11:05AM | 2023-07-04 | 21 | TD | N | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-06-26 | N/A | 2023-07-04 | N/A |  | N/A | 30 days | COB | 45000 | 45000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | For PO
ESB-23-106 | 23MO-O1H2 | Supply and Delivery of PPE's and Other Safety Equipments | Goods & Services | GSM | 2023-03-29 | 2023-04-04 | 9:30AM | 2023-06-06 | 63 | ESB | N | NP-SVP | N/A | 2023-05-11 | N/A | N/A | N/A | 2023-06-01 | N/A | 2023-06-06 | N/A | 2023-06-08 | N/A | 30 days |  | COB | 59000 | 59000 |  | 44919.1 | 44919.1 |  | Safetyko Industrial Supplies /Glim Diversified Sales and Services Corp./B2B Non-Specialized Wholesale Trading | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298697/698/699 | Awarded | Completed/Delivered
PSD-23-108 | 23MO-07E12 | Supply and Delivery of PNOC 50th Anniversary T-shirt with Collar/with cuff | Goods & Services | CDBB | 2023-03-31 | 2023-04-04 | 2:53PM | 2023-05-04 | 30 | PSD | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-04 | N/A |  | N/A |  |  | COB | 75250 | 75250 |  | 70520 | 70520 |  | King of Kings Trading | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298684 | Awarded | Completed/Delivered
SM-23-109 | 23MO-0782 | Printing of 2024 Wall and Desk Calendars | Goods & Services | CFCM | 2023-04-23 | 2023-04-04 | 3:24PM | 2023-11-05 | 215 | SMO | N | NP-SVP | N/A | 2023-04-21 | N/A | N/A | N/A | 2023-10-05 | N/A | 2023-05-11 | 2023-05-12 | 2023-06-07 | 2023-06-01 |  |  | COB | 650000 | 650000 |  | 418845 | 418845 |  | VJ Graphic Arts, inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#23-033 | Awarded | Completed/Delivered
PP-23-110 | 23MO-01C/01B | Supply and Delivery of Consolidated Office Forms (Accountable/Non-Accountable Forms) | Goods & Services | GSM | 2023-04-05 | 2023-04-11 | 9:09AM | 2023-06-20 | 70 | PRM | N | NP-SVP | N/A | 2023-06-10 | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | [5 empty] | COB | 198420.48 | 198420.48 |  | 144444 | 144444 |  | Grandsmart Enterprise | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/Delivered
GSD-23-112 | 23CA-03B | Replacement of Ceiling Mounted ACU at server room | Goods & Services | GSM | 2023-03-30 | 2023-04-14 | 8:18AM | 2023-05-16 | 32 | GSD | N | NP-SVP | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-05-11 | N/A | 2023-05-16 | 2023-05-17 |  |  |  |  | COB | 355806 | 355806 |  | 300000 |  | 300000 | Caresystem Technology Solution Co | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/Delivered
GSD-23-116 | 23CA-03I | Preventive Maintenance of 500kw and 2x900kw Stand-by Generator Sets at PNOC Building 5 and 6 | Goods & Services | GSM | 2023-04-13 | 2023-04-25 | 8:35AM | 2023-06-07 | 43 | GSD | N | NP-SVP | N/A | 2023-05-16 | N/A | N/A | N/A | 2023-05-24 | N/A | 2023-06-07 | 2023-06-07 |  |  |  |  | COB | 550145.47 |  | 550145.47 | 444000 |  | 444000 | 3J Power Contruction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/Delivered
GSD-23-118 | 23MO-04B15/04B1T | Fleet Monitoring System for PNOC Pooled Vehicle | Goods & Services | CDBB | 2023-04-14 | 2023-04-27 | 8:35AM | 2023-05-23 | 26 | GSD | N | NP-SVP | N/A | 2023-05-09 | N/A | N/A | N/A | 2023-05-17 | N/A | 2023-05-23 | N/A | 2023-05-24 | N/A | 30 days |  | COB | 90000 | 90000 |  | 89936 | 89936 |  | Cartrack Technologies Phl Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298692 | Awarded | Completed/ Delivered
GSD-23-121 | Approved Budget Realignment | Dismantling and Repair of Transfer Pump at PNOC Bldg 6 | Goods & Services | CDBB | 2023-02-27 | 2023-05-02 | 2:14PM | 2023-05-23 | 21 | GSD | N | NP-SVP | N/A | 2023-05-09 | N/A | N/A | N/A | 2023-05-24 | N/A | 2023-05-25 | 2023-06-02 |  |  | 30 days |  | COB | 240000 |  | 240000 | 200000 | 200000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Completed/ Delivered
GSD-23-124 | 23MO-01H2V | Supply and Delivery of Microfiber Washable PPE | Goods & Services | GSM | 2023-05-04 | 2023-05-05 | 8:40PM | 2023-05-23 | 18 | GSD | N | NP-SVP | N/A | 2023-05-10 | N/A | N/A | N/A | 2023-05-17 | N/A | 2023-05-23 | N/A | 2023-05-23 | N/A | 30 days |  | COB | 5133.3 | 5133.3 |  | 5133.3 | 5133.3 |  | Safetyko Industrial Supplies | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298691 | Awarded | Completed/ Delivered
PSD-23-125 | Approved Budget Realignment | Engagement of a Training Provider for the Conduct of an IQMS Audit Training | Goods & Services | GSM | 2023-05-02 | 2023-05-05 | 2:19PM | 2023-05-30 | 25 | PSD | N | NP-SVP | N/A | 2023-05-11 | N/A | N/A | N/A | 2023-05-25 | N/A | 2023-05-30 | N/A | 2023-05-31 | N/A | 30 days |  | COB | 200000 |  | 200000 | 60000 |  | 60000 | RPM Methods, Strategies and Documentation Services | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [8 empty] | 2023-06-07 | PO#298695 | Awarded | Completed/ Delivered
PIP-23-127 | 23MO-01H2M | Supply and Delivery of Consumables for AED | Goods & Services | CDBB | 2023-04-13 | 2023-05-05 | 3:25PM | 2023-05-25 | 20 | PIP | N | NP-SVP | N/A | 2023-05-10 | N/A | N/A | N/A | 2023-05-19 | N/A | 2023-05-25 | N/A | 2023-05-30 | N/A | 30 days |  | COB | 20000 | 20000 |  | 20000 | 20000 |  | Sy Medical Training Corp. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298694 | Awarded | Completed/Delivered
PIP-23-128 | 23MO-05C3 | Hauling Transport, Treatment and Disposal of Generated Wastes (Non-hazardous Solid Wastes | Goods & Services | GSM |  | 2023-05-05 | 3:25PM | 2023-06-07 | 33 | PIP | N | NP-SVP | N/A | 2023-05-16 | N/A | N/A | N/A | 2023-05-31 | N/A | 2023-06-17 | 2023-06-14 |  |  |  |  | COB | 123200 | 123200 |  | 122000 | 122000 |  | Clean Leaf International Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | Superceded by PIP-23-053 |  |  |  | Awarded | For Contract Drafting
GSD-23-131 | 23MO-01E5 | Supply and Delivery of Various Maintenance Tools | Goods & Services | CDBB | 2023-05-05 | 2023-05-12 | 10:03AM | 2023-06-08 | 27 | GSD | N | NP-SVP | N/A | 2023-05-23 | N/A | N/A | N/A | 2023-06-05 | N/A | 2023-06-08 | N/A | 2023-06-09 | N/A | 30 days |  | COB | 86378.67 | 86378.67 |  | 29465.2 | 29465.2 |  | KOI Industrial Supply/Co Ban Kiat Hardware Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298700/701 | Awarded | Completed/Delivered
PIP-23-132 | 23MO-06C13 | Supply and Delivery of Material for the Replacement of Existing Submersible Cable of PW6 and PW7 at PIP | Goods & Services | GSM | 2023-04-26 | 2023-05-12 | 11:02AM | 2023-06-20 | 39 | PIP | N | NP-SVP | N/A | 2023-05-23 | N/A | N/A | N/A | 2023-06-19 | N/A | 2023-06-20 | N/A | 2023-06-22 | N/A | 30 Days |  | COB | 370333 | 370333 |  | 265000 | 265000 |  | Pumpcraft Industrial Sales | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298703 | Awarded | Completed/ Delivered
PIP-23-134 | 23MO-01H2M | Supply and Delivery of Conference Chair | Goods & Services | GSM | 2023-04-27 | 2023-05-22 | 8:55AM | 2023-06-22 | 31 | PIP | N | NP-SVP | N/A | 2023-05-27 | N/A | N/A | N/A | 2023-06-21 | N/A | 2023-06-22 | N/A | 2023-06-30 | N/A | 30 days |  | COB | 64000 | 64000 |  | 55192 | 55192 |  | IKF Home Furnishing & office Furniture | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298709 | Awarded | Completed/ Delivered
PIP-23-135 | 23MO-06C2/06C3 | Calibration of Pressure Gauge,UFM abd Flow Totalizer | Goods & Services | GSM | 2023-05-18 | 2023-05-23 | 8:55AM | 2023-06-22 | 30 | PIP | N | NP-SVP | N/A | 2023-05-27 | N/A | N/A | N/A | 2023-06-14 | N/A | 2023-06-22 | N/A | 2023-06-30 | N/A | 30 days |  | COB | 153800 | 153800 |  | 142240 | 142240 |  | Senze Calibration and Measurement Laboratory, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298708 | Awarded | Completed/ Delivered
GSD-23-137 | 23CA-03K | Supply and Installation of Concrete Pole at Records Center | Goods & Services | CDBB | 2023-05-15 | 2023-05-23 | 9:15AM | 2023-06-13 | 21 | GSD | N | NP-SVP | N/A | 2023-05-27 | N/A | N/A | N/A | 2023-06-09 | N/A | 2023-06-13 | 2023-06-15 |  |  |  |  | COB | 515833.4 |  | 515833.4 | 470000 |  | 470000 | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | For Contract Drafting
ESB-23-139 | 23MO-06G1 | Supply and Delivery of Screw Pin Anchor Shackle, Galvanized | Goods & Services | CDBB | 2023-05-22 | 2023-05-24 | 2:58PM | 2023-06-20 | 27 | ESB | N | NP-SVP | N/A | 2023-05-30 | N/A | N/A | N/A | 2023-06-09 | N/A | 2023-06-20 | N/A | 2023-06-22 | N/A | 30 Days |  | COB | 18800 | 18800 |  | 10880 | 10880 |  | Villaflores Industrial Supply | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298702 | Awarded
PIP-23-143 | 23MO-01H2M | Purchase, Supply and Delivery of Foldable platform Truck Trolley and Vacuum Cleaner | Goods & Services | CDBB | 2023-05-22 | 2023-05-29 | 9:03AM | 2023-06-27 | 29 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 11000 | 11000 |  | 4900 | 4900 |  | Co Ban Kiat Hardware Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298706 | Awarded | Vacuum Only
PP-23-146 | 23MO-06C18 | Repair/Refurbishing of Furniture | Goods & Services | GSM | 2023-06-01 | 2023-06-06 | 2:40PM | 2023-06-27 | 21 | PRM | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-06-22 | N/A | 2023-06-27 |  |  |  | 30 days |  | COB | 110000 | 110000 |  | 69680.2 | 69680.2 |  | Dargo Design Component Builders Corp. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298706 | Awarded | For PO
PSD-23-149 | 23MO-01D | Supply and Delivery of COVID Response Disinfectant Supplies (Face Mask) for JUL-OCT 2023) | Goods & Services | CDBB | 2023-06-06 | 2023-06-07 | 3:00PM | 2023-06-27 | 20 | PSD | N | NP-SVP | N/A | 2023-06-09 | N/A | N/A | N/A | 2023-06-20 | N/A | 2023-06-27 | N/A |  | N/A | 30 days |  | COB | 54250 | 54250 |  | 34650 | 34650 |  | Ban Bee Commercial Co | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | For PO
PIP-23-159 | 23MO-07E7 | Materials for the 2023 Tree Planting Activity | Goods & Services | CDBB | 2023-06-14 | 2023-06-20 | 8:45AM | 2023-06-29 | 9 | PIP | N | NP-SVP | N/A | 2023-06-23 | N/A | N/A | N/A | 2023-06-26 | N/A | 2023-06-29 | N/A | 2023-06-29 | N/A | 30 days |  | COB | 38200 | 38200 |  | 30332 | 30332 |  | Ceboom Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | PO#298705 | Awarded | For PO
| Total Alloted Budget of Procurement Activities | [26 empty] | 117772737.2
| Total Contract Price of Procurement Activities Conducted | [28 empty] | 179983652.5
| Total Savings (Total Alloted Budget - Total Contract Price) | [30 empty] | 69746498.36
ONGOING
PIP-23-034 | 23CA-03C2 | Replacement of Fire Engine for Jetty and Controls - 1 Unit | Goods & Services | CDBB | 2023-01-05 | 2023-01-13 | 10:01AM |  | -44939 | PIP | N | PB | 2023-01-19 | 2023-01-24 | 2023-01-31 | 2023-02-14 | 2023-02-14 | [8 empty] | COB | 22150 |  | 22150 | [15 empty] | 1st-Non-submission of bid | 2023-02-14 | 2023-02-14 |  |  |  |  | Waiting for Update from PIP
ESB-23-046 | 23CA-MYB1A | Flattening of the Hilly Area | Infrastructure | RGV | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | [13 empty] | COB | 53540000 |  | 53540000 | [22 empty] | For Rebidding
ESB-23-047 | 23CA-MYB3A1 | Construction of New Pier | Infrastructure | RGV | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | [13 empty] | COB | 1402039.17 |  | 1402039.17 | [22 empty] | Ongoing - Post Qualification
ESB-23-048 | 23CA-MYB3A2 | Consulting Serviices for the Construction Management of the Construction of New Pier (ESB Port Dev't Option 1-Scheme B) and Flattening of the Hilly Area (Phase 1) | Consulting Services | CFCM | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | [13 empty] | COB | 43951025 |  | 43951025 | [22 empty] | Ongoing - Post Qualification
AM-23-095 | 23MO-04B1E/04B1G/04B1I | Land Surveying Consultancy (Relocation,Subdivision,Leased Area Surveys,As-built survey of PNOC Properties located in Kananga ,Leyte, Limay and Mariveles | Consulting Services | CFCM | 2023-03-14 | 2023-03-16 | 3:30PM |  | -45001 | AMD | N | PB | [13 empty] | COB | 1130000 | 1130000 | [23 empty] | Ongoing - Technical/Financial Evaluation
ESB-23-104 | 23MO-06D5 | Preventive Maintenance Services of Forklift (JAC CPCD 50H | Goods & Services | GSM | 2023-03-29 | 2023-04-03 | 1:54PM |  | -45019 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 26650 | 26650 | [16 empty] | 1st- Over ABC | 2023-05-09 | 2023-05-09 | 2023-05-09 |  |  |  | Ongoing-For Technical Evaluation
ESB-23-107 | 23MO-01H2C | Supply and Delivery of Safety Signages and Vehicle Sticker | Goods & Services | GSM | 2023-03-31 | 2023-04-04 |  |  | -45020 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 45517 | [24 empty] | Ongoing
ESB-23-111 | 23MO | Supply and Delivery of Materials for 2023 ESB Annual Maintenance Plan | Goods & Services | GSM | 2023-04-11 | 2023-04-13 | 8:49PM |  | -45029 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 593536 | 593536 | [23 empty] | Ongoing
PIP-23-113 | 23CA-02A2 | Supply, Delivery, Installation, testing and Commissioning of Level Sensors | Goods & Services | CDBB | 2023-03-10 | 2023-04-14 | 8:40AM |  | -45030 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 849500 |  | 849500 | [15 empty] | 1st -Non Receipt | 2023-05-16 | 2023-05-16 | 2023-05-16 |  |  |  | Ongoing
AM-23-114 | 23MO-04B1F | Third Party Appraisal of Various PNOC Properties | Consulting Services | CFCM | 2023-04-14 | 2023-06-09 | 4:30PM |  | -45086 | AMD | N | PB | [13 empty] | COB | 1600000 | 1600000 | [16 empty] | 1sT- Ineligible | 2023-05-30 | 2023-05-30 | 2023-05-30 |  |  |  | Ongoing
GSD-23-115 | 23CA-03A/23CA-03G | Waterproofing of PNOC Bldg.5 & 6 | Goods & Services | CDBB | 2023-04-17 | 2023-06-08 | 4:05PM |  | -45085 | GSD | N | PB |  |  | 2023-05-16 | [10 empty] | COB | 4200000 |  | 4200000 |  |  |  |  | COA,MBC,PCCI | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-05-16 | 2023-05-16 | [5 empty] | 1st- Non-compliance | 2023-06-06 | 2023-06-06 | 2023-06-06 |  |  |  | Ongoing
ESB-23-117 | 23CA-03V | Supply and Delivery of Foam-Filled Rubber Fender without Tire Net | Goods & Services | CFCM | 2023-04-24 | 2023-04-25 | 1:36PM |  | -45041 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 980000 |  | 980000 | [22 empty] | Ongoing
PIP-23-119 | 23MO-05C5 | Servicing of Genset | Goods & Services | GSM | 2023-04-20 | 2023-04-27 | 8:59AM |  | -45043 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 64685 | 64685 | [23 empty] | Ongoing
GSD-23-120 | 23CA-03G | Repair/Repainting of Compound Perimeter fence | Goods & Services | RGV | 2023-04-13 | 2023-05-02 | 2:14PM |  | -45048 | GSD | N | PB | 2023-05-11 | 2023-05-16 | 2023-05-23 | 2023-06-08 | 2023-06-08 | 2023-06-13 | [7 empty] | COB | 2800000 |  | 2800000 |  |  |  |  | COA,MBC,PCCI | [17 empty] | Ongoing
GSD-23-122 | Approved Budget Realignment | Replacement of Various Defective Parts of Passenger Elevators at PNOC Bldg.6 | Goods & Services | GSM | 2023-04-13 | 2023-05-02 | 2:14PM |  | -45048 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 137321.42 |  | 137321.42 | [22 empty] | Ongoing
GSD-23-123 | Approved Budget Realignment | De-sludging of PNOC Bldg.6,5.3 and Motorpool Septic Tanks | Goods & Services | GSM | 2023-03-16 | 2023-05-24 | 2:14PM |  | -45070 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 357000 |  | 357000 | [15 empty] | 1st -over ABC | 2023-05-17 | 2023-05-17 | 2023-05-17 |  |  |  | Ongoing-For Re-Evaluation
PSD-23-126 | Approved Budget Realignment | Conduct of Advanced Training on the use, Application and Writeshop on the Harmonized GAD Guidelines | Goods & Services | CDBB | 2023-04-27 | 2023-05-05 | 2:19PM |  | -45051 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 38500 |  | 38500 | [22 empty] | Ongoing-For Technical Evaluation
SM-23-130 | 23CA-04A3 | Supply and Delivery of Rack/Computer Server | Goods & Services | CDBB |  | 2023-05-11 | 9:04AM |  | -45057 | SMO | N | PB | [13 empty] | COB | 1002806.67 |  | 1002806.67 | [22 empty] | Ongoing- Post Qualification
PIP-23-133 | 23CA-03M | Supply and Delivery of Materials for the Replacement of Damaged Feeder line of R1 | Goods & Services | GSM | 2023-05-14 | 2023-05-12 | 11:02AM |  | -45058 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 83484 |  | 83484 | [22 empty] | For Award
BR-23-136 | 23MO-04A1 | Engagement of Project Consultant for the Development of the PNOC Bunker Fuel Refilling Station | Consulting Services | CFCM | 2023-05-17 | 2023-05-23 | 3:52PM |  | -45069 | BRDD | N | PB | [13 empty] | COB | 9500000 | 9500000 | [23 empty] | Referred Back to Proponent
PSD-23-138 | Approved Budget Inclusion | 2023 PNOC Health and Wellness Program Dance Instructor | Goods & Services | CDBB | 2023-05-22 | 2023-06-20 | 4:55PM |  | -45097 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 265000 | 265000 | [16 empty] | 1st-Non receipt Quotation | 2023-06-19 | 2023-06-19 | 2023-06-19 |  |  |  | Ongoing
PIP-23-140 | 23MO-07E8 | CSR Support for Schools of Brgy. Batangas Dos | Goods & Services | GSM | 2023-05-22 | 2023-05-29 | 9:03AM |  | -45075 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 29236 | 29236 | [23 empty] | Ongoing
PIP-23-141 | 23MO-01G | Supply and Delivery of Torque Wrench | Goods & Services | CDBB | 2023-05-18 | 2023-05-29 | 9:03AM |  | -45075 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 9784 | 9784 | [23 empty] | Ongoing
PIP-23-142 | 23MO-01G | Supply and Delivery of Inverter Welding Machine | Goods & Services | CDBB | 2023-05-05 | 2023-05-29 | 9:03AM |  | -45075 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 24505 | 24505 | [23 empty] | Ongoing
PIP-23-144 | 23MO-01G | Purchase of Electrical Materials, Consumables and Supplies | Goods & Services | CDBB | 2023-05-26 | 2023-05-31 | 11:30AM |  | -45077 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 78025 | 78025 | [23 empty] | Ongoing
SM-23-145 | 23MO-03A1 | 2023 internet/Leased Line Connection for ESB | Goods & Services | CFCM |  | 2023-05-31 | 2:05PM |  | -45077 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 300000 | 300000 | [23 empty] | Ongoing-For Evaluation
PSD-23-147 | 23MO-07E10 | Service for Event Organizing | Goods & Services | CFCM | 2023-06-06 | 2023-06-14 | 3:42PM |  | -45091 | PSD | N | PB | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 1600000 | 1600000 | [23 empty] | Ongoing- Waiting for Revised TOR
PSD-23-148 | 23MO-07E108 | Supply and Delivery of PNOC 50th Anniversary Token (Wrist Watch) | Goods & Services | CDBB | 2023-05-16 | 2023-06-07 | 3:00PM |  | -45084 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 160000 | 160000 | [23 empty] | Ongoing
PSD-23-151 | 23MO-07F2 | CY2023 Annual Physical Examination(APE) for PNOC Employees | Goods & Services | CDBB | 2023-06-06 | 2023-06-13 | 11:51AM |  | -45090 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 465000 | 465000 | [23 empty] | Ongoing
PIP-23-152 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station (part II) | Goods & Services | CDBB | 2023-06-05 | 2023-06-14 | 8:42AM |  | -45091 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 87057 |  | 87057 | [22 empty] | Ongoing
PIP-23-153 | 23MO-01E6 | Supply and Delivery of Heavy Duty Battery Charger | Goods & Services | CDBB | 2023-06-09 | 2023-06-14 | 8:42AM |  | -45091 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 14700 | 14700 | [23 empty] | Ongoing
PIP-23-154 | 23MO-06C1 | Calibration of Alcohol Breath Analyzer | Goods & Services | GSM | 2023-06-02 | 2023-06-14 | 8:42AM |  | -45091 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 5200 | 5200 | [23 empty] | Ongoing
PIP-23-155 | 23CA-030 | Rehabilitation of Maingate Security Guard Buillding and Guard House | Infrastructure | CFCM | 2023-06-01 | 2023-06-15 | 2:12PM |  | -45092 | PIP | N | PB | [13 empty] | COB | 2740000 |  | 2740000 | [22 empty] | Ongoing
GSD-23-156 | 23CA-03L | Technical Evaluation, Diagnosis and Analysis of Building 5 & 6 Electrical System | Goods & Services | CDBB | 2023-05-25 | 2023-06-16 | 8:32AM |  | -45093 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 761280 |  | 761280 | [22 empty] | Ongoing
SM-23-157 | 23MO-01E10 | Supply and Delivery of Essential ICT Supplies | Goods & Services | GSM |  | 2023-06-16 | 2:38PM |  | -45093 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 36240 | 36240 | [23 empty] | Ongoing
ESB-23-158 | 23MO-01H2U | Supply and Delivery of PPE's and Other Safety Equipment for PNOC ESB - Plastic Expandable Barricade | Goods & Services | GSM | 2023-06-15 | 2023-06-16 | 9:42PM |  | -45093 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 20000 | 20000 | [23 empty] | Ongoing
ESB-23-158 | 23CA-03U | Rehabilitation of Warehouse 1,2,3, and 4 (Concrete Walls and Roof Drainage) | Infrastructure | CFCM | 2023-06-14 | 2023-06-16 | 4:25PM |  | -45093 | ESB | N | PB | [13 empty] | COB | 4975000 |  | 4975000 | [22 empty] | Ongoing
PSD-23-160 | 23MO-481Q | PNOC Scholarship Program for SY 2023-2024 (Conduct of Testing Exam) | Goods & Services | CDBB | 2023-06-20 | 2023-06-23 | 10:05AM |  | -45100 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 21200 | 21200 | [23 empty] | Ongoing
OP-23-161 | 23MO-01H1H | Supply and Delivery of Corporate Tokens for 2023 | Goods & Services | GSM |  | 2023-06-23 | 11:30AM |  | -45100 | OP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 310000 | 310000 | [23 empty] | Ongoing
PP-23-162 | 23MO-01A | Supply and Delivery of Consolidated Computer Supplies, for 2nd & 3rd QTR year 2023 | Goods & Services | GSM | 2023-06-22 | 2023-06-26 | 9:40AM |  | -45103 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 9826874 | 9826874 | [23 empty] | Ongoing
FAILED/CANCELLED |  | FAILED/CANCELLED
GSD-23-015 | Awaiting APP | 2023 Caretaker Services- Tagaytay Property | Goods & Services | GSM | 2022-07-22 | 2023-03-07 | 9:20AM |  | -44992 | GSD | Y | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A | Jan-Dec |  | COB | 527000 | [16 empty] | 2023-03-07 | 1st - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 | 2nd - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 | 3rd - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 | 4th - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 |  |  |  | Cancelled 11.21.2022
AM-23-017 | Awaiting APP | 2023 Caretaker Services- Staffhouse, Lamao, Limay, Bataan | Goods & Services | HDVE | 2022-09-02 | 2022-10-18 | 9:05AM |  | -44852 | AMD | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-10 | N/A |  | N/A |  | N/A |  |  | COB | 324000 | [17 empty] | 1st- | [6 empty] | Cancelled 11.21.2022
PP-23-025 | Awaiting APP | Preventive Maintenance of PNOC Gym Equipment | Goods & Services | CDBB | 2022-10-17 | 2022-11-03 | 11:27AM |  | -44868 | PP | Y | NP-SVP | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  |  | COB | 59000 | [17 empty] | 1st&2nd- Non receipt of quotation/ | 1st- 11/15/222nd -12/1/2022 | 1st- 11/15/222nd -12/1/2022 | 1st- 11/15/222nd -12/2/2022 |  |  |  | Failed/Returned to End user 11.15.22
ESB-23-030 | Awaiting APP | Supply and Delivery of Various Tires for ESB | Goods & Services |  | 2023-01-03 | 2023-01-05 | 9:20AM |  | -44931 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 66000 | [24 empty] | returned to end-user 1.9.22 thru memo - Emailed by RGV/ over ABC
PIP-23-050 | 23MO-01D | Anti-Venom | Goods & Services | CDBB | 2023-01-25 | 2023-02-16 | 1:06PM |  | -44973 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 9600 | 9600 | [16 empty] | 1st-non receipt quotation | 2023-02-14 | 2023-02-14 | 2023-02-14 |  |  |  | Emailed to EGC 3:30PM
PIP-23-082 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station | Goods & Services | CDBB | 2023-01-17 | 2023-03-02 | 9:30AM |  | -44987 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 142200 |  | 142200 | [15 empty] | 1st- non-receipt | 2023-03-14 | 2023-03-14 | 2023-03-14 |  |  |  | Cancelled
PIP-23-053 | 23MO-05C3 | Hauling and Disposal of Generated Non-hazardous Solid Wastes by PNOC Industrial Park | Goods & Services | GSM | 2023-01-31 | 2023-03-03 | 3:00PM |  | -44988 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 60000 | 60000 | [16 empty] | 1st-non-receipt of bids/ 2nd-Over ABC | 2/15/2023 _3/22/23 | 2/21/2023_3/24/23 | 2023-02-23 |  |  |  | Re-Processing
SM-23-129 | 23MO-06E1 | Diagnostic/Check-up of Defective Printer MFP M180N | Goods & Services | GSM |  | 2023-05-08 | 10:35AM |  | -45054 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 2500 | 2500 | [23 empty] | Irrepairable
SM-23-077 | 23MO-06E1 | Repair of Printer HP Laser Printer M451NW | Goods & Services | GSM |  | 2023-02-23 | 10:10AM |  | -44980 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 2500 | 2500
PIP-23-085 | 23MO-01E6 | Supply and Delivery of Heavy Duty Battery Charger | Goods & Services | CDBB | 2023-02-17 | 2023-03-03 | 9:08AM |  | -44988 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 14420 | 14420 | [15 empty] | 2023-03-27 | 1st & 2nd- non receipt/3rd-non compliance/4th | 3/14/2023 & 4/28/23/5/23 | 3/14/2023 & 4/28/23-5/23 | 3/14/2023 & 4/28/23 | 0 |  |  | Cancelled
IA-23-060 | 23MO-01 | Supply and Delivery of 1 unit Maintenance Box for Epson Printer L6160 | Goods & Services |  | 2023-02-02 | 2023-02-08 | 2:31PM |  | -44965 | IAO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 1000 | 1000 | [23 empty] | Returned to End - user
SM-23-061 | 23MO-07D4 | Cloud Based Email Hosting | Goods & Services | CDBB |  | 2023-02-09 | 10:00AM |  | -44966 | SMO | N | NP-SVP | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-04-11 | 2023-04-12 | 2023-04-26 | 2023-04-25 | 29 days |  | COB |  |  |  | 298000 | 298000 |  | Tierra Networks Technologies Inc. | [11 empty] | 1st-Non Receipt of quotations | 2023-02-21 | 2023-02-22 |  |  | Contract#23-025
0
0
|  | PP-22-084 | 2022-05-11
51
Formulas:
Date PR Awarded = [Date of BAC Reso Reco Award]
Sub/Open of Bids = [Eligibility Check]
Date of BAC Reso Reco Award = [Date PR Awarded]
Eligibility Check = [Sub/Open of Bids]

## PMR 2023(Original)Updated (hidden)
| COMPANY: PHILIPPINE NATIONAL OIL COMPANY LOCATION: Bldg.6 Energy Center, Rizal Drive, BGC, Taguig SUBJECT: Procurement Monitoring |  |  |  |  | NOTE: 1.
[16 empty] | FAILED |  |  |  | ONGOING
[16 empty] | COMPLETED |  |  |  | AWARDED
#REF!
| AS OF: | 2024-10-16
PR NO. | Code (PAP) *from APP | Procurement Program/Project | Classification *Goods and Services, Infrastructure or Cosnulting Services | Account Officer *Initials | Date of PR | Date PR Received | Time Received | Date PR Awarded | TAT (days) | PMO/ End-User | Is this an Early Procurement Activity? Y/N | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Winning Bidder | List of Invited Observers | Date of Receipt of Invitation | [7 empty] | Submitted to COA |  | Reason of Failure |  |  |  |  | Payment Oder No./Contract No. | STATUS / REMARKS *Ongoing / Completed | STATUS as of today
[13 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf / Negotiation | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Reso Reco Award | Notice of Award | Contract Signing/ PO | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/Acceptance (if applicable) | Submission to IAO | Submission to OGC |  | Rebid |  | Date of Failure of Bidding | Date of Memo to Proponent (Failure of Bid) | Date Received Memo by Proponent | Date of Submitted CSS Form
GSD-23-001 | 23MO-06B14 | Contract Services for the Preventive Maintenance of Two (2) Units Passenger Elevator at PNOC Bldg.6 for 2023 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-30 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | 2023-01-03 |  | 2023-02-23 |  |  | COB | 185327.09 |  |  | 192757.8 | 192757.8 |  | KPI Elevators,Inc. | [11 empty] | 1st - Over ABC | 2022-11-28 | 2022-11-28 | 2022-11-29 | 2023-01-31 |  | Awarded | Contract for pick up of Supplier
GSD-23-002 | 23MO-06B18 | Contract Services for the Preventive Maintenance of CCTV Surveillance System at PNOC Bldg.6, 5, Computer Bldg. & Compound Perimeter | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-27 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | N/A | 2023-01-03 | N/A |  |  | COB | 89888.04 | 89888.04 |  | 66666.67 | 66666.67 |  | Comparts Computer Sales | [15 empty] | 2023-01-31 | PO#298646 | Awarded | Completed/Delivered
GSD-23-003 | 23MO-06B16 | Contract Services for the Maintenance of Fire Protection System at PNOC Bldg. 5&6 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-27 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | 2023-01-03 |  | 2023-02-20 |  |  | COB | 333900 |  |  | 310000 | 310000 |  | Lubricks Maintenance and Construction | [15 empty] | 2023-01-31 | Contract #23-017 | Awarded | Completed/Delivered
GSD-23-004 | 23MO-06B15 | Contract Services for the Preventive Maintenance of Two (2) Units Passenger Elevator at PNOC Bldg.5 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-20 | 63 | GSD | Y | NP-SVP | N/A | 2022-10-28 | N/A | N/A | N/A | 2022-12-16 | N/A | 2022-12-20 | 2023-01-03 |  | 2023-02-23 |  |  | COB | 139920 |  |  | 132000 | 132000 |  | Rockspeed Elevator and Escalator Corporation | [15 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-005 | 23MO-06B17 | Contract Services for the Water Chemical Treatment for PNOC Bldg. 5&6 | Goods & Services | CDBB | 2022-07-01 | 2022-10-18 | 3:11PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-12-15 | 2023-01-10 |  | 2023-01-30 | Jan-Dec |  | COB | 400898.8 |  |  | 308040 | 308040 |  | Impact One Nation Industrial Corp. | [7 empty] | 2023-02-08 | 2023-02-08 | 2023-02-08 |  | 1st - Non Compliance | 2022-11-15 | 2022-11-15 | 2022-11-15 | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-006 | 23MO-05C13 | Rental of Photocopying Machines for the year 2023 for PNOC Offices @ BGC, Taguig City, ESB & PIP | Goods & Services | GSM | 2022-07-07 | 2022-10-18 | 1:00PM | 2022-11-29 | 42 | GSD | Y | NP-SVP | N/A | 2022-11-27 | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-11-29 | 2023-01-03 | 2023-03-15 | 2023-02-23 | Jan-Dec |  | COB | 680000 | 680000 |  | 639000 | 639000 |  | Photopro Trading & General Merchandise Co. | [9 empty] | 2023-04-12 | [5 empty] | 2023-01-31 | Contract #23-018 | Awarded | Completed/Delivered
GSD-23-007 | 23MO-02A | Supply and Delivery of Drinking Water | Goods & Services | HDVE | 2022-06-25 | 2022-10-18 | 2:51PM | 2022-11-22 | 35 | GSD | Y | NP-SVP | N/A | 2022-10-29 | N/A | N/A | N/A | 2022-11-08 | N/A | 2022-11-22 | 2023-01-04 | 2023-01-25 | 2023-01-18 | Mar-Dec |  | COB | 360000 | 360000 |  | 278400 | 278400 |  | MSDR Water Refilling Station | [9 empty] | 2023-01-26 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-008 | 23MO-07D8 | 2023 Web Hosting and Maintenance for Document Tracking System | Goods & Services | CDBB | - | 2022-10-18 | 2:51PM | 2022-11-08 | 21 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-04 | N/A | 2022-11-08 | 2023-01-09 | 2023-01-30 | 2023-01-24 | Mar-Dec |  | COB | 239000 | 239000 |  | 238000 | 238000 |  | MYBUSYBEE INC. | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 23-002 | Awarded | Completed/Delivered
GSD-23-009 | WOR | 2023 Messengerial Services | Goods & Services | HDVE | 2022-06-28 | 2022-10-18 | 2:51PM | 2022-12-20 | 63 | GSD | Y | PB | 2022-10-25 | 2022-10-28 | 2022-11-11 | 2022-11-24 | 2022-11-24 | 2022-12-06 | 2022-12-20 | 2022-12-20 | 2022-01-09 | 2023-01-24 | 2023-01-18 | Jan-Dec |  | COB | 2666000 | 2666000 |  | 2592831.24 | 2592831.24 |  | PRC Couirier & Maintenance Services | MBC, COA, PCCI | [7 empty] | 2023-01-25 | 2023-01-27 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-010 | 23MO-06H2 | Pest Control Services | Goods & Services | CDBB |  | 2022-10-18 |  | 2022-11-08 | 21 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-02 | N/A | 2022-11-08 | 2023-01-09 | N/A | N/A | Jan-Dec |  | COB | 103824 | 103824 |  | 100800 | 100800 |  | Rampest Control Services and Supplies Company | [9 empty] | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298647 | Awarded | Completed/Delivered
ESB-23-011 | 23MO-05C12 | Preventive Maintenance of Truck Scale (Quarterly Check up and Calibration with ITDI Certificate) | Goods & Services | CDBB | 2022-07-11 | 2022-10-18 |  | 2022-11-22 | 35 | ESB | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-11-22 | N/A | 2023-01-10 | N/A | 30 days |  | COB | 83000 | 83000 |  | 83000 | 83000 |  | GCH International Mercantile, Inc. | [9 empty] | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298650 | Awarded | Completed/Delivered
GSD-23-012 | 23MO-05A | Janitorial Services | Goods & Services | CFCM | 2022-07-06 | 2022-10-18 | 8:55AM | 2023-01-17 | 91 | GSD | Y | PB | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2022-12-21 | 2023-01-12 | 2023-01-17 | 2023-01-18 |  | 2023-02-27 | Jan-Dec |  | COB | 8680000 | 8680000 |  | 8453970.56 | 8453970.56 |  | Starcom Manpower and Allied Services | MBC, COA, PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 |  |  |  | 2023-05-08 | [7 empty] | Awarded | Completed/Delivered
GSD-23-013 | 23MO-05C7 | Maintenance Services | Goods & Services | CFCM | 2022-07-22 | 2022-10-18 | 3:50PM | 2023-01-17 | 91 | GSD | Y | PB | 2022-11-08 | 2022-11-16 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2022-12-21 | 2023-01-12 | 2023-01-17 | 2023-01-18 |  |  | Jan-Dec |  | COB | 3627000 | 3627000 |  | 3605545.91 | 3605545.91 |  | Servicio Filipino,Inc. | MBC, COA, PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [5 empty] | N/A | N/A | N/A | N/A | 2023-01-31 |  | Awarded | Completed/Delivered
ESB-23-014 | 23MO-04A3 | Engagement of 3rd party Laboratory Service provider to conduct Quarterly Ambient Air Monitoring And Raw Water Testing | Goods & Services | HDVE | 2022-08-10 | 2022-10-18 | 2:10PM | 2022-11-14 | 27 | ESB | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-11-14 | 2023-01-06 | Contract draft |  | Mar-Dec |  | COB | 228000 |  |  | 221760 | 221760 |  | Berkman Systems,Inc. | [9 empty] | 2023-03-06 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-015 | Awaiting APP | 2023 Caretaker Services- Tagaytay Property | Goods & Services | GSM | 2022-07-22 | 2023-03-07 | 9:20AM |  | -44992 | GSD | Y | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A | Jan-Dec |  | COB | 527000 | [16 empty] | 2023-03-07 | 1st - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 | 2nd - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 | 3rd - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 | 4th - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 |  |  |  | Completed/Delivered
AM-23-016 | 23MO-06H2 | 2023 Pest Control Services - PNOC Staffhouse, Lamo,Limay, Bataan | Goods & Services | CDBB | 2022-08-23 | 2022-10-18 | 9:05AM | 2022-11-14 | 27 | AMD | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-08 | N/A | 2022-11-14 | N/A | 2023-01-09 | N/A | Jan-Dec |  | COB | 45000 | 45000 |  | 34000 | 34000 |  | RAM Pest Control Services & Supplies Phils. Co. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298648 | Awarded | Completed/Delivered
AM-23-017 | Awaiting APP | 2023 Caretaker Services- Staffhouse, Lamao, Limay, Bataan | Goods & Services | HDVE | 2022-09-02 | 2022-10-18 | 9:05AM |  | -44852 | AMD | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-10 | N/A |  | N/A |  | N/A |  |  | COB | 324000 | [17 empty] | 1st- | [6 empty] | Completed/Delivered
PIP-23-018 | 23MO-05C7 | Provision for Manpower for 2023 Custodial Services/Other General Services at PIP | Goods & Services | CFCM | 2022-08-23 | 2022-10-18 | 1:21PM | 2023-02-06 | 111 | PIP | Y | PB | 2022-11-22 | 2022-11-15 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2023-12-27 | 2023-01-31 | 2023-02-06 | 2023-02-14 |  | 2023-02-27 | Mar-Dec |  | COB | 3794718.27 | 3794718.27 |  | 3794718.27 | 3794718.27 |  | Servicio Filipino, Inc. | MBC,COA,PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [11 empty] | Awarded | Completed/Delivered
AM-23-019 | Awaiting APP | Security Services for PNOC Provincial Properties | Goods & Services | RGV | 2022-08-31 | 2022-10-18 | 2:19PM | 2022-12-20 | 63 | AMD | Y | PB | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-11-15 | 2022-11-15 | 2022-12-19 | 2022-12-19 | 2022-12-20 | 2023-01-26 | 2023-02-20 | 2023-02-15 | Jan-Dec |  | COB | 6188770.36 | 6188770.36 |  | 5941511.28 | 5941511.28 |  | Eliteblue Security Specialists | MBC,COA,PCCI | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 |  | 2023-02-20 | 2023-02-20 | 2023-02-20 | [5 empty] | 2023-01-31 | Contract#23-012 | Awarded | Completed/Delivered
GSD-23-020 | 23MO-05B | Security Services for Head Office, PIP &ESB | Goods & Services | RGV | 2022-08-15 | 2022-10-18 | 9:16PM | 2023-01-12 | 86 | GSD | Y | PB | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-11-15 | 2022-11-15 | 2022-12-06 | 2023-01-05 | 2023-01-12 | 2023-01-26 | 2023-02-20 | 2023-02-20 | Jan-Dec |  | COB | 48611344.64 | 48611344.64 |  | 47781296.28 | 47781296.28 |  | Eliteblue Security Specialists | MBC,COA,PCCI | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 |  | 2023-03-20 | 2023-03-20 | 2023-03-20 | [5 empty] | 2023-01-31 | Contract #23-007/008/009 | Awarded | Completed/Delivered
ESB-23-021 | 23MO-05A | 2023 Custodial and Janitorial Services | Goods & Services | CFCM | 2022-09-14 | 2022-10-18 | 3:40PM | 2023-01-12 | 86 | ESB | Y | PB | 2022-11-03 | 2022-11-08 | 2022-11-15 | 2022-11-29 | 2022-11-29 | 2022-12-21 | 2023-01-12 | 2023-01-12 | 2023-01-31 |  | 2023-02-20 | Jan-Dec |  | COB | 7530000 | 7530000 |  | 7451165.35 | 7451165.35 |  | Stewards Manpower Supply and Services | MBC,COA,PCCI | 2022-10-15 | 2022-10-15 | 2022-10-15 | 2022-10-15 | 2022-10-15 |  | 2023-05-05 | 2023-05-05 | 2023-05-05 | [5 empty] | 2023-01-31 | Contract #23-014 | Awarded | Abstract Routing 1.12.23
PIP-23-022 | 23MO-05A | Supply of Manpower,Equipment and Supplies for Janitorial Services at PIP | Goods & Services | CFCM | 2022-08-23 | 2022-10-18 | 3:25PM | 2023-02-13 | 118 | PIP | Y | PB | 2022-11-17 | 2022-11-22 | 2022-11-29 | 2022-12-13 | 2022-12-13 | 2022-12-27 | 2023-01-31 | 2023-02-13 | 2023-02-20 | 2023-02-28 | 2023-02-28 | Mar-Dec |  | COB | 4304703.82 |  |  | 3263405.9 | 3263405.9 |  | Servicio Filipino,Inc. | MBC,COA,PCCI | [15 empty] | Contract#23-021 | Awarded | Completed/Delivered
PIP-23-023 | 23CA-06A | Supply,Delivery, Testing and Commissioning of Brand New Fire Truck | Goods & Services | CFCM | 2022-10-05 | 2023-01-13 | 9:21AM | 2023-04-20 | 97 | PIP | Y | PB | 2023-01-19 | 2023-01-24 | 2023-01-31 | 2023-02-14 | 2023-02-14 | 2023-02-20 | 2023-03-30 | 2023-03-30 | 2023-04-27 | 2023-06-22 | 2023-06-19 | 180 days |  | COB | 29200000 |  | 29200000 | 28888888 |  | 28888888 | Boston Home Incorporated | MBC,COA,PCCI | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-01-31 | [5 empty] | 1st - Non Compliance | 2023-01-10 | 2023-01-11 | 2023-01-12 |  | Contract#23-039 | Awarded | Completed/Delivered
PIP-23-024 | 23MO-04A3 | Environmental Monitoring for 2023 (Waste Water-Effluent and Marine, Raw Water, Ambient Air Sampling and Laboratory Analysis | Goods & Services | CDBB | 2022-10-20 | 2023-01-19 | 5:01PM | 2023-03-16 | 56 | PIP | Y | PB |  |  | 2022-11-15 | 2023-01-05 | 2023-01-05 | 2023-01-09 |  | 2023-03-16 | 2023-03-16 | 2023-05-12 | 2023-03-21 | 1st -4th QTR |  | COB | 1032026.6 | 1032026.6 |  | 1002400 | 1002400 |  | CRL Environmental Corporation | [7 empty] | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2022-12-12 | 1st-Non Comliance in Philgeps/2nd-Non-compliant in tech specs | 1st -12/2/2022/ 2nd- 1/17/2023 | 1st-12/2/2022 | 1st-12/5/22 |  | Contract #23-023 | Awarded | Completed/Delivered
PP-23-025 | Awaiting APP | Preventive Maintenance of PNOC Gym Equipment | Goods & Services | CDBB | 2022-10-17 | 2022-11-03 | 11:27AM |  | -44868 | PP | Y | NP-SVP | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  |  | COB | 59000 | [17 empty] | 1st&2nd- Non receipt of quotation/ | 1st- 11/15/222nd -12/1/2022 | 1st- 11/15/222nd -12/1/2022 | 1st- 11/15/222nd -12/2/2022 |  |  |  | Failed/Returned to End user 11.15.22
AM-23-026 | Awaiting APP | 2023 Caretaker Services- Staffhouse, Lamao, Limay, Bataan | Goods & Services | HDVE | 2022-11-23 | 2022-11-28 | 8:55AM | 2023-01-05 | 38 | AMD | Y | NP-SVP | N/A | 2022-12-16 | N/A | N/A | N/A |  | 2022-12-21 | 2023-01-05 | 2023-01-10 | 2023-02-14 | 2023-01-25 |  |  | COB | 322700 | 322700 |  | 320612.06 | 320612.06 |  | MMA Competent Manpower and General Services | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-02-23 | [5 empty] | 2023-01-31 | Contract#23-006 | Awarded` | Completed/Delivered
SM-23-027 | 23MO-03AA | 2023 PNOC Internet/Leased Line Connection Upgrade | Goods & Services | CFCM | 2022-11-18 | 2022-11-28 | 8:45AM | 2023-01-26 | 59 | SMO | Y | PB |  | 2022-12-06 | 2022-12-13 | 2022-12-27 | 2022-12-27 | 2023-01-05 | 2023-01-24 | 2023-01-26 | 2023-01-31 | 2023-02-17 | 2023-02-13 | Mar-Dec |  | COB | 1300000 | 1300000 |  | 610980 | 610980 |  | Source Telecommunications, Inc. | MBC,PCCI, COA | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 |  | 2023-05-17 | 2023-05-17 | 2023-05-17 | [5 empty] | 2023-01-31 | Contract #23-013 | Awarded | Completed/Delivered
PP-23-028 | 23MO-06C10 | Preventive Maintenance of PNOC Gym Equipment | Goods & Services | CDBB | 2022-12-07 | 2022-12-07 | 4:25PM | 2022-12-22 | 15 | PP | Y | NP-SVP | N/A | 2022-12-14 | N/A | N/A | N/A | 2022-12-20 | N/A | 2022-12-22 | N/A | 2023-01-09 | N/A | Jan-Dec |  | COB | 65000 | 65000 |  | 28800 | 28800 |  | The FITCO Inc (Stark Fitness) | [9 empty] | 2023-01-10 |  | Superceded of PP-22-025 |  |  |  | 2023-01-31 | PO#298649 | Awarded | Completed/Delivered
PIP-23-029 | 23MO-01F131 | Supply and Delivery of 2023 Vehicle Sticker for PIP | Goods & Services | GSM | 2022-12-22 | 2022-01-03 | 1:30PM | 2023-02-14 | 407 | PIP | N | NP-SVP | N/A | 2023-01-23 | N/A | N/A | N/A | 2023-02-07 | N/A | 2023-02-14 | N/A | 2023-02-15 | N/A | 30 Days |  | COB | 9000 | 9000 |  | 6712.5 | 6712.5 |  | Forms International Enterprises,Corp. | [9 empty] | 2023-03-27 | [6 empty] | PO#298654 | Awarded | Completed/Delivered
ESB-23-030 | Awaiting APP | Supply and Delivery of Various Tires for ESB | Goods & Services |  | 2023-01-03 | 2023-01-05 | 9:20AM |  | -44931 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 66000 | [24 empty] | returned to end-user 1.9.22 thru memo - Emailed by RGV/ over ABC
PSD-23-031 | 23MO-07EB | Supply and Delivery of PNOC's 50th Anniversary T-shirt | Goods & Services | GSM | 2023-12-21 | 2023-01-11 | 10:41AM | 2023-02-09 | 29 | PSD | N | NP-SVP | N/A | 2023-01-17 | N/A | N/A | N/A | 2023-01-31 | N/A | 2023-02-09 | N/A | 2023-02-14 | N/A | 30 days |  | COB | 84000 | 84000 |  | 73500 | 73500 |  | Topsol Enterprises | [9 empty] | 2023-08-31 | [6 empty] | PO#298652 | Awarded | Completed/Delivered
SM-23-032 | 23MO-041D | Hiring of Certifying Body for PNOC QMS and Recertification | Consulting Services | CDBB | 2023-01-16 | 2023-01-12 | 10:55AM | 2023-05-16 | 124 | SMO | N | NP-SVP | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-05-12 | N/A | 2023-05-16 | N/A | 2023-05-18 | N/A |  |  | COB | 300000 | 300000 |  | 748440 | 748440 |  | SOCOTEC Certification Philippines,Inc. | [11 empty] | 1st -2nd - Non Receipt of Quotation | 2nd : 4/19/2023 | 2nd : 4/19/2023 | 2nd : 4/19/2023 |  |  | Awarded
ESB-23-090 | 23MO-04B1C | Hiring of Certifying Body for PNOC ESB ISO 9001:2015 and ISO 45001:2018 and Recertification | Consulting Services | CDBB | 2023-01-16 | 2023-03-03 | 3:20PM | 2023-05-16 | 74 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | 2023-05-16 | N/A |  | N/A |  |  | COB | 500000 | 500000
ESB-23-033 | 23MO-06D5 | Supply and Delivery of Various Tires for ESB | Goods & Services | GSM | 2023-01-03 | 2023-01-13 | 9:26AM | 2023-02-06 | 24 | ESB | N | NP-SVP | N/A | 2023-01-17 | N/A | N/A | N/A | 2023-01-25 | N/A | 2023-02-06 | N/A | 2023-02-08 | N/A | 30 days |  | COB | 66000 | 66000 |  | 55300 | 55300 |  | Fleetserv Inc. | [9 empty] | 2023-03-03 | [6 empty] | PO#298651 | Awarded | Completed/Delivered
PIP-23-034 | 23CA-03C2 | Replacement of Fire Engine for Jetty and Controls - 1 Unit | Goods & Services | CDBB | 2023-01-05 | 2023-05-31 | 10:01AM |  | -45077 | PIP | N | PB | 2023-01-19 | 2023-01-24 | 2023-01-31 | 2023-02-14 | 2023-02-14 | [8 empty] | COB | 22150000 |  | 22150000 | [15 empty] | 1st-Non-submission of bid | 2023-02-14 | 2023-02-14 |  |  |  |  | Waiting for Update from PIP
PIP-23-035 | 23MO-04A2 | Hiring of EIA Report Consultant | Consulting Services | HDVE | 2023-01-11 | 2023-01-16 | 9:08AM | 2023-01-24 | 8 | PIP | N | NP-HT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-04-13 | 2023-03-31 |  |  | COB | 170000 | 170000 |  | 170000 | 170000 |  | Engr.Aldwin Camance | [7 empty] | 2023-04-13 | 2023-04-13 | 2023-04-13 | [5 empty] | 2023-01-31 | Contract #23-011 | Awarded | Completed/Delivered
ESB-23-036 | 23CA-01C | Upgrade and Improvement of Drainage System | Infrastructure | RGV | 2023-01-10 | 2023-01-17 | 1:23PM | 2023-03-14 | 56 | ESB | N | PB | 2023-01-24 | 2023-01-26 | 2023-02-02 | 2023-02-16 | 2023-02-16 | 2023-02-21 | 2023-03-13 | 2023-03-14 | 2023-03-15 |  | 2023-05-04 | 180 days |  | COB | 4550000 |  | 4550000 | 4532619.06 |  | 4532619.06 | RM Joyce Construction | [16 empty] | Contract #23-022 | Awarded | Completed/Delivered
SM-23-037 | 23MO-07E11 | Publication of the 50th Commemorative Book | Goods & Services | CFCM | 2023-01-18 | 2023-01-18 | 3:40PM | 2023-02-14 | 27 | SMO | N | NP-SVP | N/A | 2023-01-27 | N/A | N/A | N/A | 2023-02-08 | N/A | 2023-02-14 | 2023-02-15 | 2023-03-13 | 2023-03-08 | September |  | COB | 1000000 | 1000000 |  | 978000 | 978000 |  | VJ Graphics Arts,Inc. | [7 empty] | 2023-05-22 | 2023-05-22 | 2023-05-22 |  |  | n |  |  |  |  | Awarded
PIP-23-038 | 23MO-04A6 | Assessment of Jetty Facility and Hydrographic Survey | Consulting Services | RGV | 2023-01-19 | 2023-01-19 | 2:08PM | 2023-03-28 | 68 | PIP | N | PB |  | 2023-02-21 | 2023-02-28 | 2023-03-09 | 2023-03-09 | 2023-03-20 | n/A | 2023-03-28 | 2023-03-28 | 2023-05-10 | 2023-05-03 | 120 days |  | COB | 4800000 | 4800000 |  | 4799984 | 4799984 |  | A.C. Ong Consulting. Inc. | [7 empty] | 2023-05-12 | 2023-05-12 | [7 empty] | Contract #23-026 | Awarded | Completed/Delivered
PIP-23-039 | 23MO-05C9 | Annual Physical Examination (APE) for PIP | Goods & Services | GSM | 2023-01-19 | 2023-01-23 | 10:12AM | 2023-02-21 | 29 | PIP | N | NP-SVP | N/A | 2023-01-26 | N/A | N/A | N/A | 2023-02-15 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 95000 | 95000 |  | 44227.5 | 44227.5 |  | EDGT-LAB-Tech Diagnostic Center | [9 empty] | 2023-03-07 | [6 empty] | PO#298658 | Awarded | Completed/Delivered
AS-23-040 | 23MO-041B1U | Hiring of Musical Director for 2023 | Goods & Services | HDVE |  | 2023-01-24 |  | 2023-01-24 | 0 | ASD | N | NP-SVP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-26 | 2023-03-10 | 2023-01-31 | Feb-Dec |  | COB | 420000 | 420000 |  | 385000 | 385000 |  | Anthony Go Villanueva | [9 empty] | 2023-03-13 | [5 empty] | 2023-01-31 | #23-015 | Awarded | Completed/Delivered
PIP-23-041 | 23CA-01B | Fencing of Alberba Area (250m Length) | Infrastructure | CDBB | 2023-01-04 | 2023-01-24 | 3:14PM | 2023-04-25 | 91 | PIP | N | PB | N/A | 2023-01-31 | 2023-02-07 | 2023-02-21 | 2023-02-21 | 2023-04-04 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-05-30 | 2023-05-29 | 30 days |  | COB | 3460000 |  | 3460000 | 3074702.15 | 3074702.15 |  | AR. Esbi Construction | MBC,COA,PCCI | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | [10 empty] | 23-032 | Awarded | For Signing of NOA/Contract Draft
ESB-23-042 | 23MO-01H2A | Supply, Delivery and Printing of Calling Cards (CBP) | Goods & Services | GSM | 2023-01-16 | 2023-01-31 | 2:30PM | 2023-02-21 | 21 | ESB | N | NP-SVP | N/A | 2023-02-06 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 3000 | 3000 |  | 2550 | 2550 |  | Forms International Enterprises Corporation | [16 empty] | PO#298659 | Awarded | For Signing PO
PIP-23-043 | 23CA-04B3 | Supply, Delivery and Installation of Load Break Switch | Goods & Services | GSM | 2023-01-10 | 2023-01-30 | 8:49AM | 2023-02-28 | 29 | PIP | N | NP-SVP | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-21 | N/A | 2023-02-28 | 2023-03-01 |  | 2023-04-26 |  |  | COB | 489000 |  | 489000 | 439000 |  | 439000 | Pablo S. Labasbas Construction Corporation | [16 empty] | Contract #23-028 | Awarded | Completed/Delivered
PSD-23-044 | 23MO-01D | Supply and Delivery of COVID Supplies (Face Mask) for MAR-JUN | Goods & Services | CDBB | 2023-01-30 | 2023-01-31 | 2:30PM | 2023-02-14 | 14 | PSD | N | NP-SVP | N/A | 2023-02-01 | N/A | N/A | N/A | 2023-02-09 | N/A | 2023-02-14 | N/A | 2023-02-15 | N/A |  |  | COB | 40000 | 40000 |  | 37584 | 37584 |  | SGS Healthcare Co. | [9 empty] | 2023-02-17 | [6 empty] | PO#298653 | Awarded | Completed/Delivered
PP-23-045 | 23MO-01H2B | Supply and Delivery Various Tissue | Goods & Services | CDBB | 2023-02-01 | 2023-02-02 | 11:03AM | 2023-02-16 | 14 | PRM | N | NP-SVP | N/A | 2023-02-03 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-02-16 | N/A | 2023-02-17 | N/A |  |  | COB | 19076 | 19076 |  | 18600 | 18600 |  | Eco-Hygiene Institutional Sals Corp/Sanitary Care Products Asia,Inc. | [9 empty] | 2023-02-20 | [6 empty] | PO#298656/PO#298657 | Awarded | Completed/Delivered
ESB-23-046 | 23CA-MYB1A | Flattening of the Hilly Area | Infrastructure | RGV | 2023-02-01 | 2023-06-05 | 12:00PM |  | -45082 | ESB | N | PB | 2023-06-16 | 2023-06-20 | 2023-06-27 | 2023-07-11 | 2023-07-11 |  | 2023-08-01 | [6 empty] | COB | 53540000 |  | 53540000 | 38540799.26 |  | 38540799.26 | W. Rivera Const. and Equipt. Rentals | PCA,MBC,COA, PCCI | 2023-06-27 | 2023-07-11 | 2023-07-11 | 2023-07-12 | 2023-07-20 |  |  |  |  | 2023-06-05 | 1st - non compliance | [6 empty] | For BOD Approval to Award
ESB-23-047 | 23CA-MYB3A1 | Construction of New Pier | Infrastructure | RGV | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | [13 empty] | COB | 1492039.17 |  | 1492039.17 | [22 empty] | For BOD Approval to Award
ESB-23-048 | 23CA-MYB3A2 | Consulting Serviices for the Construction Management of the Construction of New Pier (ESB Port Dev't Option 1-Scheme B) and Flattening of the Hilly Area (Phase 1) | Consulting Services | CFCM | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | [13 empty] | COB | 43951025 |  | 43951025 | [22 empty] | For BOD Approval to Award
BR-23-049 | 23MO-01H2A | Supply, Delivery and Printing of Calling Cards (MRCR) | Goods & Services | GSM | 2023-02-02 | 2023-02-02 | 3:20PM | 2023-02-21 | 19 | BRDD | N | NP-SVP | N/A | 2023-02-06 | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 1000 | 1000 |  | 850 | 850 |  | Forms International Enterprises Corporation | [16 empty] | PO#298659 | Awarded | For Signing PO
PIP-23-050 | 23MO-01D | Anti-Venom | Goods & Services | CDBB | 2023-01-25 | 2023-02-16 | 1:06PM |  | -44973 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 9600 | 9600 | [16 empty] | 1st-non receipt quotation | 2023-02-14 | 2023-02-14 | 2023-02-14 |  |  |  | Emailed to EGC 3:30PM
GSD-23-051 | 23MO-01E1 | Supply and Delivery of Biometric Scanner | Goods & Services | CDBB | 2023-02-01 | 2023-02-03 | 1:37PM | 2023-02-16 | 13 | GSD | N | NP-SVP | N/A | 2023-02-07 | N/A | N/A | N/A | 2023-02-15 | N/A | 2023-02-16 | N/A | 2/17/23 | N/A | 30 days |  | COB | 20000 | 20000 |  | 20000 | 20000 |  | Comparts Computer Sales | [9 empty] | 2023-02-20 | [6 empty] | PO#298655 | Awarded | Completed/Delivered
PIP-23-052 | 23MO-01H2J | Supply and Delivery of Various Fire Extinguisher | Goods & Services | CDBB | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-03-07 | 32 | PIP | N | NP-SVP | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-03-03 | N/A | 2023-03-07 | N/A | 2023-03-08 | N/A | 30 days |  | COB | 100000 | 100000 |  | 41750 | 41750 |  | A.D. Ramos Building Construction & Engineering Services | [9 empty] | 2023-03-13 | [6 empty] | PO#298667 | Awarded | Completed/Delivered
PIP-23-053 | 23MO-05C3 | Hauling and Disposal of Generated Non-hazardous Solid Wastes by PNOC Industrial Park | Goods & Services | GSM | 2023-01-31 | 2023-03-03 | 3:00PM |  | -44988 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 60000 | 60000 | [16 empty] | 1st-non-receipt of bids/ 2nd-Over ABC | 2/15/2023 _3/22/23 | 2/21/2023_3/24/23 | 2023-02-23 |  |  |  | Re-Processing
PIP-23-054 | 23MO-01H2I | Life Ring | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 16000 | 16000 |  | 33317.5 | 33317.5 |  | Safetyko Industrial Supplies | [9 empty] | 2023-05-19 | [6 empty] | PO#298666 | Awarded | Completed/Delivered
PIP-23-055 | 23MO-01H2F | Cotton Gloves | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 2000 | 2000 | [22 empty] | Awarded | Completed/Delivered
PIP-23-056 | 23MO-01H2G | Hi-Visibility Vest/ Reflective Vest |  | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 3000 | 3000 | [22 empty] | Awarded | Completed/Delivered
PIP-23-057 | 23MO-01H2E | Safety Shoes | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 25000 | 25000 | [22 empty] | Awarded | Completed/Delivered
BR-23-058 | Approved Budget Realignment | Engagement of an individual consultant for the development of decentralized energy systems (DES)- solar PV Rooftop system in PNOC (ESB) | Consulting Services | CFCM | 2023-02-03 | 2023-02-06 | 8:38AM | 2023-03-24 | 46 | BRDD | N | NP-SVP | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-03-24 | 2023-03-24 |  | 2023-04-18 | 30 days |  | COB | 500000 | 500000 |  | 421000 | 421000 |  | Engr. Adrian L. Rey | [9 empty] | 2023-04-27 |  | 1st-Non Receipt of Quotation | 2023-03-01 | 2023-03-01 | 2023-03-01 |  | Contract #23-024 | Awarded | Completed/Delivered
GSD-23-059 | 23MO-01E4 | Supply and Delivery of Compressor Motor for Aircon at PNOC Records Bldg. | Goods & Services | GSM | 2023-02-02 | 2023-02-07 | 1:33PM | 2023-02-28 | 21 | GSD | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-20 | N/A | 2023-02-28 | N/A | 2023-03-03 | N/A |  |  | COB | 32000 | 32000 |  | 24990 | 24990 |  | Pumpcraft Industrial Sales | [9 empty] | 2023-05-04 | [6 empty] | PO#298665 | Awarded | Completed/Delivered
IA-23-060 | 23MO-01 | Supply and Delivery of 1 unit Maintenance Box for Epson Printer L6160 | Goods & Services |  | 2023-02-02 | 2023-02-08 | 2:31PM |  | -44965 | IAO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 1000 | 1000 | [23 empty] | Returned to End - user
SM-23-061 | 23MO-07D4 | Cloud Based Email Hosting | Goods & Services | CDBB |  | 2023-02-09 | 10:00AM |  | -44966 | SMO | N | NP-SVP | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-04-11 | 2023-04-12 | 2023-04-26 | 2023-04-25 | 29 days |  | COB | 330000 | 330000 |  | 298000 | 298000 |  | Tierra Networks Technologies Inc. | [11 empty] | 1st-Non Receipt of quotations | 2023-02-21 | 2023-02-22 |  |  | Contract#23-025 | Awarded | Completed/Delivered
PIP-23-062 | 23MO-06C1 | Calibration of Various Meters | Goods & Services | GSM | 2023-02-08 | 2023-02-10 | 1:15PM | 2023-03-02 | 20 | PIP | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-23 | N/A | 2023-03-02 | N/A | 2023-03-03 | N/A | 30 days |  | COB | 49000 | 49000 |  | 48300 | 48300 |  | Premier Physic Metrologie Co. | [9 empty] | 2023-03-16 | [6 empty] | PO#298664 | Awarded | Completed/Delivered
PIP-23-063 | 23MO-04B1N | Conduct of Work Measure Environment | Goods & Services | GSM | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-02 | 20 | PIP | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-28 | N/A | 2023-03-02 | N/A | 2023-03-03 | N/A |  |  | COB | 30000 | 30000 |  | 29456 | 29456 |  | CRL Calabarquez Corp. | [9 empty] | 2023-03-10 | [5 empty] | 2023-06-06 | PO#298663 | Awarded | Completed/Delivered
PIP-23-064 | 23MO-01H2H | Supply and Delivery of Dust Mask | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-09 | 27 | PIP | N | NP-SVP | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-09 | N/A | 2023-03-13 | N/A |  |  | COB | 3000 | 3000 |  | 2040 | 2040 |  | See More Enterprise Co | [9 empty] | 2023-03-14 | [6 empty] | PO#298670 | Awarded | Completed/Delivered
PIP-23-065 | 23MO-01H2M | Supply and Delivery of various Other Supplies for Safety | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-09 | 27 | PIP | N | NP-SVP | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-09 | N/A | 2023-03-13 | N/A |  |  | COB | 68000 | 68000 |  | 32125 | 32125 |  | See More Enterprise Co/Villaflores Industrial Supply | [9 empty] | 2023-03-14 | [6 empty] | PO#298670/298671 | Awarded | Completed/Delivered
PIP-23-066 | 23MO-07E5 | Supply and Delivery of Materials for the Coastal Clean-Up 2023 | Goods & Services | GSM | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-02-28 | 18 | PIP | N | NP-SVP | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-23 | N/A | 2023-02-28 | N/A | 2023-03-01 | N/A | 30 Days |  | COB | 35000 | 35000 |  | 29820 | 29820 |  | Ceboom Enterprises/Syner Graphics Co./ Safetyko | [16 empty] | PO#298660/298661 | Awarded | Completed/Delivered
PIP-23-067 | 23MO-06C10 | Supply and Delivery of 100Watts LED Street Light | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-07 | 25 | PIP | N | NP-SVP | N/A | 2023-02-15 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-07 | N/A | 2023-03-08 | N/A | 30 Days |  | COB | 200000 | 200000 |  | 140000 | 140000 |  | West Point Engineering Supplies Incorporated | [9 empty] | 2023-03-10 | [6 empty] | PO#298668 | Awarded | Completed/Delivered
PIP-23-068 | 23MO-01H2L | Supply and Delivery of Safety Hazards | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-09 | 27 | PIP | N | NP-SVP | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-09 | N/A | 2023-03-13 | N/A |  |  | COB | 22000 | 22000 |  | 16100 | 16100 |  | Villaflores Industrial Supply | [9 empty] | 2023-03-14 | [6 empty] | PO#298671 | Awarded | Completed/Delivered
PSD-23-069 | 23MO-01H1C | Supply and Delivery of CY 2023 Token for Loyalty Service Awardees | Goods & Services | GSM | 2023-02-08 | 2023-02-13 | 10:31AM | 2023-03-23 | 38 | PSD | N | NP-SVP | N/A | 2023-02-28 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-03-23 | N/A | 2023-03-27 | N/A | 30 Days |  | COB | 160000 | 160000 |  | 88000 | 88000 |  | 3D Image Works and Design House | [16 empty] | PO#298675 | Awarded | Completed/Delivered
PIP-23-070 | 23MO-06C12 | Preventive Maintenance Services of CCTV System for PIP | Goods & Services | GSM | 2023-02-22 | 2023-03-03 | 2:00PM | 2023-03-21 | 18 | PIP | N | NP-SVP | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-03-21 | 2023-03-27 | 2023-05-22 | 2023-03-28 | 30 days |  | COB | 171000 | 171000 |  | 112500 | 112500 |  | Compass Integrated Solutions,Inc. | [16 empty] | Contract#23-070 | Awarded | Completed/Delivered
PSD-23-071 | 23MO-01H1F/01H1D/01H1G | Supply and Delivery of CY 2023 Token for Loyalty Service Awardees & Retirees | Goods & Services | GSM | 2023-02-08 | 2023-02-15 | 3:57PM | 2023-03-21 | 34 | PSD | N | NP-SVP | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-03-21 | N/A | 2023-03-27 | N/A | 30 Days |  | COB | 48000 | 48000 |  | 46000 | 46000 |  | Ad-Man Resources Inc. / Suarez Brothers Metal Arts, Inc. | [9 empty] | 2023-09-06 | [6 empty] | PO#298678/677 | Awarded | Completed/Delivered | 2 Tube Trophy/ 5 Plaque Retirees
PSD-23-072 | 23MO-01D | Supply and Delivery of Fluquadri Vaccine (Adult) | Goods & Services | CDBB | 2023-02-13 | 2023-02-14 | 4:07PM | 2023-03-02 | 16 | PSD | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-28 | N/A | 2023-03-02 | N/A | 2023-03-03 | N/A | 30 days |  | COB | 90000 | 90000 |  | 71003 | 71003 |  | Pharma Quest Co. | [9 empty] | 2023-03-06 | [6 empty] | PO#298662 | Awarded | Completed/Delivered
GAD-23-073 | 23MO-07E2 | Supply and Delivery of T-shirts for 2023 National Women's Month Celebration | Goods & Services | GSM |  | 2023-02-15 | 7:50AM | 2023-03-14 | 27 | GAD | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-27 | N/A | 2023-03-14 | N/A | 2023-03-14 | N/A |  |  | COB | 39300 | 39300 |  | 29260 | 29260 |  | Ceboom Enterprises | [15 empty] | 2023-05-25 | PO#298672 | Awarded | Completed/Delivered
SM-23-074 | 23MO-01A | Supply and Delivery of Stamp with Inscription | Goods & Services | GSM |  | 2023-02-16 |  | 2023-03-09 | 21 | SMO | N | NP-SVP | N/A | 2023-02-23 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-03-09 | N/A | 2023-03-10 | N/A | 30 days |  | COB | 3500 | 3500 |  | 3500 | 3500 |  | ZAB Enterprises Inc. | [9 empty] | 2023-04-28 | [6 empty] | PO#298669 | Awarded | Completed/Delivered
GSD-23-075 | 23CA-03D | Exterior Repainting of Bldg.5 | Infrastructure | CFCM | 2023-02-10 | 2023-02-16 | 2:40PM | 2023-05-02 | 75 | GSD | N | PB | 2023-02-28 | 2023-03-02 | 2023-03-09 | 2023-03-23 | 2023-03-23 | 2023-03-30 | 2023-04-28 | 2023-05-02 | 2023-05-03 | 2023-06-05 | 2023-05-30 | 60 days |  | COB | 4500000 |  | 4500000 | 4217025 |  | 4217025 | Pablo S. Labasbas Construction Corporation | MBC,PCCI, COA | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-02-28 |  | 2023-06-23 | 2023-06-23 | 2023-06-23 | [6 empty] | Contract#23-034 | Awarded | Completed/Delivered
PP-23-076 | 23MO-01A | Supply and Delivery of Consolidated Computer Supplies, for 1st QTR year 2023 | Goods & Services | GSM | 2023-02-17 | 2023-02-17 | 3:05PM | 2023-05-02 | 74 | PRM | N | NP-SVP | N/A | 2023-03-25 | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-05-08 | N/A |  |  | COB | 907538.92 | 907538.92 |  | 700234.96 | 700234.96 |  | Accessories & Supplies Depot,Inc (ASDI)/PBT Technology Solutions,Inc/Philcopy Corporation | [16 empty] | PO#298685/686/687 | Awarded | Completed/Delivered
SM-23-077 | 23MO-06E1 | Repair of Printer HP Laser Printer M451NW | Goods & Services | GSM |  | 2023-02-23 | 10:10AM |  | -44980 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 2500 | 2500
PP-23-078 | 23MO-01A | Supply and Delivery of Consolidated Commonly Used Supplies, 1st QTR | Goods & Services | GSM | 2023-02-22 | 2023-02-23 | 3:10PM | 2023-06-27 | 124 | PRM | N | NP-SVP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | N/A | 2023-07-06 | N/A | 30 dyas |  | COB | 265541.82 | 265541.82 |  | 432060.59 | 432060.59 |  | ZAB Enterprises Inc./ Halden General Merchandise/Oriental School and office Supply | [9 empty] | 2023-09-06 | [6 empty] | PO#298711/712/713 | Awarded | Completed/Delivered
PIP-23-079 | 23MO-01A | Supply and Delivery of Laserjet Ink | Goods & Services | GSM | 2023-02-17 | 2023-02-27 | 9:30PM | 2023-04-11 | 43 | PIP | N | NP-SVP | N/A | 2023-03-15 | N/A | N/A | N/A | 2023-03-29 | N/A | 2023-04-11 | N/A | 2023-04-13 | N/A | 30 Days |  | COB | 30000 | 30000 |  | 23664 | 23664 |  | Accessories & Supplies Depot,Inc (ASDI) | [16 empty] | PO#298682 | Awarded | Completed/Delivered
PSD-23-080 | Approved Budget Realignment | Supply and Delivery of 2023 Wellness Tshirts | Goods & Services | GSM | 2023-02-16 | 2023-02-27 | 3:40PM | 2023-03-21 | 22 | PSD | N | NP-SVP | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-15 | N/A | 2023-03-21 | N/A | 2023-03-27 | N/A | 30 days |  | COB | 45900 | 45900 |  | 26010 | 26010 |  | Ceboom Enterprises | [16 empty] | PO#298679 | Awarded | PENDING APPROVAL FROM OP
GAD-23-081 | 23MO-07E2 | Supply and Delivery of Tote Bags for 2023 National Womens Month Celebration | Goods & Services | GSM | 2023-02-27 | 2023-02-27 | 3:58PM | 2023-03-14 | 15 | GAD | N | NP-SVP | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-09 | N/A | 2023-03-14 | N/A | 2023-03-14 | N/A | 30 days |  | COB | 16000 | 16000 |  | 13440 | 13440 |  | King of Kings Trading | [15 empty] | 2023-05-25 | PO#298673 | Awarded | Completed/Delivered
PIP-23-082 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station | Goods & Services | CDBB | 2023-01-17 | 2023-03-02 | 9:30AM |  | -44987 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 142200 |  | 142200 | [15 empty] | 1st- non-receipt | 2023-03-14 | 2023-03-14 | 2023-03-14 |  |  |  | Cancelled
PIP-23-083 | 23MO-06D2 | Supply and Delivery of Tires and Windshield Wipers | Goods & Services | CDBB | 2023-02-22 | 2023-03-02 | 9:30AM | 2023-03-16 | 14 | PIP | N | NP-SVP | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-15 | N/A | 2023-03-16 | N/A | 2023-03-17 | N/A | 30 days |  | COB | 166800 | 166800 |  | 115800 | 115800 |  | MENDO Enterprises | [9 empty] | 2023-03-23 | [6 empty] | PO#298674 | Awarded | Completed/Delivered
PSD-23-084 | 23M0 -01H1A | Supply and Delivery of CY2023 Token For 30 Years Loyalty Service Awardees(Wrist Watch) | Goods & Services | GSM | 2023-02-28 | 2023-03-02 | 11:30AM | 2023-05-11 | 70 | PSD | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-11 | N/A | 2023-05-19 | N/A | 30 days |  | COB | 550000 | 550000 |  | 598080 | 598080 |  | Neuchatel, Inc. | [16 empty] | PO#298688 | Awarded
PIP-23-085 | 23MO-01E6 | Supply and Delivery of Heavy Duty Battery Charger | Goods & Services | CDBB | 2023-02-17 | 2023-03-03 | 9:08AM |  | -44988 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 14420 | 14420 | [15 empty] | 2023-03-27 | 1st & 2nd- non receipt/3rd-non compliance/4th | 3/14/2023 & 4/28/23/5/23 | 3/14/2023 & 4/28/23-5/23 | 3/14/2023 & 4/28/23 | 0 |  |  | Cancelled
PIP-23-086 | 23MO-01H2D | Supply and Delivery of Flags & Accessories | Goods & Services | GSM | 2023-02-27 | 2023-03-03 | 9:08AM | 2023-03-21 | 18 | PIP | N | NP-SVP | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-03-21 | N/A | 2023-03-27 | N/A | 30days |  | COB | 30000 | 30000 |  | 14070 | 14070 |  | Flags of All Nations | [16 empty] | PO#298676 | Awarded | Completed/Delivered
SM-23-087 | 23MO-07D4 | Cloud Based Email Hosting | Goods & Services | CDBB |  | 2023-03-03 | 3:50PM | 2023-04-11 | 39 | SMO | N | NP-SVP | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-04-11 | 2023-04-12 | 2023-04-26 | 2023-04-25 | 29 days |  | COB | 330000 | 330000 |  | 298000 | 298000 |  | Tierra Networks Technologies Inc. | [9 empty] | 2023-04-26 |  |  |  | Superceded by SM-23-061 |  |  | Contract#23-025 | Awarded | Completed/Delivered
PSD-23-088 | 23MO-05C6 | Temporary Office Services | Goods & Services | CDBB | 2023-03-02 | 2023-03-06 | 9:25PM | 2023-03-21 | 15 | PSD | N | NP-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Contract draft | 2023-03-27 | April- December |  | COB | 5000000 | 5000000 |  | 4812586.65 | 4812586.65 |  | LBP Resources and Development Corporation | [18 empty] | Completed/Delivered
GSD-23-089 | 23MO-01E3 | Audio/Video Player w/ Wireless Microphone | Goods & Services | GSM | 2023-03-03 | 2023-03-07 | 11:20PM | 2023-03-30 | 23 | GSD | N | NP-SVP | N/A | 2023-03-15 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-03-30 | N/A | 2023-04-03 | N/A | 30 days |  | COB | 28000 | 28000 |  | 27995 | 27995 |  | Uly Tech Trading | [9 empty] | 2023-04-13 | [6 empty] | PO#29861 | Awarded | Completed/Delivered
ESB-23-091 | Approved Budget Realignment | Engagement of Consultancy Firm for the Preparation of Engineering Geological and Geohazard Assessment Report | Consulting Services | CFCM | 2023-02-01 | 2023-04-18 | 10:55PM | 2023-05-23 | 35 | ESB | N | NP-SVP | N/A | 2023-04-20 | N/A | N/A | N/A | 2023-05-18 | N/A | 2023-05-23 | 2023-05-24 |  |  | 30 days |  | COB | 200000 | 200000 |  | 199200 | 199200 |  | Woodfields Consultants, Inc. | [11 empty] | 1st&2nd -Non Receipt/3rd - deferred lack of detailed Presentation | 3/28/2023- 4/17/23 | 3/28/2023- 4/17/23 | 3/28/2023- 4/17/23 |  |  | Awarded | Completed/Delivered
PIP-23-092 | 23MO-06C16 | Supply and Delivery of Various Paints | Goods & Services | GSM | 2023-01-24 | 2023-03-10 | 3:40PM | 2023-05-25 | 76 | PIP | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-19 | N/A | 2023-05-25 | N/A | 2023-05-29 | N/A | 30 days |  | COB | 99555 | 99555 |  | 99376.1 | 99376.1 |  | Shigan Construction Supplies Trading | [11 empty] | 1st - Over ABC | 2023-03-27 | 2023-03-27 | 2023-03-28 |  | PO#298693 | Awarded
PIP-23-093 | 23MO-06C9 | Supply and Delivery of Mechanical Consumables for Booster Pumps | Goods & Services | GSM | 2023-01-24 | 2023-03-10 | 3:40PM | 2023-05-30 | 81 | PIP | N | NP-SVP | N/A | 2023-03-18 | N/A | N/A | N/A | 2023-05-26 | N/A | 2023-05-30 | N/A | 2023-06-01 | N/A | 30 days |  | COB | 324632.79 | 324632.79 |  | 157718 | 157718 |  | Manara Marketing | [16 empty] | PO#298696 | Awarded | Completed/Delivered
GSD-23-094 | 23MO-06C16 | Supply and Replacement of 1125kva Caterpillar Genset Motor Starter at PNOC Bldg.5 | Goods & Services | GSM | 2023-02-27 | 2023-03-15 | 3:30PM | 2023-04-13 | 29 | GSD | N | NP-SVP | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-04-13 | 2023-04-17 | 2023-05-31 | 2023-05-18 | 30 days |  | COB | 482000 | 482000 |  | 399764.46 | 399764.46 |  | Tabuko Energy Network Corp. | [16 empty] | Contract #23-029 | Awarded | Completed/Delivered
AM-23-095 | 23MO-04B1E/04B1G/04B1I | Land Surveying Consultancy (Relocation,Subdivision,Leased Area Surveys,As-built survey of PNOC Properties located in Kananga ,Leyte, Limay and Mariveles | Consulting Services | CFCM | 2023-03-14 | 2023-03-16 | 3:30PM | 2023-08-08 | 145 | AMD | N | PB | 2023-04-06 | 2023-04-11 | 2023-05-25 | 2023-04-18 | 2023-06-08 | 2023-06-29 | 2023-08-04 | 2023-08-08 | 2023-08-31 |  |  | 65 Days |  | COB | 1130000 | 1130000 |  | 868000 | 868000 |  | SmartGeo Surveying and Geomatics | COA,MBC,PCCI | 2023-05-17 | 2023-05-17 | 2023-05-17 | 2023-05-17 | [12 empty] | Awarded | For Contract Finalization
PP-23-096 | 23CA-04A10 | Supply, Design, Develop and Installation of PNOC Asset Inventory Management System | Goods & Services | CDBB | 2023-03-13 | 2023-03-16 | 1:27PM | 2023-03-23 | 7 | PRM | N | PB-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-24 | Contract draft |  |  |  | COB | 3640000 | 3640000 |  | 28000000 |  | 28000000 | DBP DATA Center Inc. | [17 empty] | Awarded | Contract Drafting
PSD -23-097 | 23MO-04B1R | Engagement of Retainer Physician for PNOC Head Office | Goods & Services | GSM | 2023-03-13 | 2023-03-21 | 9:30AM | 2023-03-30 | 9 | PSD | N | NP-SVP | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-03-30 | N/A | 2023-03-30 | 2023-03-30 |  | 2023-03-31 | April- December |  | COB | 399999.78 | 399999.78 |  | 399000 | 399000 |  | Dra. Marie Yvette Soriano-Jarmillo,MD,FPCOM | [17 empty] | Awarded | Completed/Delivered
PIP-23-098 | 23CA-05B | Purchase, Supply and Delivery of Three Wheel Electric Motorcycle | Goods & Services | GSM | 2023-03-17 | 2023-03-22 | 9:43AM | 2023-04-11 | 20 | PIP | N | NP-SVP | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-04-04 | N/A | 2023-04-11 | N/A |  | N/A |  |  | COB | 195000 | 195000 |  | 194640 |  | 194640 | Marquay Trading OPC | [9 empty] | 2023-05-08 | [6 empty] | PO#298683 | Awarded | Completed/Delivered
AM-23-099 | 23CA-03T | PNOC Staffhouse Buildings Repair (Re-roofing and re-painting | Infrastructure | CDBB | 2023-03-21 | 2023-03-24 | 11:29AM | 2023-05-30 | 67 | AMD | N | PB |  | 2023-04-11 | 2023-04-18 | 2023-05-04 | 2023-05-04 | 2023-05-17 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-23 | 2023-06-20 | 30 days |  | COB | 1499099.77 | 1499099.77 |  | 1472193.8 |  | 1472193.8 | De Jesus Construction | 2023-04-30 | [15 empty] | Contract # 23-040 | Awarded
PIP-23-100 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station | Goods & Services | CDBB | 2023-03-15 | 2023-04-11 | 4:42PM | 2023-05-11 | 30 | PIP | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-05-02 | N/A |  | N/A |  |  | COB | 142200 |  | 142200 | 39132.5 |  | 39132.5 | RBC (Mariveles)hardware, Inc./UpTown Industrial Sales, Inc, | [10 empty] | Superceded by PIP-23-082 | 2nd- Non receipt | 2023-04-05 | 2023-04-05 | 2023-04-11 | 2023-06-06 | PO#298689/690 | Awarded | Not all Items are Awarded
PSD-23-101 | Approved Budget Reallocation | Conduct of QMS Appreciation Tranings | Goods & Services | GSM | 2023-03-22 | 2023-03-27 | 3:40pm | 2023-05-02 | 36 | PSD | N | NP-SVP | N/A | 2023-04-01 | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-05-02 | 2023-05-04 | 2023-05-22 | 2023-05-19 |  |  | COB | 151200 | 151200 |  | 120000 | 120000 |  | JBDC Occupational Health Safety and Environmental Consultancy | [16 empty] | Contract # 23-031 | Awarded | Completed/Delivered
SM-23-102 | 23CA-04A2 | Supply and Delivery of Desktop Computer | Goods & Services | CDBB |  | 2023-03-29 | 3:31PM | 2023-03-30 | 1 | SMO | N | NP-SVP | N/A | [7 empty] | N/A | 2023-03-31 | N/A |  |  | COB | 689000 |  | 689000 | 689000 |  | 689000 | Columbia Technologies Inc. | [9 empty] | 2023-04-20 | [6 empty] | PO#298680 | Awarded | Completed/Delivered
PSD-23-103 | 23MO-07E10 | Venue Rental for PNOC 50th Anniversary | Goods & Services | CDBB | 2023-03-29 | 2023-04-03 | 4:14PM | 2023-05-16 | 43 | PSD | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-10 | N/A | 2023-05-16 | 2023-05-19 | 2023-08-03 | 2023-06-29 | 1 day |  | COB | 703000 | 703000 |  | 702744 | 702744 |  | The Marquiz Events Place | [16 empty] | Contract#23-035 | Awarded | Completed/Delivered
ESB-23-104 | 23MO-06D5 | Preventive Maintenance Services of Forklift (JAC CPCD 50H | Goods & Services | GSM | 2023-03-29 | 2023-06-07 | 1:54PM | 2023-07-04 | 27 | ESB | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-07-03 | N/A | 2023-07-04 | N/A | 2023-07-07 | N/A | 30 Days |  | COB | 26650 | 26650 |  | 29068 | 29068 |  | JAC Automobile Int'l Phils. Inc. | [11 empty] | 1st - TOR rev & 2nd - Over ABC | 1ST-April 26 / 2ND - May 09 | 1ST-April 26 / 2ND - May 09 | 1ST-April 26 / 2ND - May 09 |  | PO#298716 | Awarded | Completed/Delivered
AM-23-105 | 23MO-01E7 | Supply and Delivery of Electronic Typewriter | Goods & Services | GSM | 2023-03-30 | 2023-06-13 | 10:05AM | 2023-07-04 | 21 | AMD | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-06-27 | N/A | 2023-07-04 | N/A | 2023-07-12 | N/A | 30 days |  | COB | 45000 | 45000 |  | 82380 | 82380 |  | Business Machines Corporation | [11 empty] | 1st -Over ABC | 2023-06-06 | 2023-06-06 | 2023-06-06 |  | PO#298717 | Awarded | Completed/Delivered
TD-23-150 | Approved Budget Realignment | Supply and Delivery of Electronic Typewriter and its comsumable | Goods & Services | GSM | 2023-06-09 | 2023-06-13 | 11:05AM | 2023-07-04 | 21 | TD | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-06-26 | N/A | 2023-07-04 | N/A | 2023-07-12 | N/A | 30 days |  | COB | 45000 | 45000 | [22 empty] | Awarded | Completed/Delivered
ESB-23-106 | 23MO-O1H2 | Supply and Delivery of PPE's and Other Safety Equipments | Goods & Services | GSM | 2023-03-29 | 2023-04-04 | 9:30AM | 2023-06-06 | 63 | ESB | N | NP-SVP | N/A | 2023-05-11 | N/A | N/A | N/A | 2023-06-01 | N/A | 2023-06-06 | N/A | 2023-06-08 | N/A | 30 days |  | COB | 79000 | 79000 |  | 64919.1 | 64919.1 |  | Safetyko Industrial Supplies /Glim Diversified Sales and Services Corp./B2B Non-Specialized Wholesale Trading/Villaflores Trading | [16 empty] | PO#298697/698/699/731 | Awarded | Completed/Delivered
ESB-23-107 | 23MO-01H2C | Supply and Delivery of Safety Signages and Vehicle Sticker | Goods & Services | GSM | 2023-03-31 | 2023-04-04 |  | 2023-07-25 | 112 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 55517 | 55517
PSD-23-108 | 23MO-07E12 | Supply and Delivery of PNOC 50th Anniversary T-shirt with Collar/with cuff | Goods & Services | CDBB | 2023-03-31 | 2023-04-04 | 2:53PM | 2023-05-04 | 30 | PSD | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-04 | N/A | 2023-05-05 | N/A | 30 days |  | COB | 75250 | 75250 |  | 70520 | 70520 |  | King of Kings Trading | [16 empty] | PO#298684 | Awarded | Completed/Delivered
SM-23-109 | 23MO-0782 | Printing of 2024 Wall and Desk Calendars | Goods & Services | CFCM | 2023-04-23 | 2023-04-04 | 3:24PM | 2023-11-05 | 215 | SMO | N | NP-SVP | N/A | 2023-04-21 | N/A | N/A | N/A | 2023-10-05 | N/A | 2023-05-11 | 2023-05-12 |  | 2023-06-01 |  |  | COB | 650000 | 650000 |  | 418845 | 418845 |  | VJ Graphic Arts, inc. | [16 empty] | Contract#23-033 | Awarded
PP-23-110 | 23MO-01C/01B | Supply and Delivery of Consolidated Office Forms (Accountable/Non-Accountable Forms) | Goods & Services | GSM | 2023-04-05 | 2023-04-11 | 9:09AM | 2023-06-20 | 70 | PRM | N | NP-SVP | N/A | 2023-06-10 | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | [5 empty] | COB | 198420.48 | 198420.48 |  | 144444 | 144444 |  | Grandsmart Enterprise | [17 empty] | Awarded
ESB-23-111 | 23MO-061A/06A2/06B2-06B5/06B8-06B12/06C15/06f1/06f2 | Supply and Delivery of Materials for 2023 ESB Annual Maintenance Plan | Goods & Services | GSM | 2023-04-11 | 2023-04-13 | 8:49PM | 2023-06-27 | 75 | ESB | N | NP-SVP | N/A | 2023-04-29 | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | N/A | 2023-07-07 | N/A | 30 days |  | COB | 593536 | 593536 |  | 329529.1 | 329529.1 |  | Greatphil Enterprises Inc./Up-Town Industrial Sales, Inc/United Hardware & General Merchandise / ECM Hardware and Equipments Corp. | [16 empty] | PO#298714/715 | Awarded | Completed/Delivered
GSD-23-112 | 23CA-03B | Replacement of Ceiling Mounted ACU at server room | Goods & Services | GSM | 2023-03-30 | 2023-04-14 | 8:18AM | 2023-05-16 | 32 | GSD | N | NP-SVP | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-05-11 | N/A | 2023-05-16 | 2023-05-17 | 2023-09-11 | 2023-08-11 | 21 days |  | COB | 355806 | 355806 |  | 300000 |  | 300000 | Caresystem Technology Solution Co | [16 empty] | Contract#23-037 | Awarded | Completed/Delivered
PIP-23-113 | 23CA-02A2 | Supply, Delivery, Installation, testing and Commissioning of Level Sensors | Goods & Services | CDBB | 2023-03-10 | 2023-04-14 | 8:40AM |  | -45030 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 849500 |  | 849500 | [15 empty] | 1st -Non Receipt | 2023-05-16 | 2023-05-16 | 2023-05-18
AM-23-114 | 23MO-04B1F | Third Party Appraisal of Various PNOC Properties | Consulting Services | CFCM | 2023-04-14 | 2023-06-09 | 4:30PM | 2023-09-21 | 104 | AMD | N | PB | [13 empty] | COB | 1600000 | 1600000 |  | 1405000 | 1405000 |  | Value Metric Inc. | [11 empty] | 1sT- Ineligible | 2023-05-30 | 2023-05-30 | 2023-05-30 |  |  | Awarded | For Justification/Memo
GSD-23-115 | 23CA-03A/23CA-03G | Waterproofing of PNOC Bldg.5 & 6 | Goods & Services | CDBB | 2023-04-17 | 2023-06-08 | 4:05PM | 2023-09-07 | 91 | GSD | N | PB | 2023-06-13 | 2023-06-15 | 2023-06-22 | 2023-07-06 | 2023-07-06 | 2023-07-17 | 2023-09-06 | 2023-09-07 | [5 empty] | COB | 4200000 |  | 4200000 | 4150000 | 4150000 |  | Isometric Enterprises | COA,MBC,PCCI | 2023-06-22 | 2023-07-06 | 2023-07-06 | 2023-07-13 | 2023-07-25 | [5 empty] | 1st- Non-compliance | 2023-06-06 | 2023-06-06 | 2023-06-06 |  |  | Awarded
GSD-23-116 | 23CA-03I | Preventive Maintenance of 500kw and 2x900kw Stand-by Generator Sets at PNOC Building 5 and 6 | Goods & Services | GSM | 2023-04-13 | 2023-04-25 | 8:35AM | 2023-06-07 | 43 | GSD | N | NP-SVP | N/A | 2023-05-16 | N/A | N/A | N/A | 2023-05-24 | N/A | 2023-06-07 | 2023-06-07 |  |  |  |  | COB | 550145.47 |  | 550145.47 | 444000 |  | 444000 | 3J Power Contruction Corporation | [17 empty] | Awarded
ESB-23-117 | 23CA-03V | Supply and Delivery of Foam-Filled Rubber Fender without Tire Net | Goods & Services | RGV | 2023-04-24 | 2023-04-25 | 1:36PM | 2023-07-13 | 79 | ESB | N | PB | 2023-05-25 | 2023-05-30 | 2023-06-06 | 2023-06-20 | 2023-06-20 | 2023-06-27 | 2023-07-13 | 2023-07-13 | N/A | 2023-07-17 | N/A | 90 days |  | COB | 980000 |  | 980000 | 769800 |  | 769800 | First & Finest Technology Corporation | COA,MBC,PCCI | 2023-06-06 | 2023-06-20 | 2023-06-20 | 2023-06-21 | 2023-06-28 | [10 empty] | PO#298719 | Awarded | For Signing of PO
GSD-23-118 | 23MO-04B15/04B1T | Fleet Monitoring System for PNOC Pooled Vehicle | Goods & Services | CDBB | 2023-04-14 | 2023-04-27 | 8:35AM | 2023-05-23 | 26 | GSD | N | NP-SVP | N/A | 2023-05-09 | N/A | N/A | N/A | 2023-05-17 | N/A | 2023-05-23 | N/A | 2023-05-24 | N/A | 30 days |  | COB | 90000 | 90000 |  | 89936 | 89936 |  | Cartrack Technologies Phl Inc. | [16 empty] | PO#298692 | Awarded | Completed/ Delivered
PIP-23-119 | 23MO-05C5 | Servicing of Genset | Goods & Services | GSM | 2023-04-20 | 2023-07-14 | 9:49AM | 2023-08-10 | 27 | PIP | N | NP-SVP | N/A | 2023-07-21 | N/A | N/A | N/A | 2023-08-09 | N/A | 2023-08-10 | N/A | 2023-08-31 | N/A | 30 days |  | COB | 64685 | 64685 |  | 60000 | 60000 |  | Mabuhay FOXTROTTrading Supply Wholesaling | [9 empty] | 2023-09-06 |  | 1st-non Compliance- | 2023-07-04 | 2023-07-07 | 2023-07-07 |  | PO#298734 | Awarded | Completed/ Delivered
GSD-23-120 | 23CA-03G | Repair/Repainting of Compound Perimeter fence | Goods & Services | RGV | 2023-04-13 | 2023-05-02 | 2:14PM | 2023-07-06 | 65 | GSD | N | PB | 2023-05-11 | 2023-05-16 | 2023-05-23 | 2023-06-08 | 2023-06-08 | 2023-06-13 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-08-07 | 2023-08-04 | 60 days |  | COB | 2800000 |  | 2800000 | 2377650 |  | 2377650 | Jayterkiel Builders | COA,MBC,PCCI | 2023-05-31 | 2023-06-08 | 2023-06-08 | 2023-06-09 | 2023-06-16 |  | 2023-08-10 | 2023-08-10 | 2023-08-10 | [6 empty] | Contract #23-046 | Awarded | Completed/ Delivered
GSD-23-121 | Approved Budget Realignment | Dismantling and Repair of Transfer Pump at PNOC Bldg 6 | Goods & Services | CDBB | 2023-02-27 | 2023-05-02 | 2:14PM | 2023-05-23 | 21 | GSD | N | NP-SVP | N/A | 2023-05-09 | N/A | N/A | N/A | 2023-05-24 | N/A | 2023-05-25 | 2023-06-02 | 2023-06-21 | 2023-06-21 | 30 days |  | COB | 240000 |  | 240000 | 200000 | 200000 |  | Pablo S. Labasbas Construction Corporation | [9 empty] | 2023-06-22 | [6 empty] | Contract #23-041 | Awarded | Completed/ Delivered
GSD-23-122 | Approved Budget Realignment | Replacement of Various Defective Parts of Passenger Elevators at PNOC Bldg.6 | Goods & Services | GSM | 2023-04-13 | 2023-05-02 | 2:14PM |  | -45048 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 137321.42 |  | 137321.42 | [22 empty] | Cancelled
GSD-23-123 | Approved Budget Realignment | De-sludging of PNOC Bldg.6,5.3 and Motorpool Septic Tanks | Goods & Services | GSM | 2023-03-16 | 2023-05-24 | 2:14PM |  | -45070 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 357000 |  | 357000 | [15 empty] | 1st -over ABC /2nd-Non Compliance | 05/17/2023 / 07/28/23 | 05/17/2023 / 07/28/23 | 05/17/2023 / 07/28/23 |  |  |  | Cancelled
GSD-23-124 | 23MO-01H2V | Supply and Delivery of Microfiber Washable PPE | Goods & Services | GSM | 2023-05-04 | 2023-05-05 | 8:40PM | 2023-05-23 | 18 | GSD | N | NP-SVP | N/A | 2023-05-10 | N/A | N/A | N/A | 2023-05-17 | N/A | 2023-05-23 | N/A | 2023-05-23 | N/A | 30 days |  | COB | 5133.3 | 5133.3 |  | 5133.3 | 5133.3 | [18 empty] | PO#298691 | Awarded
PSD-23-125 | Approved Budget Realignment | Engagement of a Training Provider for the Conduct of an IQMS Audit Training | Goods & Services | GSM | 2023-05-02 | 2023-05-05 | 2:19PM | 2023-05-30 | 25 | PSD | N | NP-SVP | N/A | 2023-05-11 | N/A | N/A | N/A | 2023-05-25 | N/A | 2023-05-30 | N/A | 2023-05-31 | N/A | 30 days |  | COB | 200000 |  | 200000 | 60000 |  | 60000 | RPM Methods, Strategies and Documentation Services | [15 empty] | 2023-06-07 | PO#298695 | Awarded | Completed/ Delivered
PSD-23-126 | Approved Budget Realignment | Advanced Training on the use, Application and Writeshop on the Harmonized GAD Guidelines | Goods & Services | CDBB | 2023-04-27 | 2023-05-05 | 2:19PM | 2023-07-18 | 74 | PSD | N | NP-SVP | N/A | 2023-06-23 | N/A | N/A | N/A | 2023-07-13 | N/A | 2023-07-18 | N/A | 2023-08-17 | N/A | Nov.20-21 |  | COB | 38500 | 38500 |  | 49000 | 49000 |  | R.P. Olivar Development Consultancy & Services | [11 empty] | 1st- Change in TOR/2nd-Non-Compliance | 2nd- 6/13/23 | 2023-06-13 | 2023-06-13 |  | PO#298725 | Awarded | Completed/ Delivered
PIP-23-127 | 23MO-01H2M | Supply and Delivery of Consumables for AED | Goods & Services | CDBB | 2023-04-13 | 2023-05-05 | 3:25PM | 2023-05-25 | 20 | PIP | N | NP-SVP | N/A | 2023-05-10 | N/A | N/A | N/A | 2023-05-19 | N/A | 2023-05-25 | N/A | 2023-05-30 | N/A | 30 days |  | COB | 20000 | 20000 |  | 20000 | 20000 |  | Sy Medical Training Corp. | [16 empty] | PO#298694 | Awarded | Completed/Delivered
PIP-23-128 | 23MO-05C3 | Hauling Transport, Treatment and Disposal of Generated Wastes (Non-hazardous Solid Wastes | Goods & Services | GSM |  | 2023-05-05 | 3:25PM | 2023-06-07 | 33 | PIP | N | NP-SVP | N/A | 2023-05-16 | N/A | N/A | N/A | 2023-05-31 | N/A | 2023-06-17 | 2023-06-14 |  |  |  |  | COB | 123200 | 123200 |  | 122000 | 122000 |  | Clean Leaf International Corporation | [13 empty] | Superceded by PIP-23-053 |  |  |  | Awarded | For Contract Drafting
SM-23-129 | 23MO-06E1 | Diagnostic/Check-up of Defective Printer MFP M180N | Goods & Services | GSM |  | 2023-05-08 | 10:35AM |  | -45054 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 2500 | 2500 | [23 empty] | Irrepairable
SM-23-130 | 23CA-04A3 | Supply and Delivery of Rack/Computer Server | Goods & Services | CDBB |  | 2023-05-11 | 9:04AM | 2023-07-11 | 61 | SMO | N | PB | N/A | 2023-05-23 | 2023-05-30 | 2023-06-13 | 2023-06-13 | 2023-06-23 | 2023-07-11 | 2023-07-11 | N/A | 2023-07-13 | N/A | 90 days |  | COB | 1002806.67 |  | 1002806.67 | 846000 |  | 846000 | DCI Int'L it Solutions & Services Corp. | MBC,PCCI, COA | 2023-05-30 | 2023-06-13 | 2023-06-13 | 2023-06-14 | 2023-06-21 | [10 empty] | PO#298718 | Awarded | Completed/Delivered
GSD-23-131 | 23MO-01E5 | Supply and Delivery of Various Maintenance Tools | Goods & Services | CDBB | 2023-05-05 | 2023-05-12 | 10:03AM | 2023-06-08 | 27 | GSD | N | NP-SVP | N/A | 2023-05-23 | N/A | N/A | N/A | 2023-06-05 | N/A | 2023-06-08 | N/A | 2023-06-09 | N/A | 30 days |  | COB | 86378.67 | 86378.67 |  | 29465.2 | 29465.2 |  | KOI Industrial Supply/Co Ban Kiat Hardware Inc. | [16 empty] | PO#298700/701 | Awarded | Completed/Delivered
PIP-23-132 | 23MO-06C13 | Supply and Delivery of Material for the Replacement of Existing Submersible Cable of PW6 and PW7 at PIP | Goods & Services | GSM | 2023-04-26 | 2023-05-12 | 11:02AM | 2023-06-20 | 39 | PIP | N | NP-SVP | N/A | 2023-05-23 | N/A | N/A | N/A | 2023-06-19 | N/A | 2023-06-20 | N/A | 2023-06-22 | N/A | 30 Days |  | COB | 370333 | 370333 |  | 265000 | 265000 |  | Pumpcraft Industrial Sales | [16 empty] | PO#298703 | Awarded | Completed/ Delivered
PIP-23-133 | 23MO-01G | Supply and Delivery of Materials for the Replacement of Damaged Feeder line of R1 | Goods & Services | GSM | 2023-05-14 | 2023-05-12 | 11:02AM | 2023-07-20 | 69 | PIP | N | NP-SVP | N/A | 2023-05-22 | N/A | N/A | N/A | 2023-06-23 | N/A | 2023-07-20 | N/A | 2023-08-31 | N/A | 30 days |  | COB | 83484 | 83484 |  | 77760 | 77760 |  | Up-Town Industrial Sales,Inc. | [16 empty] | PO#298735 | Awarded | Completed/ Delivered
PIP-23-134 | 23MO-01H2M | Supply and Delivery of Conference Chair | Goods & Services | GSM | 2023-04-27 | 2023-05-22 | 8:55AM | 2023-06-22 | 31 | PIP | N | NP-SVP | N/A | 2023-05-27 | N/A | N/A | N/A | 2023-06-21 | N/A | 2023-06-22 | N/A | 2023-06-30 | N/A | 30 days |  | COB | 64000 | 64000 |  | 55192 | 55192 |  | IKF Home Furnishing & office Furniture | [16 empty] | PO#298709 | Awarded | Completed/ Delivered
PIP-23-135 | 23MO-06C2/06C3 | Calibration of Pressure Gauge,UFM abd Flow Totalizer | Goods & Services | GSM | 2023-05-18 | 2023-05-23 | 8:55AM | 2023-06-22 | 30 | PIP | N | NP-SVP | N/A | 2023-05-27 | N/A | N/A | N/A | 2023-06-14 | N/A | 2023-06-22 | N/A | 2023-06-30 | N/A | 30 days |  | COB | 153800 | 153800 |  | 142240 | 142240 |  | Senze Calibration and Measurement Laboratory, Inc. | [16 empty] | PO#298708 | Awarded | Completed/ Delivered
BR-23-136 | 23MO-04A1 | Engagement of Project Consultant for the Development of the PNOC Bunker Fuel Refilling Station | Consulting Services | CFCM | 2023-05-17 | 2023-05-23 | 3:52PM |  | -45069 | BRDD | N | PB | [13 empty] | COB | 9500000 | 9500000 | [23 empty] | Back to Proponent
GSD-23-137 | 23CA-03K | Supply and Installation of Concrete Pole at Records Center | Goods & Services | CDBB | 2023-05-15 | 2023-05-23 | 9:15AM | 2023-06-13 | 21 | GSD | N | NP-SVP | N/A | 2023-05-27 | N/A | N/A | N/A | 2023-06-09 | N/A | 2023-06-13 | 2023-06-15 | 2023-07-04 | 2023-06-29 | 7 days |  | COB | 515833.4 |  | 515833.4 | 470000 |  | 470000 | Pablo S. Labasbas Construction Corporation | [16 empty] | Contract#23-043 | Awarded | Completed/ Delivered
PSD-23-138 | Approved Budget Inclusion | 2023 PNOC Health and Wellness Program Dance Instructor | Goods & Services | CDBB | 2023-05-22 | 2023-06-20 | 4:55PM |  | -45097 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 265000 | 265000 | [16 empty] | 1st-Non receipt Quotation | 2023-06-19 | 2023-06-19 | 2023-06-19
ESB-23-139 | 23MO-06G1 | Supply and Delivery of Screw Pin Anchor Shackle, Galvanized | Goods & Services | CDBB | 2023-05-22 | 2023-05-24 | 2:58PM | 2023-06-20 | 27 | ESB | N | NP-SVP | N/A | 2023-05-30 | N/A | N/A | N/A | 2023-06-09 | N/A | 2023-06-20 | N/A | 2023-06-22 | N/A | 30 Days |  | COB | 18800 | 18800 |  | 10880 | 10880 |  | Villaflores Industrial Supply | [16 empty] | PO#298702 | Awarded | Completed/ Delivered
PIP-23-140 | 23MO-07E8 | CSR Support for Schools of Brgy. Batangas Dos | Goods & Services | GSM | 2023-05-22 | 2023-05-29 | 9:03AM | 2023-07-13 | 45 | PIP | N | NP-SVP | N/A | 2023-06-07 | N/A | N/A | N/A | 2023-07-14 | N/A | 2023-07-13 | N/A | 2023-09-05 | N/A | 30 Days |  | COB | 29236 | 29236 |  | 23990 | 23990 |  | ZAB Enterprises Inc. /ShiganConstruction Supplies Trading | [16 empty] | PO#298737 | Awarded | Completed/ Delivered
PIP-23-141 | 23MO-01G | Supply and Delivery of Torque Wrench | Goods & Services | CDBB | 2023-05-18 | 2023-05-29 | 9:03AM |  | -45075 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 9784 | 9784 | [22 empty] | Awarded
PIP-23-142 | 23MO-01G | Supply and Delivery of Inverter Welding Machine | Goods & Services | CDBB | 2023-05-05 | 2023-05-29 | 9:03AM |  | -45075 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 24505 | 24505 | [22 empty] | Awarded
PIP-23-143 | 23MO-01H2M | Purchase, Supply and Delivery of Foldable platform Truck Trolley and Vacuum Cleaner | Goods & Services | CDBB | 2023-05-22 | 2023-07-03 | 9:03AM | 2023-07-20 | 17 | PIP | N | NP-SVP | N/A | 2023-07-06 | N/A | N/A | N/A | 2023-07-17 | N/A | 2023-07-20 | N/A | 2023-08-29 | N/A | 30 days |  | COB | 11000 | 11000 |  | 9900 | 9900 |  | Co Ban Kiat Hardware Inc. | [9 empty] | 2023-07-05 | [6 empty] | PO#298706 | Awarded | Vacuum Only
PIP-23-144 | 23MO-01G | Purchase of Electrical Materials, Consumables and Supplies | Goods & Services | CDBB | 2023-05-26 | 2023-05-31 | 11:30AM |  | -45077 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 78025 | 78025 |  | 32695 | 32695 |  | Ecoshift Corporation | [17 empty] | Awarded
SM-23-145 | 23MO-03A1 | 2023 internet/Leased Line Connection for ESB |  | RGV |  | 2023-05-31 | 2:05PM |  | -45077 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 300000 | 300000
PP-23-146 | 23MO-06C18 | Repair/Refurbishing of Furniture | Goods & Services | GSM | 2023-06-01 | 2023-06-06 | 2:40PM | 2023-06-27 | 21 | PRM | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-06-22 | N/A | 2023-06-27 |  |  |  | 30 days |  | COB | 110000 | 110000 |  | 69680.2 | 69680.2 |  | Dargo Design Component Builders Corp. | [17 empty] | Awarded
PSD-23-147 | 23MO-07E10 | Engagement of a Service Provider for the Overall Event Management for the 50th Anniversary Gala of PNOC | Goods & Services | CFCM | 2023-06-06 | 2023-07-03 | 2:05PM |  | -45110 | PSD | N | PB | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 1600000 | 1600000
PSD-23-148 | 23MO-07E108 | Supply and Delivery of PNOC 50th Anniversary Token (Wrist Watch) | Goods & Services | CDBB | 2023-05-16 | 2023-06-07 | 3:00PM |  | -45084 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 160000 | 160000 | [16 empty] | 1st - Non Compliance | [6 empty] | Cancelled
PSD-23-149 | 23MO-01D | Supply and Delivery of COVID Response Disinfectant Supplies (Face Mask) for JUL-OCT 2023) | Goods & Services | CDBB | 2023-06-06 | 2023-06-07 | 3:00PM | 2023-06-29 | 22 | PSD | N | NP-SVP | N/A | 2023-06-09 | N/A | N/A | N/A | 2023-06-20 | N/A | 2023-06-29 | N/A | 2023-07-05 | N/A | 30 days |  | COB | 54250 | 54250 |  | 34650 | 34650 |  | Ban Bee Commercial Co | [16 empty] | PO#298710 | Awarded | Completed/Delivered
PSD-23-151 | 23MO-07F2 | CY2023 Annual Physical Examination(APE) for PNOC Employees | Goods & Services | CDBB | 2023-06-06 | 2023-06-13 | 11:51AM | 2023-08-22 | 70 | PSD | N | NP-SVP | N/A | 2023-06-17 | N/A | N/A | N/A | 2023-08-17 | N/A | 2023-08-22 | 2023-08-22 |  |  | 1 month |  | COB | 465000 | 465000 |  | 282612 | 282612 |  | Christian Medical Clinic, Inc. | [17 empty] | Awarded | For Justification Memo
PIP-23-152 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station (part II) | Goods & Services | CDBB | 2023-06-05 | 2023-06-14 | 8:42AM | 2023-07-11 | 27 | PIP | N | NP-SVP | N/A | 2023-06-17 | N/A | N/A | N/A | 2023-07-03 | N/A | 2023-07-11 | N/A | 2023-07-17 | N/A | 30 days | 30 days | COB | 87057 |  | 87057 | 79166 |  | 79166 | RBC(Mariveles) Hardware,Inc./Up-Town Industrial Sales, Inc. | [9 empty] | 2023-07-20 | [6 empty] | PO#298720/721 | Awarded | Completed/Delivered
PIP-23-153 | 23MO-01E6 | Supply and Delivery of Heavy Duty Battery Charger | Goods & Services | CDBB | 2023-06-09 | 2023-06-14 | 8:42AM |  | -45091 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 14700 | 14700 | [23 empty] | Superceded by PIP-23-085
PIP-23-154 | 23MO-06C1 | Calibration of Alcohol Breath Analyzer | Goods & Services | GSM | 2023-06-02 | 2023-06-14 | 8:42AM | 2023-07-13 | 29 | PIP | N | NP-SVP | N/A | 2023-06-20 | N/A | N/A | N/A | 2023-07-04 | N/A | 2023-07-13 | N/A | 2023-07-17 | N/A | 30 days |  | COB | 5200 | 5200 |  | 4704 | 4704 |  | GLJM Diversified Sales and Services Corp. | [16 empty] | PO#298722 | Awarded | Ongoing
PIP-23-155 | 23CA-030 | Rehabilitation of Maingate Security Guard Buillding and Guard House | Infrastructure | CFCM | 2023-06-01 | 2023-06-15 | 2:12PM |  | -45092 | PIP | N | PB | [13 empty] | COB | 2740000 |  | 2740000
GSD-23-156 | 23CA-03L | Technical Evaluation, Diagnosis and Analysis of Building 5 & 6 Electrical System | Goods & Services | CDBB | 2023-05-25 | 2023-06-16 | 8:32AM |  | -45093 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 761280 |  | 761280 | [21 empty] | Awarded | Pending at OP
SM-23-157 | 23MO-01E10 | Supply and Delivery of Essential ICT Supplies | Goods & Services | GSM |  | 2023-06-16 | 2:38PM | 2023-08-08 | 53 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 36240 | 36240 |  | 800 | 800 |  | Agile Techfrontier Corporation | [9 empty] | 2023-09-06 | [6 empty] | PO#298732 | Awarded | incomplete
ESB-23-158 | 23CA-03U | Rehabilitation of Warehouse 1,2,3, and 4 (Concrete Walls and Roof Drainage) | Infrastructure | CFCM | 2023-06-14 | 2023-06-16 | 4:25PM |  | -45093 | ESB | N | PB | [13 empty] | COB | 4975000 |  | 4975000
PIP-23-159 | 23MO-07E7 | Supply and Delivery of Materials for the 2023 Tree Planting Activity | Goods & Services | CDBB | 2023-06-14 | 2023-06-20 | 8:45AM | 2023-06-29 | 9 | PIP | N | NP-SVP | N/A | 2023-06-23 | N/A | N/A | N/A | 2023-06-26 | N/A | 2023-06-29 | N/A | 2023-06-29 | N/A | 30 days |  | COB | 38200 | 38200 |  | 30332 | 30332 |  | Ceboom Enterprises | [9 empty] | 2023-07-05 | [6 empty] | PO#298705 | Awarded
PSD-23-160 | 23MO-481Q | PNOC Scholarship Program for SY 2023-2024 (Conduct of Testing Exam) | Goods & Services | CDBB | 2023-06-20 | 2023-06-23 | 10:05AM | 2023-07-27 | 34 | PSD | N | NP-SVP | N/A | 2023-06-30 | N/A | N/A | N/A | 2023-07-26 | N/A | 2023-07-27 | N/A |  | N/A | 30 days |  | COB | 21200 | 21200 |  | 7200 | 7200 |  | Asian Psychological Servces & Assessment Inc. | [16 empty] | PO#298738 | Awarded | Completed/Delivered
OP-23-161 | 23MO-01H1H | Supply and Delivery of Corporate Tokens for 2023 | Goods & Services | GSM |  | 2023-06-23 | 11:30AM |  | -45100 | OP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 310000 | 310000 | [23 empty] | Ongoing
PP-23-162 | 23MO-01A | Supply and Delivery of Consolidated Computer Supplies, for 2nd & 3rd QTR year 2023 | Goods & Services | GSM | 2023-06-22 | 2023-06-26 | 9:40AM | 2023-08-22 | 57 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 982687 | 982687 | [23 empty] | Ongoing
GSD-23-163 | Approved Budget Realignment | Replacement of Two Broken Window Glass at PNOC Bldg.6 | Goods & Services | GSM | 2023-06-20 | 2023-07-03 | 2:30PM | 2023-08-01 | 29 | GSD | N | NP-SVP | N/A | 2023-07-11 | N/A | N/A | N/A | 2023-08-01 | N/A | 2023-08-01 | N/A | 2023-08-07 | N/A | 30 days |  | COB | 50160 | 50160 |  | 48350 | 48350 |  | G.C. Sales Builders | [9 empty] | 2023-08-23 | [6 empty] | PO#298724 | Awarded | Completed/Delivered
PIP-23-164 | 23MO-01H2K | Supply and Delivery Safety Signages | Goods & Services | GSM | 2023-06-30 | 2023-07-04 | 10:25AM | 2023-07-25 | 21 | PIP | N | NP-SVP | N/A | 2023-07-11 | N/A | N/A | N/A | 2023-07-20 | N/A | 2023-07-27 | N/A | 2023-08-30 | N/A | 30 days |  | COB | 10000 | 10000 |  | 8682 | 8682 |  | PBOX Creative Advertising Corporation | [16 empty] | PO#298733 | Awarded | Completed/Delivered
PSD-23-165 | 23MO-07E10C | Supply and Delivery of PNOC 2023 Anniversary Raffle Items | Goods & Services | CDBB | 2023-06-30 | 2023-07-04 | 10:10PM | 2023-08-01 | 28 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 448500 | 448500
PP-23-166 | 23MO-04B1S | Appraisal of PNOC,PAFC,PSTC & PDMC Vehicles and Unserviceable Properties for Disposal | Goods & Services | GSM | 2023-06-30 | 2023-07-10 | 9:42AM | 2023-08-08 | 29 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 100000 | 100000
SMO-23-167 | 23MO-06E1 | Repair of Printer Epson L385 | Goods & Services | GSM |  | 2023-07-11 | 1:42PM |  | -45118 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 2500 | 2500
PIP-23-168 | 23CA-03R | Supply and Delivery of 1500 Liters Diesel (Mother Tank/Supply) Tank at R2 | Goods & Services | CDBB | 2023-07-11 | 2023-07-17 | 8:51AM | 2023-08-22 | 36 | 0 | N | NP-SVP | N/A | 2023-08-01 | N/A | N/A | N/A | 2023-08-16 | N/A | 2023-08-22 | 2023-08-22 |  |  |  |  | COB | 247500 |  | 247500 | 218000 | 218000 |  | Pumpcraft Industrial Sales | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | For Justification Memo
PRM-23-169 | 23MO-01 | Supply and Delivery of Various Tissue(3rd&4th QTR) | Goods & Services | GSM | 2023-07-18 | 2023-07-19 | 9:06AM | 2023-08-22 | 34 | PRM | N | NP-SVP | N/A | 2023-07-31 | N/A | N/A | N/A | 2023-08-14 | N/A | 2023-08-22 | N/A |  | N/A |  |  | COB | 20678.81 | 20678.81 |  | 20104.5 | 20104.5 |  | Eco-Hygiene Institutional Sales Corp./ Sanitary Care Products Asia, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | For Justification Memo
PRM-23-170 | 23MO-01A | Supply and Delivery of Consolidated Commonly Used Supplies, 2nd & 3rd QTR | Goods & Services | GSM | 2023-07-17 | 2023-07-20 | 10:30AM |  | -45127 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 556990.38 | 556990.38
PSD-23-171 | Approved Budget Realignment | Supply and Delivery of Costumes for the Members of PNOC Voices | Goods & Services | CDBB | 2023-06-29 | 2023-07-26 | 9:19AM | 2023-08-24 | 29 | PSD | N | NP-SVP | N/A | 2023-08-01 | N/A | N/A | N/A | 2023-08-23 | N/A | 2023-08-24 | 2023-08-31 | 2023-09-14 | 2023-09-14 | 45 days |  | COB | 142000 | 142000 |  | 136500 | 136500 |  | JEM Tangco Fashion House | [16 empty] | Contract#23-049 | Awarded | Completed/Delivered
PIP-23-172 | 23MO-06C5 | Pullout, Repair, and Reinstallation of Submersible Pumps and Motors and/or PMS of Production Wells | Goods & Services | CDBB | 2023-07-03 | 2023-08-07 | 9:13AM | 2023-09-05 | 29 | PIP | N | NP-SVP | N/A | 2023-08-25 | N/A | N/A | N/A | 2023-09-04 | N/A | 2023-09-05 | [5 empty] | COB | 875000 | 875000 |  | 868795.2 | 868795.2 |  | E.J.U. Trading
PSD-23-173 | Approved Budget Realignment | Conduct of Values Orientation Workshop (VOW) | Goods & Services | CDBB | 2023-08-03 | 2023-08-07 | 3:34PM |  | -45145 | PSD | Y | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 180000 | 180000
SMO-23-174 | 23CA-04A5 | PNOC Network Rehabilitation and Reconfiguration Project | Goods & Services | RGV |  | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 4000000 |  | 4000000
SMO-23-175 | 23CA-04A9 | MS Office Upgrade (Home & Business 2021) | Goods & Services | RGV |  | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 1112500 |  | 1112500
SMO-23-176 | 23-CA04A7 | Laptop Computers | Goods & Services | RGV |  | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 426000 |  | 426000
SMO-23-177 | 23CA-04A6 | Desktop Computer Set | Goods & Services | RGV | 2023-08-22 | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 340000 |  | 340000
SMO-23-178 | 23CA-04A8 | Network Attached Storage (NAS) with Installed 4x4TB SATA SSD | Goods & Services | RGV |  | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 555020 |  | 555020
SMO-23-179 | 23CA-04A4 | POE Switch 24-Ports | Goods & Services | RGV | 2023-06-16 | 2023-09-04 | 1:30PM |  | -45173 | SMO | Y | PB | [13 empty] | COB | 914326.67 |  | 914326.67
GSD-23-180 | 23MO-06C16 | Instrumentation Testing of 3508 caterpillar Genset at PNOC Bldg.5 | Goods & Services | GSM | 2023-07-20 | 2023-09-05 | 1:45PM | 2023-09-21 | 16 | GSD | N | NP-SVP |  |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 65300 | 65300 |  | 56500 | 56500 |  | Tabuko Energy Network Corp. | [17 empty] | Awarded
CS-23-181 | 23MO-01H2A | Supply and Delivery of Calling Cards for Directors | Goods & Services | RACC | 2023-09-11 | 2023-09-19 | 3:05PM |  | -45188 | CORSEC | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 2000 | 2000
SMO-23-182 | 23MO-01E10 | Supply and Delivery of Essential ICT Supplies Part II | Goods & Services | GSM | 2023-09-19 | 2023-09-19 | 4:05PM |  | -45188 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 40200 | 40200
PSD-23-183 | 23MO-07E108 | Supply and Delivery of PNOC 50th Anniversary Token (Tumbler) | Goods & Services | CDBB | 2023-09-14 | 2023-09-21 | 1:15PM |  | -45190 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 160000 | 160000
OP-23-184 | Approved Budget Inclusion | Supply and Delivery of PNOC 50th Anniversary Souvenir ( USB- Adapter) | Goods & Services | RACC |  | 2023-09-26 |  |  | -45195 | OP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 368000 | 368000
OP-23-185 | Approved Budget Realignment | Supply and Delivery of Tablet Computer | Goods & Services | RGV | 2023-08-23 | 2023-09-27 | 2:35PM |  | -45196 | OP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 189000 | 189000
PSD-23-186 | 23MO-01H1G | Supply and Delivery of Wood Plaque (For Retiree) | Goods & Services | GSM | 2023-09-21 | 2023-09-27 | 2:50PM |  | -45196 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 4000 | 4000
|  | PP-22-084 | 2022-05-11
51
Formulas:
Date PR Awarded = [Date of BAC Reso Reco Award]
Sub/Open of Bids = [Eligibility Check]
Date of BAC Reso Reco Award = [Date PR Awarded]
Eligibility Check = [Sub/Open of Bids]

## RMB-PMR 2024
PHILIPPINE NATIONAL OIL COMPANY
2024 FIRST SEMESTER PROCUREMENT MONITORING REPORT
PR NO. | Code (PAP) *from APP | Procurement Program/Project | Classification *Goods and Services, Infrastructure or Cosnulting Services | Account Officer *Initials | Date of PR | Date PR Received | Time Received | Date PR Awarded | TAT (days) | PMO/ End-User | Is this an Early Procurement Activity? Y/N | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Winning Bidder | List of Invited Observers | Date of Receipt of Invitation | [7 empty] | Submitted to COA |  | Reason of Failure |  |  |  |  | Payment Oder No./Contract No. | STATUS / REMARKS *Ongoing / Completed | STATUS as of today
[13 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf / Negotiation | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Reso Reco Award | Notice of Award | Contract Signing/ PO | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/Acceptance (if applicable) | Submission to IAO | Submission to OGC |  | Rebid |  | Date of Failure of Bidding | Date of Memo to Proponent (Failure of Bid) | Date Received Memo by Proponent | Date of Submitted CSS Form
COMPLETED PROCUREMENT ACTIVITIES
SMO-24-001 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Energy Supply Base | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | 2024-12-31 |  | COB | 608000 | 608000 |  | 555397.33 |  | 555397.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [10 empty] | Contract#24-001 | Completed | Transmitted to End-User 2/20/24
SMO-24-002 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Industrial Park | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | 2024-12-31 |  | COB | 735000 | 735000 |  | 673647.33 |  | 673647.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [10 empty] | Contract#24-001 | Completed | Transmitted to End-User 2/20/24
SMO-24-003 | 24CA-04A3 | PNOC Network Rehabilitation and Reconfiguration Project | Goods & Services | CFCM |  | 2024-01-15 | 2:53PM | 2024-03-14 | 59 | SMO | N | PB | 2024-01-23 | 2024-01-25 | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 2024-02-29 | 2024-03-14 | 2024-03-14 | 2024-04-29 | 2024-04-05 | 90 days |  | COB | 4900000 |  | 4900000 | 4792565 |  | 4792565 | Pronet Systems Integrated Network Solution, Inc. | MBC, COA, PCCI | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-16 | 2024-02-22 | [10 empty] | Contract#24-002 | Completed | Received Signed 3.15.24
SMO-24-004 | 24CA-04A2 | Supply and Delivery of Laptop Computers | Goods & Services | CFCM | 2023-12-18 | 2024-01-15 | 2:53PM | 2024-04-01 | 77 | SMO | N | NP-SVP | N/A | 2024-02-01 | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-28 | 2024-04-01 | 2024-04-01 | N/A | 2024-04-04 | N/A | 90 days |  | COB | 706000 |  | 706000 | 626690 |  | 626690 | Joneco Tech Marketing Corporation | MBC, COA, PCCI | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-29 | 2024-03-12 | [10 empty] | PO#298785 | Completed | rEceived Signed PO 4.15.24
GSD-24-005 | 24MO-07B | 2024 Security Services for PNOC Head Office | Goods & Services | RGV | 2024-01-09 | 2024-01-25 | 11:00AM | 2024-04-16 | 82 | GSD | N | PB | 2024-01-31 | 2024-02-06 | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-26 | 2024-04-12 | 2024-04-16 | 2024-04-16 | 2024-05-08 | 2024-04-26 | 2024-12-31 |  | COB | 10400000 | 10400000 |  | 10333557.5 | 10333557.5 |  | Eliteblue Security Specialist, Inc. | MBC, COA, PCCI | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-08 | 2024-03-16 | [10 empty] | Contract#24-003 | Completed | Completed/Delivered
SMO-24-006 | 24MO-06A1 | Consulting Services for the Digital Transformation Initiative of PNOC | Consulting Services | CFCM | 2024-01-22 | 2024-01-26 | 8:30AM | 2024-01-31 | 5 | SMO | N | NP-AA | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-02 | 2024-03-11 | 2024-03-01 | 2024-12-31 |  | COB | 4950000 | 4950000 |  | 4912969.56 | 4912969.56 |  | University of the Philippines | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Completed
PIP-24-007 | 24MO-08D1U | 2024 Preventive Maintenance of PNOC Gym Equipment | Goods & Services | GSM | 2024-01-31 | 2024-02-20 | 11:09AM | 2024-03-14 | 23 | PRM | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-13 | N/A | 2024-03-14 | N/A | 2024-03-18 | N/A | 2024-12-31 | COB | COB | 48000 | 48000 |  | 48000 | 48000 |  | The FitCo, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298783 | Completed | Completed/Delivered
GSD-24-009 | 24MO-03A9AN | Purchase of Materials for Fabrication of of Bed Frame | Goods & Services | GSM | 2024-01-25 | 2024-02-08 | 1:35PM | 2024-03-19 | 40 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4665 | 4665 |  | 3120 | 3120 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
GSD-24-012 | 24MO-03A9AN | Carpentry Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 7145 | 7145 |  | 4940 | 4940 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
GSD-24-013 | 24MO-03A9AN | Plumbing Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 12196 | 12196 |  | 9650 | 9650 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
GSD-24-014 | 24MO-03A9AN | Electrical Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4133.75 | 4133.75 |  | 3231 | 3231 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
GSD-24-015 | 24MO-08D1W | Aircon Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 34490.57 | 34490.57 |  | 33892 | 33892 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
SMO-24-016 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token | Goods & Services | GSM |  | 2024-03-01 | 4:15PM | 2024-04-25 | 55 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-22 | N/A | 2024-04-25 | N/A | 2024-04-25 | N/A | 30 days |  | COB | 275000 | 275000 |  | 215520 | 215520 |  | Jen Lin Corporate Giveaways | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298787 | Completed | Completed/Delivered
PSD-24-017 | 24MO-038AC | Supply and Delivery of Fluquadri (Adult) | Goods & Services | RGV | 2024-02-19 | 2024-03-06 | 4:15PM | 2024-04-18 | 43 | PSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-16 | N/A | 2024-04-18 | N/A | 2024-04-23 | N/A | 15 days |  | COB | 85000 | 85000 |  | 61456 | 61456 |  | Pharma Quest Co. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298786 | Completed | Completed
PRM-24-020 | 24MO-03A1 | Supply and Delivery of Consolidated Commonly-Use Supplies for January-February 2024 | Goods & Services | GSM | 2024-03-20 | 2024-03-11 | 2:30PM | 2024-05-16 | 66 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | 2024-05-29 | N/A | 30 days |  | COB | 333058.99 | 333058.99 |  | 240263.15 | 240263.15 |  | Varyline & Lambert Trading | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298795/ 298796 | Completed | Completed/Delivered
PIP-24-021 | 24MO-07C5D | Hauling, Transport, Treatment and Disposal of Generated Hazardous wastes of PIP | Goods & Services | RGV | 2024-01-23 | 2024-03-14 | 9:16AM | 2024-05-28 | 75 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-05-24 | N/A | 2024-05-28 | 2024-06-04 | 2024-06-24 | 2024-07-01 | 30 days |  | COB | 137917 | 137917 |  | 104500 | 104500 |  | Clean Leaf Intrenational Corp. | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Completed | NOA/for Contract Draft
PIP-24-023 | 24MO-06B6 | 2024 Environmental Monitoring (Waste Water-Effluent and Marine, Raw Water, Ambient Air Sampling and Laboratory Analysis) | Goods & Services | RGv | 2023-09-06 | 2024-03-22 | 10:09AM | 2024-05-27 | 66 | PIP | N | PB | N/A | 2024-04-04 | 2024-04-11 | 2024-04-25 | 2024-04-25 | 2024-05-03 | 2024-05-27 | 2024-05-28 | 2024-05-30 | 2024-06-21 | 2024-06-13 | 2024-12-31 |  | COB | 825000 | 825000 |  | 688140 | 688140 |  | CRL Environmental Corporation | COA/MBC/PCCI | 2024-04-11 | 2024-04-25 | 2024-04-25 | 2024-05-03 | 2024-05-28 | [10 empty] | Contract#24-009 | Completed
SMO-24-024 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token(Bamboo Stainless Cup) | Goods & Services | CFCM |  | 2024-03-25 | 1:58PM | 2024-04-25 | 31 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-23 | N/A | 2024-04-25 | N/A | 2024-04-30 | N/A | 30 days | COB | COB | 90000 | 90000 |  | 40000 | 40000 |  | CSG Manufacturing Corporation | N/A | 2024-04-26 | 2024-04-03 | 2024-05-16 | 2024-05-16 | 2024-05-16 | [10 empty] | PO#298788 | Completed | Completed/Delivered
PIP-24-025 | 24MO-03A7C/08D1L | Supply and Delivery of Electrical Items(Batteries for Genset and Fire Engine) | Goods & Services | GSM | 2024-01-15 | 2024-03-25 | 2:37PM | 2024-04-25 | 31 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-25 | N/A | 2024-04-25 | N/A | 2024-05-07 | N/A | 30 days |  | COB | 195600 | 195600 |  | 153614 | 153614 |  | 8 Days A Week Consumer Goods Trading | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298789 | Completed | Completed/Delivered
GSD-24-026 | 24MO-04A3 | 2024 Supply and Delivery of Drinking Water | Goods & Services | GSM | 2024-03-12 | 2024-04-04 | 9:03AM | 2024-04-23 | 19 | GSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-19 | N/A | 2024-04-23 | 2024-04-29 | 2024-06-21 | 2024-04-30 | 2024-12-31 |  | COB | 212000 | 212000 |  | 176320 | 176320 |  | MSDR Water Refilling Station | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-013 | Completed | Contract for Signing of EAL
SMO-24-027 | 24MO-09D15 | Supply and Delivery of Barcode Scanner | Goods & Services | GSM | 2024-04-04 | 2024-04-05 | 11:50AM | 2024-04-30 | 25 | SMO | N | NP-SVP | N/A | 2024-04-12 | N/A | N/A | N/A | 2024-04-25 | N/A | 2024-04-30 | N/A | 2024-05-08 | N/A | 30 days |  | COB | 211000 | 211000 |  | 56440 | 56440 |  | A.G. Datacom Phis.,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298790 | Completed | Completed/Delivered
PSD-24-028 | 24MO-07C2 | 2024 Temporary Office Services | Goods & Services | RGV |  | 2024-04-11 | 8:30AM | 2024-04-11 | 0 | PSD | N | NP-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-05-30 | 2024-04-26 | 2024-12-31 |  | COB | 9500000 | 9500000 |  | 7464399.68 | 7464399.68 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-004 | Completed | Completed/Delivered
SMO-24-029 | 24MO-09D6 | Supply and Delivery of Cloud-based Email, Productivity, and Collaboration Service Subscription / Email Hosting Service Subscription | Goods & Services | RGV |  | 2024-04-17 | 2:30PM | 2024-05-30 | 43 | SMO | N | PB | 2024-04-25 | 2024-04-26 | 2024-04-03 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-23 | 2024-05-30 | 2024-05-30 | 2024-07-01 | 2024-06-25 | 30 days |  | COB | 1800000 | 1800000 |  | 1383810.97 | 1383810.97 |  | ePLDT,Inc. | COA/MBC/PCCI | 2024-04-04 | 2024-04-11 | 2024-04-25 | 2024-04-25 | 2024-05-03 | [11 empty] | Completed | NTP/Contract for Sign of OP
PSD-24-030 | 24CA-04F | Supply, Delivery, Installation and Implementation of Time and Attendance Monitoring System w/ 3 Biometric devices (facial recognition/finger scan) | Goods & Services | RGV | 2024-03-25 | 2024-04-19 | 1:08PM | 2024-05-14 | 25 | PSD | N | NP-SVP | N/A | 2024-05-09 | N/A | N/A | N/A | 2024-05-14 | N/A | 2024-05-14 | 2024-05-14 | 2024-06-30 | 2024-06-23 | 15 days |  | COB | 800000 |  | 800000 | 635000 |  | 635000 | 3GX Computer and IT Solutions Techshop | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-006 | Completed | Completed/Delivered
GSD-24-031 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at G/Fr. Zone #1 Compressor#1 of PNOC Bldg.5 | Goods & Services | GSM | 2024-02-29 | 2024-04-18 | 11:17AM | 2024-04-30 | 12 | GSD | N | NP-SVP | N/A | 2024-04-24 | N/A | N/A | N/A | 2024-04-29 | N/A | 2024-04-30 | 2024-04-30 | 2024-06-30 | 2024-05-02 | 30 days |  | COB | 161760 | 161760 |  | 140000 | 140000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #24-011 | Completed | Contract for Sign of OP 6.24.24
GSD-24-032 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at 2nd/Flr. Zone #1 Compressor#2 of PNOC Bldg.5 | Goods & Services | GSM | 2024-01-25 | 2024-04-23 | 11:35AM | 2024-04-30 | 7 | GSD | N | NP-SVP | N/A | 2024-04-24 | N/A | N/A | N/A | 2024-04-29 | N/A | 2024-04-30 | 2024-04-30 | 2024-06-30 | 2024-05-02 | 30 days |  | COB | 162720 | 162720 |  | 135000 | 135000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #24-011 | Completed | Contract for Sign of OP 6.24.24
GSD-24-033 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at 3rd/Flr. Zone #2 of PNOC Bldg.5 | Goods & Services | GSM | 2024-04-17 | 2024-04-23 | 9:20AM | 2024-04-30 | 7 | GSD | N | NP-SVP | N/A | 2024-04-24 | N/A | N/A | N/A | 2024-04-29 | N/A | 2024-04-30 | 2024-04-30 | 2024-07-01 | 2024-05-02 | 30 days |  | COB | 161760 | 161760 |  | 138000 | 138000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #24-011 | Completed | Contract for Sign of OP 6.24.24
CS-24-034 | Memo Realignment | Corporate Retreat and Planning of Board of Directors | Goods & Services | CFCM | 2024-04-22 | 2024-04-24 | 2:43PM | 2024-05-10 | 16 | CORSEC | N | NP-SVP | N/A | 2024-05-04 | N/A | N/A | N/A | 2024-05-08 | N/A | 2024-05-10 | 2024-05-09 | 2024-06-10 | 2024-05-13 | 3 days |  | COB | 400000 | 400000 |  | 398000 | 398000 |  | Marivent Resort Hotel, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-005 | Completed | Contract for Signing of Contractor
GSD-24-035 | 24MO-08C2C | 2024 Pest Control Services for PNOC Building at Fort Bonifacio and PNOC Property in Tagaytay | Goods & Services | GSM | 2024-03-11 | 2024-04-05 | 9:41AM | 2024-05-16 | 41 | GSD | N | NP-SVP | N/A | 2024-05-07 | N/A | N/A | N/A | 2024-05-14 | N/A | 2024-05-16 | N/A | 2024-05-27 | N/A | 2024-12-31 |  | COB | 81000 | 81000 |  | 68200 | 68200 |  | Ram Pest Control Services | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298793 | Completed | Completed/Delivered
PIP-24-036 | 24MO-08D1Q | Supply and Delivery of Lighting Panel Board | Goods & Services | GSM | 2024-01-31 | 2024-04-18 | 9:45AM | 2024-05-21 | 33 | PIP | N | NP-SVP | N/A | 2024-05-07 | N/A | N/A | N/A | 2024-05-17 | N/A | 2024-05-21 | N/A | 2024-05-28 | N/A | 30 days |  | COB | 120000 | 120000 |  | 110000 | 110000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298794 | Completed | Completed/Delivered
GSD-24-037 | 24MO-08D1X | Reconditioning /Rehabilitation of 900kW Caterpillar Genset Alternator at PNOC Bldg.5 | Goods & Services | CFCM | 2024-03-12 | 2024-04-19 | 2:33PM | 2024-06-06 | 48 | GSD | N | PB | 2024-04-30 | 2024-05-02 | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-29 | 2024-06-06 | 2024-06-06 | 2024-06-06 |  | 2024-06-21 | 30 days |  | COB | 1755291.67 | 1755291.67 |  | 1495600 | 1495600 |  | Tabuko Energy Network Corp. | COA/MBC/ PCCI | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-28 | 2024-06-09 | [11 empty] | Completed | For NTP?Comtract
GSD-24-038 | 24CA-04D | Supply and Delivery of Interactive Flat Panel Display | Goods & Services | RGV | 2024-04-04 | 2024-04-23 | 9:52AM | 2024-06-06 | 44 | GSD | N | PB | 2024-04-30 | 2024-05-02 | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-29 | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-06-11 | 2024-06-11 | 2024-07-11 |  | COB | 2200000 |  | 2200000 | 1200684 |  | 1200684 | A.G. Datacom Phils.,Inc./American Technologies, Inc. | COA/MBC/ PCCI | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-28 | 2024-06-10 | [10 empty] | PO#298797/ 298798 | Completed | Completed/Delivered
OP-24-043 | Approved Budget Inclusion | Highly Technical Consultant for the Office of the President and Board of Directors for Public-Private Partnership | Consulting Services | CFCM | 2024-04-30 | 2024-04-30 | 10:30AM | 2024-05-02 | 2 | OP | N | NP-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-06 | 2024-06-19 | 2024-05-09 | 2024-11-15 |  | COB | 360000 | 360000 |  | 360000 | 360000 |  | Atty. Alberto C. Agra | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-007 | Completed | Contract for signing of Contractor
PIP-24-045 | 24MO-03A7A | Supply and Delivery of Mechanical Consumables for Booster Pumps | Goods & Services | RGV | 2024-02-20 | 2024-04-30 | 11:13AM | 2024-05-21 | 21 | PIP | N | NP-SVP | N/A | 2024-05-07 | N/A | N/A | N/A | 2024-05-17 | N/A | 2024-05-21 | N/A | 2024-05-24 | N/A | 30 days |  | COB | 146408 | 146408 |  | 66030 | 66030 |  | Pumpcraft Industrial Sales/Manara Marketing | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298792/298791 | Completed | Completed
GSD-24-057 | 24MO-07C1 | 2024 Messengerial Services | Goods & Services | RGV | 2024-05-30 | 2024-06-04 | 8:43AM | 2024-06-06 | 2 | GSD | N | NP-AA | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 |  | 2024-06-20 | 2024-12-31 |  | COB | 1250000 | 1250000 |  | 1250000 | 1250000 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Completed | For Abstract/NOA Signing
GSD-24-058 | 24MO-07C3 | 2024 Maintenance Services | Goods & Services | RGV | 2024-05-30 | 2024-06-04 | 8:43AM | 2024-06-06 | 2 | GSD | N | NP-AA | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 |  | 2024-06-20 | 2024-12-31 |  | COB | 2550000 | 2550000 |  | 2550000 | 2550000 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Completed | For Abstract/NOA Signing
[26 empty] | Total Alloted Budget of Procurement Activities | 46223145.98 | 37617145.98 | 8606000
[26 empty] | Total Contract Price Procurement Activities Conducted |  |  |  | 41128637.52 | 32644653.86 | 8483983.66
[26 empty] | Total Savings (Total Alloted Budget - Total Contract Price) | 5094508.46
ONGOING PROCUREMENT PROJECTS
ESB-24-040 | 24MO-08D1D | Preventive Maintenance of Truck Scale (Quarterly Check-up and Calibration with ITDI Certificate) | Goods & Services | GSM | 2024-01-31 | 2024-04-25 | 4:31PM |  | -45407 | ESB | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A | [8 empty] | COB | 83000 | 83000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing-Technical Evaluation
PIP-24-041 | 24MO-08D1S | Supply and Delivery of Consumables for Painting and Repair | Goods & Services | GSM | 2024-02-01 | 2024-05-20 | 11:30AM |  | -45432 | PIP | N | NP-SVP | N/A | [12 empty] | COB | 127727 | 127727 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 1st | 1st - No Bid Receive | 2024-06-13 | 2024-06-13 | 2024-06-14 |  |  |  | Awating for rebid
PIP-24-041 | 24MO-08D1S | Supply and Delivery of Consumables for Painting and Repair (Rebid) | Goods & Services | GSM |  | 2024-06-19 | 11:30AM |  | -45462 | PIP | N | NP-SVP | N/A | 2024-06-25 | N/A | N/A | N/A | [8 empty] | COB | 127727 | 127727 | [6 empty] | N/A | N/A | N/A | N/A | N/A
ESB-24-046 | Approved Budget Realignment | Supply and Delivery of Foam-Filled Rubber Fender | Goods & Services | RGV | 2024-02-14 | 2024-05-02 | 10:20AM |  | -45414 | ESB | N | PB | 2024-06-13 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-02 | [8 empty] | COB | 1616684 | 1616684 | [5 empty] | COA/MBC/ PCCI | 2024-06-18 | 2024-07-02 | 2024-07-02 | 2024-07-09 | 2024-07-21 | [12 empty] | Ongoing
SMO-24-059 | 24MO-03A8A3 | Supply and Delivery of Token/Giveaways (Electronic Gift Set) | Goods & Services | GSM |  | 2024-06-03 | 1:28PM |  | -45446 | SMO | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 165000 | 165000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1ST- NO BID RECEIVE | 2024-06-13 | 2024-06-13 | 2024-06-14 |  |  |  | For Opening of Bids
GSD-24-060 | Awaiting Approved Budget Realignment | Contract Services for the Preventive Maintenance of 2 units Passenger elevator at PNOC Bldg.6 | Goods & Services | GSM | 2024-05-20 | 2024-06-24 | 9:44AM |  | -45467 | GSD | N | NP-SVP | N/A | N/A | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 102161.63 | 102161.63 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing
GSD-24-061 | 24MO-08C1P | Fire Protection Services for PNOC Bldgs. 5&6 | Goods & Services | GSM |  | 2024-06-04 | 9:44AM |  | -45447 | GSD | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 154999.98 | 154999.98 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
GSD-24-062 | 24MO-08C1D | Preventive Maintenance of Centralized AC Units at PNOC Bldg. 5&6 | Goods & Services | GSM | 2024-05-20 | 2024-06-04 | 9:44AM |  | -45447 | GSD | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 531990 | 531990 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st-File Cannot be Open | 2024-06-25 | 2024-06-26 | 2024-06-26 |  |  | Failed Bidding | Awaiting Reply from Proponent
SMO-24-063 | 24MO-09D10 | Procurement of AutoCAD Software (1yr. Subscription for PNOC-HO) | Goods & Services | GSM | 2024-06-03 | 2024-06-06 | 8:50AM |  | -45449 | SMO | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 120000 | 120000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
PSD-24-064 | 24MO-03A8A2 | Supply and Delivery of Birthday Token (Smart Watch) | Goods & Services | GSM | 2024-05-16 | 2024-06-06 | 4:26PM |  | -45449 | PSD | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 290000 | 290000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st - Non-Submission | 2024-06-25 | 2024-06-26 | 2024-06-26 |  |  | Failed Bidding | Awaiting Reply from Proponent
AMD-24-066 | 24MO-07B | 2024 Security Services (Provincial Posts) (July 01-December 31, 2024) | Goods & Services | RGV | 2024-05-09 | 2024-06-07 | 1:59PM |  | -45450 | AMD | N | PB | 2024-06-13 | 2024-06-18 | 2024-06-25 | 2024-07-09 | 2024-07-09 | [8 empty] | COB | 3215634 | 3215634 | [5 empty] | COA/MBC/ PCCI | 2024-06-25 | 2024-06-09 | 2024-06-09 | 2024-07-16 | 2024-07-29
ESB-24-067 | 24MO-06A5 | Engagement of Environmental Services to Conduct Quarterly Ambient Air Quality , Semi-Annual Raw Water Testing and Ambient Ambient Water Quality Monitoring at ESB | Goods & Services | RGV | 2024-05-06 | 2024-06-07 | 2:48PM |  | -45450 | ESB | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 250000 | 250000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
SMO-24-068 | 24MO-03A5P/03A5Q/03A5N/03A5O | Supply and Delivery of Various IT Equipments Supplies | Goods & Services | GSM | 2024-06-04 | 2024-06-07 | 3:51PM |  | -45450 | SMO | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 292700 | 292700 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
OC-24-069 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token for Office of the Chairman | Goods & Services | GSM |  | 2024-06-07 | 4:00PM |  | -45450 | OC | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 207580.24 | 207580.24 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
SMO-24-070 | 24MO-09C1 | Supply, Delivery and Installation of Rental units of Multi-Functional Printers for PNOC Offices | Goods & Services | RMB |  | 2024-06-10 | 1:09PM |  | -45453 | SMO | N | NP-SVP |  |  | N/A | N/A | N/A | [8 empty] | COB | 800000 | 800000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
PIP-24-071 | 24MO-08D10 | Genset Servicing | Goods & Services | RGV | 2024-05-11 | 2024-06-11 | 11:10AM |  | -45454 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 100000 | 100000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
ESB-24-072 | 24MO-08A1-A2/ 24MO-08C1C-IK/ 24MO-08D1D/24MO-08D1G | Supply and Delivery of Materials for 2024 ESB Annual Maintenance Plan | Goods & Services | GSM | 2024-04-25 | 2024-06-13 | 8:34AM |  | -45456 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 610199.75 | 610199.75 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
GSD-24-073 | 24CA-038 | Replacement of Airconditioning System - Ground Floor to 3rd Floor of PNOC Building 5 | Goods & Services | CFCM | 2024-05-16 | 2024-06-18 | 10:30AM |  | -45461 | GSD | N | PB | 2024-06-20 | 2024-06-25 | 2024-07-02 | 2024-07-06 | 2024-07-06 | [8 empty] | COB | 19760000 |  | 19760000 |  |  |  |  | COA/MBC/ PCCI | 2024-07-27 | 2024-07-16 | 2024-07-16 | 2024-07-13 | 2024-08-04
PRM-24-075 | 24MO-03A1 | Supply and Delivery of Computer Supplies | Goods & Services | GSM | 2024-06-05 | 2024-06-18 | 8:18PM |  | -45461 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 302175.97 | 302175.97 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
PRM-24-076 | 24MO-03A1 | Supply and Delivery of Commonly-use Supplies | Goods & Services | GSM | 2024-06-10 | 2024-06-24 | 10:50AM |  | -45467 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 335746.13 | 335746.13 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
PRM-24-077 | 24MO-08F1 | Refurbishing and Revarnishing of Furniture | Goods & Services | GSM | 2024-06-10 | 2024-06-25 | 1:49PM |  | -45468 | PRM | N | NP-SVP | N/A | [5 empty] | N/A | [6 empty] | COB | 106837 | 106837 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
PIP-24-078 | 24MO-07B | 2024 Security Services for PNOC IP | Goods & Services | RGV | 2024-01-17 | 2024-06-25 | 4:20PM |  | -45468 | PIP | N | PB | 2024-06-28 | [12 empty] | COB | 9960827.5 | 9960827.5 | [5 empty] | COA/MBC/ PCCI | [17 empty] | For July Posting
ESB-24-079 | 24MO-07B | 2025 Security Services for PNOC ESB | Goods & Services | RGV | 2024-01-17 | 2024-06-25 | 4:20PM |  | -45468 | ESB | N | PB | 2024-06-28 | [12 empty] | COB | 4862580 | 4862580 | [5 empty] | COA/MBC/ PCCI | [17 empty] | For July Posting
AD-24-080 | 24MO-03A2 | Printing of Cash and Charge Invoices | Goods & Services | GSM | 2024-06-24 | 2024-06-27 | 1:31PM |  | -45470 | AD | N | NP-AA | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  |  |  |  | COB | 240000 | 240000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | Superceded by AD-24-055 |  |  |  |  | For July Posting
PIP-24-048 | 24MO-07A | Supply of Manpower, equipment and Supplies for Janitorial Services at PIP from June 1 to December 2024 | Goods & Services | RGV | 2024-05-05 | 2024-06-27 | 2:10PM |  | -45470 | PIP | N | PB | 2024-06-28 | [12 empty] | COB | 2784590.02 | 2784590.02 | [5 empty] | COA/MBC/ PCCI
PIP-24-049 | 24MO-07C3 | Provision of Manpower for 2024 Custodial Services/Other General Services at PNOC IP (June 1 to December 31 2024 | Goods & Services | RGV | 2024-05-05 | 2024-05-15 | 1:33PM |  | -45427 | PIP | N | PB | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-25 | 2024-06-25 | [8 empty] | COB | 2801245.35 | 2801245.35 | [5 empty] | COA/MBC/ PCCI
SMO-24-050 | 24MO-09D5 | Supply and Delivery of Adobe Acrobat Pro for Teams (1-year subsciption) | Goods & Services | GSM | 2024-04-17 | 2024-05-10 | 1:17PM |  | -45422 | SMO | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A |  | N/A |  | N/A |  |  |  |  | COB | 219377.21 | 219377.21 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing- For Award
PRM-24-051 | 24MO-09D12 | Asset Inventory Management System | Goods & Services | CFCM | 2024-04-16 | 2024-05-20 | 2:52PM |  | -45432 | PRM | N | PB | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-25 | 2024-06-25 | [8 empty] | COB | 4000000 | 4000000 | [5 empty] | COA/MBC/ PCCI | 2024-06-11 | 2024-06-25 | 2024-06-25 | 2024-07-02 | 2024-07-14
BDD-24-052 | Approved Budget Inclusion | Supply and Delivery of Various Measuring Devices and Accessories | Goods & Services | CFCM | 2024-05-15 | 2024-05-23 | 3:56PM |  | -45435 | BRDD | N | PB | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-25 | 2024-06-25 | [8 empty] | COB | 1011000 | 1011000 | [5 empty] | COA/MBC/ PCCI | 2024-06-11 | 2024-06-25 | 2024-06-25 | 2024-07-02 | 2024-07-14
AMD-24-053 | 24MO-07A | 2024 Caretaker Services - PNOC Staffhouse,Lamao, Limay, Bataan | Goods & Services | GSM | 2024-05-15 | 2024-05-23 | 3:56PM |  | -45435 | AMD | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A | 2024-06-20 | N/A |  | N/A |  |  |  |  | COB | 175754.31 | 175754.31 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing- For Award
PRM-24-054 | 24MO-06B8 | Appraisal for PNOC,PAFC,PSTC and PDMC's Unserviceable Properties | Goods & Services | GSM | 2024-05-22 | 2024-05-31 | 8:13AM |  | -45443 | PRM | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A | 2024-06-24 | N/A |  | N/A |  |  |  |  | COB | 175000 | 175000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing- For Award
GSD-24-056 | 24MO-07A | 2024 Janitorial Services | Goods & Services | RGV | 2024-05-30 | 2024-06-04 | 8:43AM | 2024-06-06 | 2 | GSD | N | NP-AA | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 |  |  | July-December |  | COB | 7900000 | 7900000 |  | 7900000 | 7900000 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For Abstract/NOA Signing
| 24CA-04A5 | Procurement of Computerized Accounting System | Goods & Services | CFCM | 2024-04-29 | 2024-04-30 | 10:51AM |  | -45412 | AD | N | PB | 2024-05-28 | 2024-05-30 | 2024-06-06 | 2024-06-18 | 2024-06-18 | [8 empty] | COB | 4070000 | 4070000 | [5 empty] | PCCI/MBC/COA | 2024-06-06 | 2024-06-18 | 2024-06-18 | 2024-06-25 | 2024-07-07 | [5 empty] | 1st-No bid Receive | 2024-06-18 | 2024-06-18 | 2024-06-19 |  |  | Failed Bidding
| Approved Budget Inclusion | Consultancy Services for Comprehensive Reorganization | Consulting Services | RGV | 2024-06-11 | 2024-06-18 | 2:21PM |  | -45461 | PSD | N | PB | [13 empty] | COB | 2000000 | 2000000
FAILED
PRM-24-018 | 24MO-03A2 | Supply and Delivery of Consolidated Office Forms for CY2024 | Goods & Services | GSM | 2024-02-29 | 2024-03-07 | 10:50AM |  | -45358 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 401287.7 | 401287.7 | [5 empty] | N/A | N/A | N/A | N/A | N/A
ESB-24-047 |  | 2024 Custodial and Janitorial Services for PNOC ESB | Goods & Services | CFCM | 2024-04-26 | 2024-05-06 | 11:40AM |  | -45418 | ESB | N | PB | [13 empty] | COB | 4283000 | 4283000 | [5 empty] | COA/MBC/ PCCI | [17 empty] | Awating for TOR
SMO-24-065 | 24MO-09E12 | Venue Rental and Catering for Partner's Night | Goods & Services | CFCM | 2024-06-04 | 2024-06-06 | 3:21PM |  | -45449 | SMO | N | PB | [13 empty] | COB | 1200000 | 1200000 | [5 empty] | COA/MBC/ PCCI | [17 empty] | Returned to SMO 6/18/24
CANCELLED
PMD-24-010 | 24MO-08D1A | Repair of Printer - Epson L210 | Goods & Services | GSM | 2024-02-08 | 2024-02-13 | 1:30PM |  | -45335 | PMD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 2500 | [15 empty] | N/A | No bid | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
OP-24-008 | 24MO-08E1D | Repair of Expander NGS-5802 | Goods & Services | RGV | 2024-01-30 | 2024-02-08 | 9:00AM |  | -45330 | OP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 10000 | [22 empty] | Cancelled by proponent
PIP-24-011 | 24MO-09E10 | Supply and Delivery of Materials for 2024 Parkwide Coastal Clean Up | Goods & Services | GSM | 2024-01-29 | 2024-02-13 | 10:30AM |  | -45335 | PIP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 12000 | [16 empty] | Non Compliance | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
SMO-24-022 | 24MO-09C1 | Supply, Delivery and Installation of Rental units of Multi-Functional Printers for PNOC Offices | Goods & Services | CFCM |  | 2024-04-29 | 10:03AM |  | -45411 | SMO | N | PB | 2024-04-30 |  | 2024-05-09 | [7 empty] | N/A |  | COB | COB | 500000 | 500000 | [16 empty] | 1st-non submission | [6 empty] | Cancelled/ Change of Mode of Procurement
[26 empty] | Total Alloted Budget of On-going Procurement Activities | 69500537.09 | 43670537.09 | 19760000
Recommended for Approval:
|  | Prepared by: | [7 empty] | Bids and Awards Committee: | [9 empty] | Approved by:
|  | R. M. Babera | [7 empty] | A. E. Suyom J. R. Racho A. G. Buenviaje J. C. J. Cui | [9 empty] | OLIVER B. BUTALID
President and CEO
Formulas:
Date of BAC Reso Reco Award = [Date PR Awarded]
Sub/Open of Bids = [Eligibility Check]

## PMR 2024
PHILIPPINE NATIONAL OIL COMPANY
2024 FIRST SEMESTER PROCUREMENT MONITORING REPORT
PR NO. | Code (PAP) *from APP | Procurement Program/Project | Classification *Goods and Services, Infrastructure or Cosnulting Services | Account Officer *Initials | Date of PR | Date PR Received | Time Received | Date PR Awarded | TAT (days) | PMO/ End-User | Is this an Early Procurement Activity? Y/N | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Winning Bidder | List of Invited Observers | Date of Receipt of Invitation | [7 empty] | Submitted to COA |  | Reason of Failure |  |  |  |  | Payment Oder No./Contract No. | STATUS / REMARKS *Ongoing / Completed | STATUS as of today
[13 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf / Negotiation | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Reso Reco Award | Notice of Award | Contract Signing/ PO | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/Acceptance (if applicable) | Submission to IAO | Submission to OGC |  | Rebid |  | Date of Failure of Bidding | Date of Memo to Proponent (Failure of Bid) | Date Received Memo by Proponent | Date of Submitted CSS Form
COMPLETED PROCUREMENT ACTIVITIES
SMO-24-001 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Energy Supply Base | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | February-December |  | COB | 608000 | 608000 |  | 555397.33 |  | 555397.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [10 empty] | Contract#24-001 | Completed | Transmitted to End-User 2/20/24
SMO-24-002 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Industrial Park | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | February-December |  | COB | 735000 | 735000 |  | 673647.33 |  | 673647.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [10 empty] | Contract#24-001 | Completed | Transmitted to End-User 2/20/24
SMO-24-003 | 24MO-04A3 | PNOC Network Rehabilitation and Reconfiguration Project | Goods & Services | CFCM |  | 2024-01-15 | 2:53PM | 2024-03-14 | 59 | SMO | N | PB | 2024-01-23 | 2024-01-25 | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 2024-02-29 | 2024-03-14 | 2024-03-14 | 2024-04-29 | 2024-04-05 | 90 days |  | COB | 4900000 | 4900000 |  | 4792565 |  | 4792565 | Pronet Systems Integrated Network Solution, Inc. | MBC, COA, PCCI | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-16 | 2024-02-22 | [10 empty] | Contract#24-002 | Awarded | Received Signed 3.15.24
SMO-24-004 | 24MO-04A2 | Supply and Delivery of Laptop Computers | Goods & Services | CFCM | 2023-12-18 | 2024-01-15 | 2:53PM | 2024-04-01 | 77 | SMO | N | NP-SVP | N/A | 2024-02-01 | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-28 | 2024-04-01 | 2024-04-01 | N/A | 2024-04-04 | N/A | 90 days |  | COB | 706000 |  | 706000 | 626690 |  | 626690 | Joneco Tech Marketing Corporation | MBC, COA, PCCI | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-29 | 2024-03-12 | [10 empty] | PO#298785 | Awarded | rEceived Signed PO 4.15.24
GSD-24-005 | 24MO-07B | 2024 Security Services for PNOC Head Office | Goods & Services | RGV | 2024-01-09 | 2024-01-25 | 11:00AM | 2024-04-16 | 82 | GSD | N | PB | 2024-01-31 | 2024-02-06 | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-26 | 2024-04-12 | 2024-04-16 | 2024-04-16 | 2024-05-08 | 2024-04-26 | May-December |  | COB | 10400000 | 10400000 |  | 10333557.5 | 10333557.5 |  | Eliteblue Security Specialist, Inc. | MBC, COA, PCCI | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-08 | 2024-03-16 | [10 empty] | Contract#24-003 | Awarded | Completed/Delivered
SMO-24-006 | 24MO-06A1 | Consulting Services for the Digital Transformation Initiative of PNOC | Consulting Services | CFCM | 2024-01-22 | 2024-01-26 | 8:30AM | 2024-01-31 | 5 | SMO | N | AA | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-02 | 2024-03-11 | 2024-03-01 |  |  | COB | 4950000 | 4950000 |  | 4912969.56 | 4912969.56 |  | University of the Philippines | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded
PIP-24-007 | 24MO-08D1U | 2024 Preventive Maintenance of PNOC Gym Equipment | Goods & Services | GSM | 2024-01-31 | 2024-02-20 | 11:09AM | 2024-03-14 | 23 | PRM | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-13 | N/A | 2024-03-14 | N/A | 2024-03-18 | N/A | Jan-Dec | COB | COB | 48000 | 48000 |  | 48000 | 48000 |  | The FitCo, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298783 | Awarded | Completed/Delivered
GSD-24-009 | 24MO-03A9AN | Purchase of Materials for Fabrication of of Bed Frame | Goods & Services | GSM | 2024-01-25 | 2024-02-08 | 1:35PM | 2024-03-19 | 40 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4665 | 4665 |  | 3120 | 3120 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Completed/Delivered
GSD-24-012 | 24MO-03A9AN | Carpentry Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 7145 | 7145 |  | 4940 | 4940 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Completed/Delivered
GSD-24-013 | 24MO-03A9AN | Plumbing Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 12196 | 12196 |  | 9650 | 9650 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Completed/Delivered
GSD-24-014 | 24MO-03A9AN | Electrical Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4133.75 | 4133.75 |  | 3231 | 3231 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Completed/Delivered
GSD-24-015 | 24MO-08D1W | Aircon Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 34490.57 | 34490.57 |  | 33892 | 33892 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Completed/Delivered
SMO-24-016 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token | Goods & Services | GSM |  | 2024-03-01 | 4:15PM | 2024-04-25 | 55 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-22 | N/A | 2024-04-25 | N/A | 2024-04-25 | N/A | 30 days |  | COB | 275000 | 275000 |  | 215520 | 215520 |  | Jen Lin Corporate Giveaways | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298787 | Awarded | Completed/Delivered
PSD-24-017 | 24MO-038AC | Supply and Delivery of Fluquadri (Adult) | Goods & Services | RGV | 2024-02-19 | 2024-03-06 | 4:15PM | 2024-04-18 | 43 | PSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-16 | N/A | 2024-04-18 | N/A | 2024-04-23 | N/A | 15 days |  | COB | 85000 | 85000 |  | 61456 | 61456 |  | Pharma Quest Co. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298786 | Awarded | Completed
PRM-24-020 | 24MO-03A1 | Supply and Delivery of Consolidated Commonly-Use Supplies for January-February 2024 | Goods & Services | GSM | 2024-03-20 | 2024-03-11 | 2:30PM | 2024-05-16 | 66 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | 2024-05-29 | N/A | 30 days |  | COB | 333058.99 | 333058.99 |  | 240263.15 | 240263.15 |  | Varyline & Lambert Trading | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298795/ 298796 | Awarded | Completed/Delivered
PIP-24-021 | 24MO-07C5D | Hauling, Transport, Treatment and Disposal of Generated Hazardous wastes of PIP | Goods & Services | RGV | 2024-01-23 | 2024-03-14 | 9:16AM | 2024-05-28 | 75 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-05-24 | N/A | 2024-05-28 | 2024-06-04 | 2024-06-24 | 2024-07-01 | 30 days |  | COB | 137917 | 137917 |  | 104500 | 104500 |  | Clean Leaf Intrenational Corp. | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | NOA/for Contract Draft
PIP-24-023 | 24MO-06B6 | 2024 Environmental Monitoring (Waste Water-Effluent and Marine, Raw Water, Ambient Air Sampling and Laboratory Analysis) | Goods & Services | RGv | 2023-09-06 | 2024-03-22 | 10:09AM | 2024-05-27 | 66 | PIP | N | PB | N/A | 2024-04-04 | 2024-04-11 | 2024-04-25 | 2024-04-25 | 2024-05-03 | 2024-05-27 | 2024-05-28 | 2024-05-30 | 2024-06-21 | 2024-06-13 | 2nd-4th QTR |  | COB | 825000 | 825000 |  | 688140 | 688140 |  | CRL Environmental Corporation | COA/MBC/PCCI | 2024-04-11 | 2024-04-25 | 2024-04-25 | 2024-05-03 | [11 empty] | Contract#24-009 | Awarded
SMO-24-024 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token(Bamboo Stainless Cup) | Goods & Services | CFCM |  | 2024-03-25 | 1:58PM | 2024-04-25 | 31 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-23 | N/A | 2024-04-25 | N/A | 2024-04-30 | N/A | 30 days | COB | COB | 90000 | 90000 |  | 40000 | 40000 |  | CSG Manufacturing Corporation | N/A | 2024-04-26 | 2024-04-03 | 2024-05-16 | 2024-05-16 | 2024-05-16 | [10 empty] | PO#298788 | Awarded | Completed/Delivered
PIP-24-025 | 24MO-03A7C/08D1L | Supply and Delivery of Electrical Items(Batteries for Genset and Fire Engine) | Goods & Services | GSM | 2024-01-15 | 2024-03-25 | 2:37PM | 2024-04-25 | 31 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-25 | N/A | 2024-04-25 | N/A | 2024-05-07 | N/A | 30 days |  | COB | 195600 | 195600 |  | 153614 | 153614 |  | 8 Days A Week Consumer Goods Trading | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298789 | Awarded | Completed/Delivered
GSD-24-026 | 24MO-04A3 | 2024 Supply and Delivery of Drinking Water | Goods & Services | GSM | 2024-03-12 | 2024-04-04 | 9:03AM | 2024-04-23 | 19 | GSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-19 | N/A | 2024-04-23 | 2024-04-29 | 2024-06-21 | 2024-04-30 | May-December |  | COB | 212000 | 212000 |  | 176320 | 176320 |  | MSDR Water Refilling Station | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-013 | Awarded | Contract for Signing of EAL
SMO-24-027 | 24MO-09D15 | Supply and Delivery of Barcode Scanner | Goods & Services | GSM | 2024-04-04 | 2024-04-05 | 11:50AM | 2024-04-30 | 25 | SMO | N | NP-SVP | N/A | 2024-04-12 | N/A | N/A | N/A | 2024-04-25 | N/A | 2024-04-30 | N/A | 2024-05-08 | N/A | 30 days |  | COB | 211000 | 211000 |  | 56440 | 56440 |  | A.G. Datacom Phis.,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298790 | Awarded | Completed/Delivered
PSD-24-028 | 24MO-07C2 | 2024 Temporary Office Services | Goods & Services | RGV |  | 2024-04-11 | 8:30AM | 2024-04-11 | 0 | PSD | N | NP-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-05-30 | 2024-04-26 | May-December |  | COB | 9500000 | 9500000 |  | 7464399.68 | 7464399.68 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-004 | Awarded | Completed/Delivered
SMO-24-029 | 24MO-09D6 | Supply and Delivery of Cloud-based Email, Productivity, and Collaboration Service Subscription / Email Hosting Service Subscription | Goods & Services | RGV |  | 2024-04-17 | 2:30PM | 2024-05-30 | 43 | SMO | N | PB | 2024-04-25 | 2024-04-26 | 2024-04-03 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-23 | 2024-05-30 | 2024-05-30 | 2024-07-01 | 2024-06-25 | 30 days |  | COB | 1800000 | 1800000 |  | 1383810.97 | 1383810.97 |  | ePLDT,Inc. | COA/MBC/PCCI | 2024-04-04 | 2024-04-11 | 2024-04-25 | 2024-04-25 | 2024-05-03 | [11 empty] | Awarded | NTP/Contract for Sign of OP
PSD-24-030 | 24CA-04A6 | Supply, Delivery, Installation and Implementation of Time and Attendance Monitoring System w/ 3 Biometric devices (facial recognition/finger scan) | Goods & Services | RGV | 2024-03-25 | 2024-04-19 | 1:08PM | 2024-05-14 | 25 | PSD | N | NP-SVP | N/A | 2024-05-09 | N/A | N/A | N/A | 2024-05-14 | N/A | 2024-05-14 | 2024-05-14 | 2024-06-11 | 2024-06-23 | 15 days |  | COB | 800000 |  | 800000 | 635000 |  | 635000 | 3GX Computer and IT Solutions Techshop | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-006 | Awarded | Completed/Delivered
GSD-24-031 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at G/Fr. Zone #1 Compressor#1 of PNOC Bldg.5 | Goods & Services | GSM | 2024-02-29 | 2024-04-18 | 11:17AM | 2024-04-30 | 12 | GSD | N | NP-SVP | N/A | 2024-04-24 | N/A | N/A | N/A | 2024-04-29 | N/A | 2024-04-30 | 2024-04-30 | 2024-07-01 | 2024-05-02 | 30 days |  | COB | 161760 | 161760 |  | 140000 | 140000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #24-011 | Awarded | Contract for Sign of OP 6.24.24
GSD-24-032 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at 2nd/Flr. Zone #1 Compressor#2 of PNOC Bldg.5 | Goods & Services | GSM | 2024-01-25 | 2024-04-23 | 11:35AM | 2024-04-30 | 7 | GSD | N | NP-SVP | N/A | 2024-04-24 | N/A | N/A | N/A | 2024-04-29 | N/A | 2024-04-30 | 2024-04-30 | 2024-07-01 | 2024-05-02 | 30 days |  | COB | 162720 | 162720 |  | 135000 | 135000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #24-011 | Awarded | Contract for Sign of OP 6.24.24
GSD-24-033 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at 3rd/Flr. Zone #2 of PNOC Bldg.5 | Goods & Services | GSM | 2024-04-17 | 2024-04-23 | 9:20AM | 2024-04-30 | 7 | GSD | N | NP-SVP | N/A | 2024-04-24 | N/A | N/A | N/A | 2024-04-29 | N/A | 2024-04-30 | 2024-04-30 | 2024-07-01 | 2024-05-02 | 30 days |  | COB | 161760 | 161760 |  | 138000 | 138000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #24-011 | Awarded | Contract for Sign of OP 6.24.24
CS-24-034 | Memo Realignment | Corporate Retreat and Planning of Board of Directors | Goods & Services | CFCM | 2024-04-22 | 2024-04-24 | 2:43PM | 2024-05-10 | 16 | CORSEC | N | NP-SVP | N/A | 2024-05-04 | N/A | N/A | N/A | 2024-05-08 | N/A | 2024-05-10 | 2024-05-09 | 2024-06-10 | 2024-05-13 | 3 days |  | COB | 400000 | 400000 |  | 398000 | 398000 |  | Marivent Resort Hotel, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-005 | Awarded | Contract for Signing of Contractor
GSD-24-035 | 24MO-08C2C | 2024 Pest Control Services for PNOC Building at Fort Bonifacio and PNOC Property in Tagaytay | Goods & Services | GSM | 2024-03-11 | 2024-04-05 | 9:41AM | 2024-05-16 | 41 | GSD | N | NP-SVP | N/A | 2024-05-07 | N/A | N/A | N/A | 2024-05-14 | N/A | 2024-05-16 | N/A | 2024-05-27 | N/A | May-Dec |  | COB | 81000 | 81000 |  | 68200 | 68200 |  | Ram Pest Control Services | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298793 | Awarded | Completed/Delivered
PIP-24-036 | 24MO-08D1Q | Supply and Delivery of Lighting Panel Board | Goods & Services | GSM | 2024-01-31 | 2024-04-18 | 9:45AM | 2024-05-21 | 33 | PIP | N | NP-SVP | N/A | 2024-05-07 | N/A | N/A | N/A | 2024-05-17 | N/A | 2024-05-21 | N/A | 2024-05-28 | N/A | 30 days |  | COB | 120000 | 120000 |  | 110000 | 110000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298794 | Awarded | Completed/Delivered
GSD-24-037 | 24MO-08D1X | Reconditioning /Rehabilitation of 900kW Caterpillar Genset Alternator at PNOC Bldg.5 | Goods & Services | CFCM | 2024-03-12 | 2024-04-19 | 2:33PM | 2024-06-06 | 48 | GSD | N | PB | 2024-04-30 | 2024-05-02 | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-29 | 2024-06-06 | 2024-06-06 | 2024-06-06 |  | 2024-06-21 | 30 days |  | COB | 1755291.67 | 1755291.67 |  | 1495600 | 1495600 |  | Tabuko Energy Network Corp. | COA/MBC/ PCCI | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-28 | 2024-06-09 | [11 empty] | Awarded | For NTP?Comtract
GSD-24-038 | 24CA-04D | Supply and Delivery of Interactive Flat Panel Display | Goods & Services | RGV | 2024-04-04 | 2024-04-23 | 9:52AM | 2024-06-06 | 44 | GSD | N | PB | 2024-04-30 | 2024-05-02 | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-29 | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-06-11 | 2024-06-11 | 30 days |  | COB | 2200000 |  | 2200000 | 1200684 |  | 1200684 | A.G. Datacom Phils.,Inc./American Technologies, Inc. | COA/MBC/ PCCI | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-28 | 2024-06-10 | [10 empty] | PO#298797/ 298798 | Awarded | Completed/Delivered
OP-24-043 | Approved Budget Inclusion | Highly Technical Consultant for the Office of the President and Board of Directors for Public-Private Partnership | Consulting Services | CFCM | 2024-04-30 | 2024-04-30 | 10:30AM | 2024-05-02 | 2 | OP | N | NP-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-06 | 2024-06-19 | 2024-05-09 | May-November |  | COB | 300000 | 300000 |  | 360000 | 360000 |  | Atty. Alberto C. Agra | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-007 | Awarded | Contract for signing of Contractor
PIP-24-045 | 24MO-03A74 | Supply and Delivery of Mechanical Consumables for Booster Pumps | Goods & Services | RGV | 2024-02-20 | 2024-04-30 | 11:13AM | 2024-05-21 | 21 | PIP | N | NP-SVP | N/A | 2024-05-07 | N/A | N/A | N/A | 2024-05-17 | N/A | 2024-05-21 | N/A | 2024-05-24 | N/A | 30 days |  | COB | 146408 | 146408 |  | 66030 | 66030 |  | Pumpcraft Industrial Sales/Manara Marketing | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298792/298791 | Awarded | Completed
GSD-24-057 | 24MO-07C1 | 2024 Messengerial Services | Goods & Services | RGV | 2024-05-30 | 2024-06-04 | 8:43AM | 2024-06-06 | 2 | GSD | N | NP-AA | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 |  | 2024-06-20 | July-December |  | COB | 1250000 | 1250000 |  | 1250000 | 1250000 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | For Abstract/NOA Signing
GSD-24-058 | 24MO-07C3 | 2024 Maintenance Services | Goods & Services | RGV | 2024-05-30 | 2024-06-04 | 8:43AM | 2024-06-06 | 2 | GSD | N | NP-AA | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 |  | 2024-06-20 | July-December |  | COB | 2550000 | 2550000 |  | 2550000 | 2550000 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | For Abstract/NOA Signing
[26 empty] | Total Alloted Budget of Procurement Activities | 46163145.98 | 42457145.98 | 3706000
[26 empty] | Total Contract Price Procurement Activities Conducted |  |  |  | 41128637.52 | 32644653.86 | 8483983.66
[26 empty] | Total Savings (Total Alloted Budget - Total Contract Price) | 5034508.46
ONGOING PRCUREMENT PROJECTS
PRM-24-019 | 24MO-03A1 | Supply and Delivery of Consolidated Computer Supplies for January-February 2024 | Goods & Services | GSM | 2024-02-12 | 2024-03-07 | 10:58AM |  | -45358 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A | 30 days |  | COB | 734811.81 | 734811.81 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
PRM-24-039 | 2MO-03A1 | Supply and Delivery of Consolidated Computer Supplies for March-April 2024 | Goods & Services | GSM | 2024-04-22 | 2024-04-26 | 1:15PM |  | -45408 | PRM | N | NP-SVP | N/A | [12 empty] | COB | 192335.62 | 192335.62 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Pending
ESB-24-040 | 24MO-08D1D | Preventive Maintenance of Truck Scale (Quarterly Check-up and Calibration with ITDI Certificate) | Goods & Services | GSM | 2024-01-31 | 2024-04-25 | 4:31PM |  | -45407 | ESB | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A | [8 empty] | COB | 83000 | 83000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing-Technical Evaluation
PIP-24-041 | 24MO-08D1S | Supply and Delivery of Consumables for Painting and Repair | Goods & Services | GSM | 2024-02-01 | 2024-05-20 | 11:30AM |  | -45432 | PIP | N | NP-SVP | N/A | [12 empty] | COB | 127727 | 127727 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 1st | 1st - No Bid Receive | 2024-06-13 | 2024-06-13 | 2024-06-14 |  |  |  | Awating for rebid
PIP-24-041 | 24MO-08D1S | Supply and Delivery of Consumables for Painting and Repair (Rebid) | Goods & Services | GSM |  | 2024-06-19 | 11:30AM |  | -45462 | PIP | N | NP-SVP | N/A | 2024-06-25 | N/A | N/A | N/A | [8 empty] | COB | 127727 | 127727 | [6 empty] | N/A | N/A | N/A | N/A | N/A
PRM-24-042 | 24MO-03A1 | Supply and Delivery of Consolidated Commonly Use Supplies for March-April 2024 | Goods & Services | GSM | 2024-04-25 | 2024-04-29 | 9:07AM |  | -45411 | PRM | N | NP-SVP | N/A | [12 empty] | COB | 153774.18 | 153774.18 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
ESB-24-046 | Approved Budget Realignment | Supply and Delivery of Foam-Filled Rubber Fender | Goods & Services | RGV | 2024-02-14 | 2024-05-02 | 10:20AM |  | -45414 | ESB | N | PB | 2024-06-13 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-02 | [8 empty] | COB | 1616684 | 1616684 | [5 empty] | COA/MBC/ PCCI | 2024-06-18 | 2024-07-02 | 2024-07-02 | 2024-07-09 | 2024-07-21 | [12 empty] | Ongoing
SMO-24-059 | 24MO-03A8A3 | Supply and Delivery of Token/Giveaways (Electronic Gift Set) | Goods & Services | GSM |  | 2024-06-03 | 1:28PM |  | -45446 | SMO | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 165000 | 165000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1ST- NO BID RECEIVE | 2024-06-13 | 2024-06-13 | 2024-06-14 |  |  |  | For Opening of Bids
GSD-24-060 | Awaiting Approved Budget Realignment | Contract Services for the Preventive Maintenance of 2 units Passenger elevator at PNOC Bldg.6 | Goods & Services | GSM | 2024-05-20 | 2024-06-24 | 9:44AM |  | -45467 | GSD | N | NP-SVP | N/A | N/A | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 102161.63 | 102161.63 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing
GSD-24-061 | 24MO-08C1P | Fire Protection Services for PNOC Bldgs. 5&6 | Goods & Services | GSM |  | 2024-06-04 | 9:44AM |  | -45447 | GSD | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 154999.98 | 154999.98 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
GSD-24-062 | 24MO-08C1D | Preventive Maintenance of Centralized AC Units at PNOC Bldg. 5&6 | Goods & Services | GSM | 2024-05-20 | 2024-06-04 | 9:44AM |  | -45447 | GSD | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 531990 | 531990 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st-File Cannot be Open | 2024-06-25 | 2024-06-26 | 2024-06-26 |  |  | Failed | Awaiting Reply from Proponent
SMO-24-063 | 24MO-09D10 | Procurement of AutoCAD Software (1yr. Subscription for PNOC-HO) | Goods & Services | GSM | 2024-06-03 | 2024-06-06 | 8:50AM |  | -45449 | SMO | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 120000 | 120000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
PSD-24-064 | 24MO-03A8A2 | Supply and Delivery of Birthday Token (Smart Watch) | Goods & Services | GSM | 2024-05-16 | 2024-06-06 | 4:26PM |  | -45449 | PSD | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 290000 | 290000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st - Non-Submission | 2024-06-25 | 2024-06-26 | 2024-06-26 |  |  | Failed | Awaiting Reply from Proponent
AMD-24-066 | 24MO-07B | 2024 Security Services (Provincial Posts) (July 01-December 31, 2024) | Goods & Services | RGV | 2024-05-09 | 2024-06-07 | 1:59PM |  | -45450 | AMD | N | PB | 2024-06-13 | 2024-06-18 | 2024-06-25 | 2024-07-09 | 2024-07-09 | [8 empty] | COB | 3215634 | 3215634 | [5 empty] | COA/MBC/ PCCI | 2024-06-25 | 2024-06-09 | 2024-06-09 | 2024-07-16 | 2024-07-29
ESB-24-067 | 24MO-06A5 | Engagement of Environmental Services to Conduct Quarterly Ambient Air Quality , Semi-Annual Raw Water Testing and Ambient Ambient Water Quality Monitoring at ESB | Goods & Services | RGV | 2024-05-06 | 2024-06-07 | 2:48PM |  | -45450 | ESB | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 250000 | 250000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
SMO-24-068 | 24MO-03A5P/03A5Q/03A5N/03A5O | Supply and Delivery of Various IT Equipments Supplies | Goods & Services | GSM | 2024-06-04 | 2024-06-07 | 3:51PM |  | -45450 | SMO | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 292700 | 292700 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
OC-24-069 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token for Office of the Chairman | Goods & Services | GSM |  | 2024-06-07 | 4:00PM |  | -45450 | OC | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 207580.24 | 207580.24 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
SMO-24-070 | 24MO-09C1 | Supply, Delivery and Installation of Rental units of Multi-Functional Printers for PNOC Offices | Goods & Services | RMB |  | 2024-06-10 | 1:09PM |  | -45453 | SMO | N | NP-SVP |  |  | N/A | N/A | N/A | [8 empty] | COB | 800000 | 800000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
PIP-24-071 | 24MO-08D10 | Genset Servicing | Goods & Services | RGV | 2024-05-11 | 2024-06-11 | 11:10AM |  | -45454 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 100000 | 100000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
ESB-24-072 | 24MO-08A1-A2/ 24MO-08C1C-IK/ 24MO-08D1D/24MO-08D1G | Supply and Delivery of Materials for 2024 ESB Annual Maintenance Plan | Goods & Services | GSM | 2024-04-25 | 2024-06-13 | 8:34AM |  | -45456 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 610199.75 | 610199.75 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
GSD-24-073 | 24CA-038 | Replacement of Airconditioning System - Ground Floor to 3rd Floor of PNOC Building 5 | Goods & Services | CFCM | 2024-05-16 | 2024-06-18 | 10:30AM |  | -45461 | GSD | N | PB | 2024-06-20 | 2024-06-25 | 2024-07-02 | 2024-07-06 | 2024-07-06 | [8 empty] | COB | 19760000 |  | 19760000 |  |  |  |  | COA/MBC/ PCCI | 2024-07-27 | 2024-07-16 | 2024-07-16 | 2024-07-13 | 2024-08-04
PRM-24-075 | 24MO-03A1 | Supply and Delivery of Computer Supplies | Goods & Services | GSM | 2024-06-05 | 2024-06-18 | 8:18PM |  | -45461 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 302175.97 | 302175.97 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
PRM-24-076 | 24MO-03A1 | Supply and Delivery of Commonly-use Supplies | Goods & Services | GSM | 2024-06-10 | 2024-06-24 | 10:50AM |  | -45467 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 335746.13 | 335746.13 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
PRM-24-077 | 24MO-08F1 | Refurbishing and Revarnishing of Furniture | Goods & Services | GSM | 2024-06-10 | 2024-06-25 | 1:49PM |  | -45468 | PRM | N | NP-SVP | N/A | [5 empty] | N/A | [6 empty] | COB | 106837 | 106837 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
PIP-24-078 | 24MO-07B | 2024 Security Services for PNOC IP | Goods & Services | RGV | 2024-01-17 | 2024-06-25 | 4:20PM |  | -45468 | PIP | N | PB | 2024-06-28 | [12 empty] | COB | 9960827.5 | 9960827.5 | [5 empty] | COA/MBC/ PCCI | [17 empty] | For July Posting
ESB-24-079 | 24MO-07B | 2025 Security Services for PNOC ESB | Goods & Services | RGV | 2024-01-17 | 2024-06-25 | 4:20PM |  | -45468 | ESB | N | PB | 2024-06-28 | [12 empty] | COB | 4862580 | 4862580 | [5 empty] | COA/MBC/ PCCI | [17 empty] | For July Posting
AD-24-080 | 24MO-03A2 | Printing of Cash and Charge Invoices | Goods & Services | GSM | 2024-06-24 | 2024-06-27 | 1:31PM |  | -45470 | AD | N | NP-AA | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  |  |  |  | COB | 240000 | 240000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | Superceded by AD-24-055 |  |  |  |  | For July Posting
PIP-24-048 | 24MO-07A | Supply of Manpower, equipment and Supplies for Janitorial Services at PIP from June 1 to December 2024 | Goods & Services | RGV | 2024-05-05 | 2024-06-27 | 2:10PM |  | -45470 | PIP | N | PB | 2024-06-28 | [12 empty] | COB | 2784590.02 | 2784590.02 | [5 empty] | COA/MBC/ PCCI
PIP-24-049 | 24MO-07C3 | Provision of Manpower for 2024 Custodial Services/Other General Services at PNOC IP (June 1 to December 31 2024 | Goods & Services | RGV | 2024-05-05 | 2024-05-15 | 1:33PM |  | -45427 | PIP | N | PB | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-25 | 2024-06-25 | [8 empty] | COB | 2801245.35 | 2801245.35 | [5 empty] | COA/MBC/ PCCI
SMO-24-050 | 24MO-09D5 | Supply and Delivery of Adobe Acrobat Pro for Teams (1-year subsciption) | Goods & Services | GSM | 2024-04-17 | 2024-05-10 | 1:17PM |  | -45422 | SMO | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A |  | N/A |  | N/A |  |  |  |  | COB | 219377.21 | 219377.21 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing- For Award
PRM-24-051 | 24MO-09D12 | Asset Inventory Management System | Goods & Services | CFCM | 2024-04-16 | 2024-05-20 | 2:52PM |  | -45432 | PRM | N | PB | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-25 | 2024-06-25 | [8 empty] | COB | 4000000 | 4000000 | [5 empty] | COA/MBC/ PCCI | 2024-06-11 | 2024-06-25 | 2024-06-25 | 2024-07-02 | 2024-07-14
BDD-24-052 | Approved Budget Inclusion | Supply and Delivery of Various Measuring Devices and Accessories | Goods & Services | CFCM | 2024-05-15 | 2024-05-23 | 3:56PM |  | -45435 | BRDD | N | PB | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-25 | 2024-06-25 | [8 empty] | COB | 1011000 | 1011000 | [5 empty] | COA/MBC/ PCCI | 2024-06-11 | 2024-06-25 | 2024-06-25 | 2024-07-02 | 2024-07-14
AMD-24-053 | 24MO-07A | 2024 Caretaker Services - PNOC Staffhouse,Lamao, Limay, Bataan | Goods & Services | GSM | 2024-05-15 | 2024-05-23 | 3:56PM |  | -45435 | AMD | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A | 2024-06-20 | N/A |  | N/A |  |  |  |  | COB | 175754.31 | 175754.31 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing- For Award
PRM-24-054 | 24MO-06B8 | Appraisal for PNOC,PAFC,PSTC and PDMC's Unserviceable Properties | Goods & Services | GSM | 2024-05-22 | 2024-05-31 | 8:13AM |  | -45443 | PRM | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A | 2024-06-24 | N/A |  | N/A |  |  |  |  | COB | 175000 | 175000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing- For Award
GSD-24-056 | 24MO-07A | 2024 Janitorial Services | Goods & Services | RGV | 2024-05-30 | 2024-06-04 | 8:43AM | 2024-06-06 | 2 | GSD | N | NP-AA | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 |  |  | July-December |  | COB | 7900000 | 7900000 |  | 7900000 | 7900000 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | For Abstract/NOA Signing
FAILED
AD-24-055 | 24MO-03A2 | Printing of Cash and Charge Invoices | Goods & Services | GSM | 2024-05-23 | 2024-05-29 | 8:10AM |  | -45441 | AD | N | NP-AA | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  |  |  |  | COB | 120000 | 120000 | [23 empty] | Cancelled/Insufficient ABC
AD-24-044 | 24CA-04A5 | Procurement of Computerized Accounting System | Goods & Services | CFCM | 2024-04-29 | 2024-04-30 | 10:51AM |  | -45412 | AD | N | PB | 2024-05-28 | 2024-05-30 | 2024-06-06 | 2024-06-18 | 2024-06-18 | [8 empty] | COB | 4070000 | 4070000 | [5 empty] | PCCI/MBC/COA | 2024-06-06 | 2024-06-18 | 2024-06-18 | 2024-06-25 | 2024-07-07 | [5 empty] | 1st-No bid Receive | 2024-06-18 | 2024-06-18 | 2024-06-19 |  |  |  | AwaIting for rebid
RETURNED TO END-USER
PRM-24-018 | 24MO-03A2 | Supply and Delivery of Consolidated Office Forms for CY2024 | Goods & Services | GSM | 2024-02-29 | 2024-03-07 | 10:50AM |  | -45358 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 401287.7 | 401287.7 | [5 empty] | N/A | N/A | N/A | N/A | N/A
ESB-24-047 |  | 2024 Custodial and Janitorial Services for PNOC ESB | Goods & Services | CFCM | 2024-04-26 | 2024-05-06 | 11:40AM |  | -45418 | ESB | N | PB | [13 empty] | COB | 4283000 | 4283000 | [5 empty] | COA/MBC/ PCCI | [17 empty] | Awating for TOR
SMO-24-065 | 24MO-09E12 | Venue Rental and Catering for Partner's Night | Goods & Services | CFCM | 2024-06-04 | 2024-06-06 | 3:21PM |  | -45449 | SMO | N | PB | [13 empty] | COB | 1200000 | 1200000 | [5 empty] | COA/MBC/ PCCI | [17 empty] | Returned to SMO 6/18/24
PSD-24-074 | Approved Budget Inclusion | Consultancy Services for Comprehensive Reorganization | Consulting Services | RGV | 2024-06-11 | 2024-06-18 | 2:21PM |  | -45461 | PSD | N | PB | [13 empty] | COB | 2000000 | 2000000 | [5 empty] | COA/MBC/ PCCI
CANCELLED
PMD-24-010 | 24MO-08D1A | Repair of Printer - Epson L210 | Goods & Services | GSM | 2024-02-08 | 2024-02-13 | 1:30PM |  | -45335 | PMD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 2500 | [15 empty] | N/A | No bid | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
OP-24-008 | 24MO-08E1D | Repair of Expander NGS-5802 | Goods & Services | RGV | 2024-01-30 | 2024-02-08 | 9:00AM |  | -45330 | OP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 10000 | [22 empty] | Cancelled by proponent
PIP-24-011 | 24MO-09E10 | Supply and Delivery of Materials for 2024 Parkwide Coastal Clean Up | Goods & Services | GSM | 2024-01-29 | 2024-02-13 | 10:30AM |  | -45335 | PIP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 12000 | [16 empty] | Non Compliance | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
SMO-24-022 | 24MO-09C1 | Supply, Delivery and Installation of Rental units of Multi-Functional Printers for PNOC Offices | Goods & Services | CFCM |  | 2024-04-29 | 10:03AM |  | -45411 | SMO | N | PB | 2024-04-30 |  | 2024-05-09 | [7 empty] | N/A |  | COB | COB | 500000 | 500000 | [16 empty] | 1st-non submission | [6 empty] | Cancelled/ Change of Mode of Procurement
[26 empty] | Total Alloted Budget of On-going Procurement Activities | 64511458.7 | 44751458.7 | 19760000
Formulas:
Date of BAC Reso Reco Award = [Date PR Awarded]
Sub/Open of Bids = [Eligibility Check]

## PMR 2024 Updated
PHILIPPINE NATIONAL OIL COMPANY
2024 FIRST SEMESTER PROCUREMENT MONITORING REPORT
PR NO. | Code (PAP) *from APP | Procurement Program/Project | Classification *Goods and Services, Infrastructure or Cosnulting Services | Account Officer *Initials | Date of PR | Date PR Received | Time Received | Date PR Awarded | TAT (days) | PMO/ End-User | Is this an Early Procurement Activity? Y/N | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Winning Bidder | List of Invited Observers | Date of Receipt of Invitation | [7 empty] | Submitted to COA |  | Reason of Failure |  |  |  |  | Payment Oder No./Contract No. | STATUS / REMARKS *Ongoing / Completed | STATUS as of today
[13 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf / Negotiation | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Reso Reco Award | Notice of Award | Contract Signing/ PO | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/Acceptance (if applicable) | Submission to IAO | Submission to OGC |  | Rebid |  | Date of Failure of Bidding | Date of Memo to Proponent (Failure of Bid) | Date Received Memo by Proponent | Date of Submitted CSS Form
COMPLETED PROCUREMENT ACTIVITIES
SMO-24-001 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Energy Supply Base | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | 2024-12-31 |  | COB | 608000 | 608000 |  | 555397.33 |  | 555397.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [10 empty] | Contract#24-001 | Completed | Transmitted to End-User 2/20/24
SMO-24-002 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Industrial Park | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | 2024-12-31 |  | COB | 735000 | 735000 |  | 673647.33 |  | 673647.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [10 empty] | Contract#24-001 | Completed | Transmitted to End-User 2/20/24
SMO-24-003 | 24CA-04A3 | PNOC Network Rehabilitation and Reconfiguration Project | Goods & Services | CFCM |  | 2024-01-15 | 2:53PM | 2024-03-14 | 59 | SMO | N | PB | 2024-01-23 | 2024-01-25 | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 2024-02-29 | 2024-03-14 | 2024-03-14 | 2024-04-29 | 2024-04-05 | 90 days |  | COB | 4900000 |  | 4900000 | 4792565 |  | 4792565 | Pronet Systems Integrated Network Solution, Inc. | MBC, COA, PCCI | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-16 | 2024-02-22 | [10 empty] | Contract#24-002 | Completed | Received Signed 3.15.24
SMO-24-004 | 24CA-04A2 | Supply and Delivery of Laptop Computers | Goods & Services | CFCM | 2023-12-18 | 2024-01-15 | 2:53PM | 2024-04-01 | 77 | SMO | N | NP-SVP | N/A | 2024-02-01 | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-28 | 2024-04-01 | 2024-04-01 | N/A | 2024-04-04 | N/A | 90 days |  | COB | 706000 |  | 706000 | 626690 |  | 626690 | Joneco Tech Marketing Corporation | MBC, COA, PCCI | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-29 | 2024-03-12 | [10 empty] | PO#298785 | Completed | rEceived Signed PO 4.15.24
GSD-24-005 | 24MO-07B | 2024 Security Services for PNOC Head Office | Goods & Services | RGV | 2024-01-09 | 2024-01-25 | 11:00AM | 2024-04-16 | 82 | GSD | N | PB | 2024-01-31 | 2024-02-06 | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-26 | 2024-04-12 | 2024-04-16 | 2024-04-16 | 2024-05-08 | 2024-04-26 | 2024-12-31 |  | COB | 10400000 | 10400000 |  | 10333557.5 | 10333557.5 |  | Eliteblue Security Specialist, Inc. | MBC, COA, PCCI | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-08 | 2024-03-16 | [10 empty] | Contract#24-003 | Completed | Completed/Delivered
SMO-24-006 | 24MO-06A1 | Consulting Services for the Digital Transformation Initiative of PNOC | Consulting Services | CFCM | 2024-01-22 | 2024-01-26 | 8:30AM | 2024-01-31 | 5 | SMO | N | NP-AA | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-02 | 2024-03-11 | 2024-03-01 | 2024-12-31 |  | COB | 4950000 | 4950000 |  | 4912969.56 | 4912969.56 |  | University of the Philippines | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Completed
PIP-24-007 | 24MO-08D1U | 2024 Preventive Maintenance of PNOC Gym Equipment | Goods & Services | GSM | 2024-01-31 | 2024-02-20 | 11:09AM | 2024-03-14 | 23 | PRM | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-13 | N/A | 2024-03-14 | N/A | 2024-03-18 | N/A | 2024-12-31 | COB | COB | 48000 | 48000 |  | 48000 | 48000 |  | The FitCo, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298783 | Completed | Completed/Delivered
GSD-24-009 | 24MO-03A9AN | Purchase of Materials for Fabrication of of Bed Frame | Goods & Services | GSM | 2024-01-25 | 2024-02-08 | 1:35PM | 2024-03-19 | 40 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4665 | 4665 |  | 3120 | 3120 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
GSD-24-012 | 24MO-03A9AN | Carpentry Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 7145 | 7145 |  | 4940 | 4940 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
GSD-24-013 | 24MO-03A9AN | Plumbing Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 12196 | 12196 |  | 9650 | 9650 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
GSD-24-014 | 24MO-03A9AN | Electrical Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4133.75 | 4133.75 |  | 3231 | 3231 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
GSD-24-015 | 24MO-08D1W | Aircon Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 34490.57 | 34490.57 |  | 33892 | 33892 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Completed | Completed/Delivered
SMO-24-016 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token | Goods & Services | GSM |  | 2024-03-01 | 4:15PM | 2024-04-25 | 55 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-22 | N/A | 2024-04-25 | N/A | 2024-04-25 | N/A | 30 days |  | COB | 275000 | 275000 |  | 215520 | 215520 |  | Jen Lin Corporate Giveaways | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298787 | Completed | Completed/Delivered
PSD-24-017 | 24MO-038AC | Supply and Delivery of Fluquadri (Adult) | Goods & Services | RGV | 2024-02-19 | 2024-03-06 | 4:15PM | 2024-04-18 | 43 | PSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-16 | N/A | 2024-04-18 | N/A | 2024-04-23 | N/A | 15 days |  | COB | 85000 | 85000 |  | 61456 | 61456 |  | Pharma Quest Co. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298786 | Completed | Completed
PRM-24-020 | 24MO-03A1 | Supply and Delivery of Consolidated Commonly-Use Supplies for January-February 2024 | Goods & Services | GSM | 2024-03-20 | 2024-03-11 | 2:30PM | 2024-05-16 | 66 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | N/A | N/A | 2024-05-16 | N/A | 2024-05-29 | N/A | 30 days |  | COB | 333058.99 | 333058.99 |  | 240263.15 | 240263.15 |  | Varyline & Lambert Trading | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298795/ 298796 | Completed | Completed/Delivered
PIP-24-021 | 24MO-07C5D | Hauling, Transport, Treatment and Disposal of Generated Hazardous wastes of PIP | Goods & Services | RGV | 2024-01-23 | 2024-03-14 | 9:16AM | 2024-05-28 | 75 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-05-24 | N/A | 2024-05-28 | 2024-06-04 | 2024-06-24 | 2024-07-01 | 30 days |  | COB | 137917 | 137917 |  | 104500 | 104500 |  | Clean Leaf Intrenational Corp. | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Completed | NOA/for Contract Draft
PIP-24-023 | 24MO-06B6 | 2024 Environmental Monitoring (Waste Water-Effluent and Marine, Raw Water, Ambient Air Sampling and Laboratory Analysis) | Goods & Services | RGv | 2023-09-06 | 2024-03-22 | 10:09AM | 2024-05-27 | 66 | PIP | N | PB | N/A | 2024-04-04 | 2024-04-11 | 2024-04-25 | 2024-04-25 | 2024-05-03 | 2024-05-27 | 2024-05-28 | 2024-05-30 | 2024-06-21 | 2024-06-13 | 2024-12-31 |  | COB | 825000 | 825000 |  | 688140 | 688140 |  | CRL Environmental Corporation | COA/MBC/PCCI | 2024-04-11 | 2024-04-25 | 2024-04-25 | 2024-05-03 | 2024-05-28 | [10 empty] | Contract#24-009 | Completed
SMO-24-024 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token(Bamboo Stainless Cup) | Goods & Services | CFCM |  | 2024-03-25 | 1:58PM | 2024-04-25 | 31 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-23 | N/A | 2024-04-25 | N/A | 2024-04-30 | N/A | 30 days | COB | COB | 90000 | 90000 |  | 40000 | 40000 |  | CSG Manufacturing Corporation | N/A | 2024-04-26 | 2024-04-03 | 2024-05-16 | 2024-05-16 | 2024-05-16 | [10 empty] | PO#298788 | Completed | Completed/Delivered
PIP-24-025 | 24MO-03A7C/08D1L | Supply and Delivery of Electrical Items(Batteries for Genset and Fire Engine) | Goods & Services | GSM | 2024-01-15 | 2024-03-25 | 2:37PM | 2024-04-25 | 31 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-25 | N/A | 2024-04-25 | N/A | 2024-05-07 | N/A | 30 days |  | COB | 195600 | 195600 |  | 153614 | 153614 |  | 8 Days A Week Consumer Goods Trading | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298789 | Completed | Completed/Delivered
GSD-24-026 | 24MO-04A3 | 2024 Supply and Delivery of Drinking Water | Goods & Services | GSM | 2024-03-12 | 2024-04-04 | 9:03AM | 2024-04-23 | 19 | GSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-19 | N/A | 2024-04-23 | 2024-04-29 | 2024-06-21 | 2024-04-30 | 2024-12-31 |  | COB | 212000 | 212000 |  | 176320 | 176320 |  | MSDR Water Refilling Station | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-013 | Completed | Contract for Signing of EAL
SMO-24-027 | 24MO-09D15 | Supply and Delivery of Barcode Scanner | Goods & Services | GSM | 2024-04-04 | 2024-04-05 | 11:50AM | 2024-04-30 | 25 | SMO | N | NP-SVP | N/A | 2024-04-12 | N/A | N/A | N/A | 2024-04-25 | N/A | 2024-04-30 | N/A | 2024-05-08 | N/A | 30 days |  | COB | 211000 | 211000 |  | 56440 | 56440 |  | A.G. Datacom Phis.,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298790 | Completed | Completed/Delivered
PSD-24-028 | 24MO-07C2 | 2024 Temporary Office Services | Goods & Services | RGV |  | 2024-04-11 | 8:30AM | 2024-04-11 | 0 | PSD | N | NP-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 | 2024-05-30 | 2024-04-26 | 2024-12-31 |  | COB | 9500000 | 9500000 |  | 7464399.68 | 7464399.68 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-004 | Completed | Completed/Delivered
SMO-24-029 | 24MO-09D6 | Supply and Delivery of Cloud-based Email, Productivity, and Collaboration Service Subscription / Email Hosting Service Subscription | Goods & Services | RGV |  | 2024-04-17 | 2:30PM | 2024-05-30 | 43 | SMO | N | PB | 2024-04-25 | 2024-04-26 | 2024-04-03 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-05-23 | 2024-05-30 | 2024-05-30 | 2024-07-01 | 2024-06-25 | 30 days |  | COB | 1800000 | 1800000 |  | 1383810.97 | 1383810.97 |  | ePLDT,Inc. | COA/MBC/PCCI | 2024-04-04 | 2024-04-11 | 2024-04-25 | 2024-04-25 | 2024-05-03 | [11 empty] | Completed | NTP/Contract for Sign of OP
PSD-24-030 | 24CA-04F | Supply, Delivery, Installation and Implementation of Time and Attendance Monitoring System w/ 3 Biometric devices (facial recognition/finger scan) | Goods & Services | RGV | 2024-03-25 | 2024-04-19 | 1:08PM | 2024-05-14 | 25 | PSD | N | NP-SVP | N/A | 2024-05-09 | N/A | N/A | N/A | 2024-05-14 | N/A | 2024-05-14 | 2024-05-14 | 2024-06-30 | 2024-06-23 | 15 days |  | COB | 800000 |  | 800000 | 635000 |  | 635000 | 3GX Computer and IT Solutions Techshop | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-006 | Completed | Completed/Delivered
GSD-24-031 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at G/Fr. Zone #1 Compressor#1 of PNOC Bldg.5 | Goods & Services | GSM | 2024-02-29 | 2024-04-18 | 11:17AM | 2024-04-30 | 12 | GSD | N | NP-SVP | N/A | 2024-04-24 | N/A | N/A | N/A | 2024-04-29 | N/A | 2024-04-30 | 2024-04-30 | 2024-06-30 | 2024-05-02 | 30 days |  | COB | 161760 | 161760 |  | 140000 | 140000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #24-011 | Completed | Contract for Sign of OP 6.24.24
GSD-24-032 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at 2nd/Flr. Zone #1 Compressor#2 of PNOC Bldg.5 | Goods & Services | GSM | 2024-01-25 | 2024-04-23 | 11:35AM | 2024-04-30 | 7 | GSD | N | NP-SVP | N/A | 2024-04-24 | N/A | N/A | N/A | 2024-04-29 | N/A | 2024-04-30 | 2024-04-30 | 2024-06-30 | 2024-05-02 | 30 days |  | COB | 162720 | 162720 |  | 135000 | 135000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #24-011 | Completed | Contract for Sign of OP 6.24.24
GSD-24-033 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at 3rd/Flr. Zone #2 of PNOC Bldg.5 | Goods & Services | GSM | 2024-04-17 | 2024-04-23 | 9:20AM | 2024-04-30 | 7 | GSD | N | NP-SVP | N/A | 2024-04-24 | N/A | N/A | N/A | 2024-04-29 | N/A | 2024-04-30 | 2024-04-30 | 2024-07-01 | 2024-05-02 | 30 days |  | COB | 161760 | 161760 |  | 138000 | 138000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #24-011 | Completed | Contract for Sign of OP 6.24.24
CS-24-034 | Memo Realignment | Corporate Retreat and Planning of Board of Directors | Goods & Services | CFCM | 2024-04-22 | 2024-04-24 | 2:43PM | 2024-05-10 | 16 | CORSEC | N | NP-SVP | N/A | 2024-05-04 | N/A | N/A | N/A | 2024-05-08 | N/A | 2024-05-10 | 2024-05-09 | 2024-06-10 | 2024-05-13 | 3 days |  | COB | 400000 | 400000 |  | 398000 | 398000 |  | Marivent Resort Hotel, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-005 | Completed | Contract for Signing of Contractor
GSD-24-035 | 24MO-08C2C | 2024 Pest Control Services for PNOC Building at Fort Bonifacio and PNOC Property in Tagaytay | Goods & Services | GSM | 2024-03-11 | 2024-04-05 | 9:41AM | 2024-05-16 | 41 | GSD | N | NP-SVP | N/A | 2024-05-07 | N/A | N/A | N/A | 2024-05-14 | N/A | 2024-05-16 | N/A | 2024-05-27 | N/A | 2024-12-31 |  | COB | 81000 | 81000 |  | 68200 | 68200 |  | Ram Pest Control Services | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298793 | Completed | Completed/Delivered
PIP-24-036 | 24MO-08D1Q | Supply and Delivery of Lighting Panel Board | Goods & Services | GSM | 2024-01-31 | 2024-04-18 | 9:45AM | 2024-05-21 | 33 | PIP | N | NP-SVP | N/A | 2024-05-07 | N/A | N/A | N/A | 2024-05-17 | N/A | 2024-05-21 | N/A | 2024-05-28 | N/A | 30 days |  | COB | 120000 | 120000 |  | 110000 | 110000 |  | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298794 | Completed | Completed/Delivered
GSD-24-037 | 24MO-08D1X | Reconditioning /Rehabilitation of 900kW Caterpillar Genset Alternator at PNOC Bldg.5 | Goods & Services | CFCM | 2024-03-12 | 2024-04-19 | 2:33PM | 2024-06-06 | 48 | GSD | N | PB | 2024-04-30 | 2024-05-02 | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-29 | 2024-06-06 | 2024-06-06 | 2024-06-06 |  | 2024-06-21 | 30 days |  | COB | 1755291.67 | 1755291.67 |  | 1495600 | 1495600 |  | Tabuko Energy Network Corp. | COA/MBC/ PCCI | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-28 | 2024-06-09 | [11 empty] | Completed | For NTP?Comtract
GSD-24-038 | 24CA-04D | Supply and Delivery of Interactive Flat Panel Display | Goods & Services | RGV | 2024-04-04 | 2024-04-23 | 9:52AM | 2024-06-06 | 44 | GSD | N | PB | 2024-04-30 | 2024-05-02 | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-29 | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-06-11 | 2024-06-11 | 2024-07-11 |  | COB | 2200000 |  | 2200000 | 1200684 |  | 1200684 | A.G. Datacom Phils.,Inc./American Technologies, Inc. | COA/MBC/ PCCI | 2024-05-09 | 2024-05-21 | 2024-05-21 | 2024-05-28 | 2024-06-10 | [10 empty] | PO#298797/ 298798 | Completed | Completed/Delivered
OP-24-043 | Approved Budget Inclusion | Highly Technical Consultant for the Office of the President and Board of Directors for Public-Private Partnership | Consulting Services | CFCM | 2024-04-30 | 2024-04-30 | 10:30AM | 2024-05-02 | 2 | OP | N | NP-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-05-02 | 2024-05-06 | 2024-06-19 | 2024-05-09 | 2024-11-15 |  | COB | 360000 | 360000 |  | 360000 | 360000 |  | Atty. Alberto C. Agra | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#24-007 | Completed | Contract for signing of Contractor
PIP-24-045 | 24MO-03A7A | Supply and Delivery of Mechanical Consumables for Booster Pumps | Goods & Services | RGV | 2024-02-20 | 2024-04-30 | 11:13AM | 2024-05-21 | 21 | PIP | N | NP-SVP | N/A | 2024-05-07 | N/A | N/A | N/A | 2024-05-17 | N/A | 2024-05-21 | N/A | 2024-05-24 | N/A | 30 days |  | COB | 146408 | 146408 |  | 66030 | 66030 |  | Pumpcraft Industrial Sales/Manara Marketing | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298792/298791 | Completed | Completed
GSD-24-057 | 24MO-07C1 | 2024 Messengerial Services | Goods & Services | RGV | 2024-05-30 | 2024-06-04 | 8:43AM | 2024-06-06 | 2 | GSD | N | NP-AA | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 |  | 2024-06-20 | 2024-12-31 |  | COB | 1250000 | 1250000 |  | 1250000 | 1250000 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Completed | For Abstract/NOA Signing
GSD-24-058 | 24MO-07C3 | 2024 Maintenance Services | Goods & Services | RGV | 2024-05-30 | 2024-06-04 | 8:43AM | 2024-06-06 | 2 | GSD | N | NP-AA | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 |  | 2024-06-20 | 2024-12-31 |  | COB | 2550000 | 2550000 |  | 2550000 | 2550000 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Completed | For Abstract/NOA Signing
[26 empty] | Total Alloted Budget of Procurement Activities | 46223145.98 | 37617145.98 | 8606000
[26 empty] | Total Contract Price Procurement Activities Conducted |  |  |  | 41128637.52 | 32644653.86 | 8483983.66
[26 empty] | Total Savings (Total Alloted Budget - Total Contract Price) | 5094508.46
ONGOING PROCUREMENT PROJECTS
ESB-24-040 | 24MO-08D1D | Preventive Maintenance of Truck Scale (Quarterly Check-up and Calibration with ITDI Certificate) | Goods & Services | GSM | 2024-01-31 | 2024-04-25 | 4:31PM |  | -45407 | ESB | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A | [8 empty] | COB | 83000 | 83000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing-Technical Evaluation
PIP-24-041 | 24MO-08D1S | Supply and Delivery of Consumables for Painting and Repair | Goods & Services | GSM | 2024-02-01 | 2024-05-20 | 11:30AM |  | -45432 | PIP | N | NP-SVP | N/A | [12 empty] | COB | 127727 | 127727 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 1st | 1st - No Bid Receive | 2024-06-13 | 2024-06-13 | 2024-06-14 |  |  |  | Awating for rebid
PIP-24-041 | 24MO-08D1S | Supply and Delivery of Consumables for Painting and Repair (Rebid) | Goods & Services | GSM |  | 2024-06-19 | 11:30AM |  | -45462 | PIP | N | NP-SVP | N/A | 2024-06-25 | N/A | N/A | N/A | [8 empty] | COB | 127727 | 127727 | [6 empty] | N/A | N/A | N/A | N/A | N/A
ESB-24-046 | Approved Budget Realignment | Supply and Delivery of Foam-Filled Rubber Fender | Goods & Services | RGV | 2024-02-14 | 2024-05-02 | 10:20AM |  | -45414 | ESB | N | PB | 2024-06-13 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-02 | [8 empty] | COB | 1616684 | 1616684 | [5 empty] | COA/MBC/ PCCI | 2024-06-18 | 2024-07-02 | 2024-07-02 | 2024-07-09 | 2024-07-21 | [12 empty] | Ongoing
SMO-24-059 | 24MO-03A8A3 | Supply and Delivery of Token/Giveaways (Electronic Gift Set) | Goods & Services | GSM |  | 2024-06-03 | 1:28PM |  | -45446 | SMO | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 165000 | 165000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1ST- NO BID RECEIVE | 2024-06-13 | 2024-06-13 | 2024-06-14 |  |  |  | For Opening of Bids
GSD-24-060 | Awaiting Approved Budget Realignment | Contract Services for the Preventive Maintenance of 2 units Passenger elevator at PNOC Bldg.6 | Goods & Services | GSM | 2024-05-20 | 2024-06-24 | 9:44AM |  | -45467 | GSD | N | NP-SVP | N/A | N/A | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 102161.63 | 102161.63 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing
GSD-24-061 | 24MO-08C1P | Fire Protection Services for PNOC Bldgs. 5&6 | Goods & Services | GSM |  | 2024-06-04 | 9:44AM |  | -45447 | GSD | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 154999.98 | 154999.98 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
GSD-24-062 | 24MO-08C1D | Preventive Maintenance of Centralized AC Units at PNOC Bldg. 5&6 | Goods & Services | GSM | 2024-05-20 | 2024-06-04 | 9:44AM |  | -45447 | GSD | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 531990 | 531990 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st-File Cannot be Open | 2024-06-25 | 2024-06-26 | 2024-06-26 |  |  | Failed Bidding | Awaiting Reply from Proponent
SMO-24-063 | 24MO-09D10 | Procurement of AutoCAD Software (1yr. Subscription for PNOC-HO) | Goods & Services | GSM | 2024-06-03 | 2024-06-06 | 8:50AM |  | -45449 | SMO | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 120000 | 120000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
PSD-24-064 | 24MO-03A8A2 | Supply and Delivery of Birthday Token (Smart Watch) | Goods & Services | GSM | 2024-05-16 | 2024-06-06 | 4:26PM |  | -45449 | PSD | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 290000 | 290000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st - Non-Submission | 2024-06-25 | 2024-06-26 | 2024-06-26 |  |  | Failed Bidding | Awaiting Reply from Proponent
AMD-24-066 | 24MO-07B | 2024 Security Services (Provincial Posts) (July 01-December 31, 2024) | Goods & Services | RGV | 2024-05-09 | 2024-06-07 | 1:59PM |  | -45450 | AMD | N | PB | 2024-06-13 | 2024-06-18 | 2024-06-25 | 2024-07-09 | 2024-07-09 | [8 empty] | COB | 3215634 | 3215634 | [5 empty] | COA/MBC/ PCCI | 2024-06-25 | 2024-06-09 | 2024-06-09 | 2024-07-16 | 2024-07-29
ESB-24-067 | 24MO-06A5 | Engagement of Environmental Services to Conduct Quarterly Ambient Air Quality , Semi-Annual Raw Water Testing and Ambient Ambient Water Quality Monitoring at ESB | Goods & Services | RGV | 2024-05-06 | 2024-06-07 | 2:48PM |  | -45450 | ESB | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 250000 | 250000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
SMO-24-068 | 24MO-03A5P/03A5Q/03A5N/03A5O | Supply and Delivery of Various IT Equipments Supplies | Goods & Services | GSM | 2024-06-04 | 2024-06-07 | 3:51PM |  | -45450 | SMO | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 292700 | 292700 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
OC-24-069 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token for Office of the Chairman | Goods & Services | GSM |  | 2024-06-07 | 4:00PM |  | -45450 | OC | N | NP-SVP | N/A | 2024-06-14 | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 207580.24 | 207580.24 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing/For Technical Evaluation
SMO-24-070 | 24MO-09C1 | Supply, Delivery and Installation of Rental units of Multi-Functional Printers for PNOC Offices | Goods & Services | RMB |  | 2024-06-10 | 1:09PM |  | -45453 | SMO | N | NP-SVP |  |  | N/A | N/A | N/A | [8 empty] | COB | 800000 | 800000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
PIP-24-071 | 24MO-08D10 | Genset Servicing | Goods & Services | RGV | 2024-05-11 | 2024-06-11 | 11:10AM |  | -45454 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 100000 | 100000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A
ESB-24-072 | 24MO-08A1-A2/ 24MO-08C1C-IK/ 24MO-08D1D/24MO-08D1G | Supply and Delivery of Materials for 2024 ESB Annual Maintenance Plan | Goods & Services | GSM | 2024-04-25 | 2024-06-13 | 8:34AM |  | -45456 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 610199.75 | 610199.75 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
GSD-24-073 | 24CA-038 | Replacement of Airconditioning System - Ground Floor to 3rd Floor of PNOC Building 5 | Goods & Services | CFCM | 2024-05-16 | 2024-06-18 | 10:30AM |  | -45461 | GSD | N | PB | 2024-06-20 | 2024-06-25 | 2024-07-02 | 2024-07-06 | 2024-07-06 | [8 empty] | COB | 19760000 |  | 19760000 |  |  |  |  | COA/MBC/ PCCI | 2024-07-27 | 2024-07-16 | 2024-07-16 | 2024-07-13 | 2024-08-04
PRM-24-075 | 24MO-03A1 | Supply and Delivery of Computer Supplies | Goods & Services | GSM | 2024-06-05 | 2024-06-18 | 8:18PM |  | -45461 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 302175.97 | 302175.97 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
PRM-24-076 | 24MO-03A1 | Supply and Delivery of Commonly-use Supplies | Goods & Services | GSM | 2024-06-10 | 2024-06-24 | 10:50AM |  | -45467 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 335746.13 | 335746.13 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
PRM-24-077 | 24MO-08F1 | Refurbishing and Revarnishing of Furniture | Goods & Services | GSM | 2024-06-10 | 2024-06-25 | 1:49PM |  | -45468 | PRM | N | NP-SVP | N/A | [5 empty] | N/A | [6 empty] | COB | 106837 | 106837 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For July Posting
PIP-24-078 | 24MO-07B | 2024 Security Services for PNOC IP | Goods & Services | RGV | 2024-01-17 | 2024-06-25 | 4:20PM |  | -45468 | PIP | N | PB | 2024-06-28 | [12 empty] | COB | 9960827.5 | 9960827.5 | [5 empty] | COA/MBC/ PCCI | [17 empty] | For July Posting
ESB-24-079 | 24MO-07B | 2025 Security Services for PNOC ESB | Goods & Services | RGV | 2024-01-17 | 2024-06-25 | 4:20PM |  | -45468 | ESB | N | PB | 2024-06-28 | [12 empty] | COB | 4862580 | 4862580 | [5 empty] | COA/MBC/ PCCI | [17 empty] | For July Posting
AD-24-080 | 24MO-03A2 | Printing of Cash and Charge Invoices | Goods & Services | GSM | 2024-06-24 | 2024-06-27 | 1:31PM |  | -45470 | AD | N | NP-AA | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  |  |  |  | COB | 240000 | 240000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | Superceded by AD-24-055 |  |  |  |  | For July Posting
PIP-24-048 | 24MO-07A | Supply of Manpower, equipment and Supplies for Janitorial Services at PIP from June 1 to December 2024 | Goods & Services | RGV | 2024-05-05 | 2024-06-27 | 2:10PM |  | -45470 | PIP | N | PB | 2024-06-28 | [12 empty] | COB | 2784590.02 | 2784590.02 | [5 empty] | COA/MBC/ PCCI
PIP-24-049 | 24MO-07C3 | Provision of Manpower for 2024 Custodial Services/Other General Services at PNOC IP (June 1 to December 31 2024 | Goods & Services | RGV | 2024-05-05 | 2024-05-15 | 1:33PM |  | -45427 | PIP | N | PB | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-25 | 2024-06-25 | [8 empty] | COB | 2801245.35 | 2801245.35 | [5 empty] | COA/MBC/ PCCI
SMO-24-050 | 24MO-09D5 | Supply and Delivery of Adobe Acrobat Pro for Teams (1-year subsciption) | Goods & Services | GSM | 2024-04-17 | 2024-05-10 | 1:17PM |  | -45422 | SMO | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A |  | N/A |  | N/A |  |  |  |  | COB | 219377.21 | 219377.21 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing- For Award
PRM-24-051 | 24MO-09D12 | Asset Inventory Management System | Goods & Services | CFCM | 2024-04-16 | 2024-05-20 | 2:52PM |  | -45432 | PRM | N | PB | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-25 | 2024-06-25 | [8 empty] | COB | 4000000 | 4000000 | [5 empty] | COA/MBC/ PCCI | 2024-06-11 | 2024-06-25 | 2024-06-25 | 2024-07-02 | 2024-07-14
BDD-24-052 | Approved Budget Inclusion | Supply and Delivery of Various Measuring Devices and Accessories | Goods & Services | CFCM | 2024-05-15 | 2024-05-23 | 3:56PM |  | -45435 | BRDD | N | PB | 2024-05-30 | 2024-06-04 | 2024-06-11 | 2024-06-25 | 2024-06-25 | [8 empty] | COB | 1011000 | 1011000 | [5 empty] | COA/MBC/ PCCI | 2024-06-11 | 2024-06-25 | 2024-06-25 | 2024-07-02 | 2024-07-14
AMD-24-053 | 24MO-07A | 2024 Caretaker Services - PNOC Staffhouse,Lamao, Limay, Bataan | Goods & Services | GSM | 2024-05-15 | 2024-05-23 | 3:56PM |  | -45435 | AMD | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A | 2024-06-20 | N/A |  | N/A |  |  |  |  | COB | 175754.31 | 175754.31 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing- For Award
PRM-24-054 | 24MO-06B8 | Appraisal for PNOC,PAFC,PSTC and PDMC's Unserviceable Properties | Goods & Services | GSM | 2024-05-22 | 2024-05-31 | 8:13AM |  | -45443 | PRM | N | NP-SVP | N/A | 2024-06-05 | N/A | N/A | N/A | 2024-06-24 | N/A |  | N/A |  |  |  |  | COB | 175000 | 175000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing- For Award
GSD-24-056 | 24MO-07A | 2024 Janitorial Services | Goods & Services | RGV | 2024-05-30 | 2024-06-04 | 8:43AM | 2024-06-06 | 2 | GSD | N | NP-AA | 2024-06-04 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-06-06 | 2024-06-06 |  |  | July-December |  | COB | 7900000 | 7900000 |  | 7900000 | 7900000 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For Abstract/NOA Signing
| 24CA-04A5 | Procurement of Computerized Accounting System | Goods & Services | CFCM | 2024-04-29 | 2024-04-30 | 10:51AM |  | -45412 | AD | N | PB | 2024-05-28 | 2024-05-30 | 2024-06-06 | 2024-06-18 | 2024-06-18 | [8 empty] | COB | 4070000 | 4070000 | [5 empty] | PCCI/MBC/COA | 2024-06-06 | 2024-06-18 | 2024-06-18 | 2024-06-25 | 2024-07-07 | [5 empty] | 1st-No bid Receive | 2024-06-18 | 2024-06-18 | 2024-06-19 |  |  | Failed Bidding
| Approved Budget Inclusion | Consultancy Services for Comprehensive Reorganization | Consulting Services | RGV | 2024-06-11 | 2024-06-18 | 2:21PM |  | -45461 | PSD | N | PB | [13 empty] | COB | 2000000 | 2000000
FAILED
PRM-24-018 | 24MO-03A2 | Supply and Delivery of Consolidated Office Forms for CY2024 | Goods & Services | GSM | 2024-02-29 | 2024-03-07 | 10:50AM |  | -45358 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 401287.7 | 401287.7 | [5 empty] | N/A | N/A | N/A | N/A | N/A
ESB-24-047 |  | 2024 Custodial and Janitorial Services for PNOC ESB | Goods & Services | CFCM | 2024-04-26 | 2024-05-06 | 11:40AM |  | -45418 | ESB | N | PB | [13 empty] | COB | 4283000 | 4283000 | [5 empty] | COA/MBC/ PCCI | [17 empty] | Awating for TOR
SMO-24-065 | 24MO-09E12 | Venue Rental and Catering for Partner's Night | Goods & Services | CFCM | 2024-06-04 | 2024-06-06 | 3:21PM |  | -45449 | SMO | N | PB | [13 empty] | COB | 1200000 | 1200000 | [5 empty] | COA/MBC/ PCCI | [17 empty] | Returned to SMO 6/18/24
CANCELLED
PMD-24-010 | 24MO-08D1A | Repair of Printer - Epson L210 | Goods & Services | GSM | 2024-02-08 | 2024-02-13 | 1:30PM |  | -45335 | PMD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 2500 | [15 empty] | N/A | No bid | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
OP-24-008 | 24MO-08E1D | Repair of Expander NGS-5802 | Goods & Services | RGV | 2024-01-30 | 2024-02-08 | 9:00AM |  | -45330 | OP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 10000 | [22 empty] | Cancelled by proponent
PIP-24-011 | 24MO-09E10 | Supply and Delivery of Materials for 2024 Parkwide Coastal Clean Up | Goods & Services | GSM | 2024-01-29 | 2024-02-13 | 10:30AM |  | -45335 | PIP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 12000 | [16 empty] | Non Compliance | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
SMO-24-022 | 24MO-09C1 | Supply, Delivery and Installation of Rental units of Multi-Functional Printers for PNOC Offices | Goods & Services | CFCM |  | 2024-04-29 | 10:03AM |  | -45411 | SMO | N | PB | 2024-04-30 |  | 2024-05-09 | [7 empty] | N/A |  | COB | COB | 500000 | 500000 | [16 empty] | 1st-non submission | [6 empty] | Cancelled/ Change of Mode of Procurement
[26 empty] | Total Alloted Budget of On-going Procurement Activities | 69500537.09 | 43670537.09 | 19760000
Recommended for Approval:
|  | Prepared by: | [7 empty] | Bids and Awards Committee: | [9 empty] | Approved by:
|  | R. M. Babera | [7 empty] | A. E. Suyom J. R. Racho A. G. Buenviaje J. C. J. Cui | [9 empty] | OLIVER B. BUTALID
President and CEO
Formulas:
Date of BAC Reso Reco Award = [Date PR Awarded]
Sub/Open of Bids = [Eligibility Check]

## PMR 2024 (3) (hidden)
| COMPANY: PHILIPPINE NATIONAL OIL COMPANY LOCATION: Bldg.6 Energy Center, Rizal Drive, BGC, Taguig SUBJECT: Procurement Monitoring |  |  |  |  | NOTE: 1.
[16 empty] | FAILED |  |  |  | ONGOING
[16 empty] | COMPLETED |  |  |  | AWARDED
#REF!
| AS OF: | 2024-10-16
PR NO. | Code (PAP) *from APP | Procurement Program/Project | Classification *Goods and Services, Infrastructure or Cosnulting Services | Account Officer *Initials | Date of PR | Date PR Received | Time Received | Date PR Awarded | TAT (days) | PMO/ End-User | Is this an Early Procurement Activity? Y/N | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Winning Bidder | List of Invited Observers | Date of Receipt of Invitation | [7 empty] | Submitted to COA |  | Reason of Failure |  |  |  |  | Payment Oder No./Contract No. | STATUS / REMARKS *Ongoing / Completed | STATUS as of today
[13 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf / Negotiation | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Reso Reco Award | Notice of Award | Contract Signing/ PO | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/Acceptance (if applicable) | Submission to IAO | Submission to OGC |  | Rebid |  | Date of Failure of Bidding | Date of Memo to Proponent (Failure of Bid) | Date Received Memo by Proponent | Date of Submitted CSS Form
ONGOING
SMO-24-001 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Energy Supply Base | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | February-December |  | COB | 608000 | 608000 |  | 555397.33 |  | 555397.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [11 empty] | Completed | Awarded
SMO-24-002 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Industrial Park | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | February-December |  | COB | 735000 | 735000 |  | 673647.33 |  | 673647.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [11 empty] | Completed | Awarded
SMO-24-003 | 24MO-04A3 | PNOC Network Rehabilitation and Reconfiguration Project | Goods & Services | CFCM |  | 2024-01-15 | 2:53PM | 2024-03-14 | 59 | SMO | N | PB | 2024-01-23 | 2024-01-25 | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 2024-02-29 | 2024-03-14 | 2024-03-14 |  | 2024-04-05 | 90 days |  | COB | 4900000 | 4900000 |  | 4792565 |  | 4792565 | Pronet Systems Integrated Network Solution, Inc. | MBC, COA, PCCI | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-16 | 2024-02-22 | [11 empty] | Awarded | Awarded
SMO-24-004 | 24MO-04A2 | Supply and Delivery of Laptop Computers | Goods & Services | CFCM | 2023-12-18 | 2024-01-15 | 2:53PM | 2024-04-01 | 77 | SMO | N | NP-SVP | N/A | 2024-02-01 | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-28 | 2024-04-01 | 2024-04-01 | N/A | 2024-04-04 | N/A | 90 days |  | COB | 706000 | 706000 |  | 626690 |  | 626690 | Joneco Tech Marketing Corporation | MBC, COA, PCCI | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-29 | 2024-03-12 | [10 empty] | PO#298785 | Awarded | Awarded
GSD-24-005 | 24MO-07B | 2024 Security Services for PNOC Head Office | Goods & Services | RGV | 2024-01-09 | 2024-01-25 | 11:00AM |  | -45316 | GSD | N | PB | 2024-01-31 | 2024-02-06 | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-26 |  | 2024-04-16 | 2024-04-16 |  |  | May-December |  | COB | 10400000 | 10400000 |  | 10333557.5 | 10333557.5 |  | Eliteblue Security Specialist, Inc. | MBC, COA, PCCI | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-08 | 2024-03-16 | [11 empty] | Awarded | Awarded
SMO-24-006 | 24MO-06A1 | Consulting Services for the Digital Transformation Initiative of PNOC | Consulting Services | CFCM | 2024-01-22 | 2024-01-26 | 8:30AM | 2024-01-31 | 5 | SMO | N | AA | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-02 | 2024-03-11 | 2024-03-01 |  |  | COB | 4950000 | 4950000 |  | 4912969.56 | 4912969.56 |  | University of the Philippines | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | Awarded
PIP-24-007 | 24MO-08D1U | 2024 Preventive Maintenance of PNOC Gym Equipment | Goods & Services | GSM | 2024-01-31 | 2024-02-20 | 11:09AM | 2024-03-14 | -45342 | PRM | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-13 | N/A | 2024-03-14 | N/A | 2024-03-18 | N/A | Jan-Dec | COB | COB | 48000 | 48000 |  | 48000 | 48000 |  | The FitCo, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298783 | Awarded | Awarded
| 24MO-08E1D | Repair of Expander NGS-5802 | OP | [6 empty] | OP | [41 empty] | Cancelled by Proponent
GSD-24-009 | 24MO-03A9AN | Purchase of Materials for Fabrication of of Bed Frame | Goods & Services | GSM | 2024-01-25 | 2024-02-08 | 1:35PM | 2024-03-19 | 40 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4665 | 4665 |  | 3120 | 3120 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Awarded
| 24MO-08D1A | Repair of Printer - Epson L210 | PMD | [6 empty] | PMD | [41 empty] | Cancelled/Irrepairable
| 24MO-09E10 | Supply and Delivery of Materials for 2024 Parkwide Coastal Clean Up | PIP | [6 empty] | PIP | [41 empty] | Cancelled by Proponent
GSD-24-012 | 24MO-03A9AN | Carpentry Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 7145 | 7145 |  | 4940 | 4940 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Awarded
GSD-24-013 | 24MO-03A9AN | Plumbing Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 12196 | 12196 |  | 9650 | 9650 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Awarded
GSD-24-014 | 24MO-03A9AN | Electrical Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4133.75 | 4133.75 |  | 3231 | 3231 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Awarded
GSD-24-015 | 24MO-08D1W | Aircon Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 34490.57 | 34490.57 |  | 33892 | 33892 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Awarded
SMO-24-016 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token | Goods & Services | GSM |  | 2024-03-01 | 4:15PM | 2024-04-25 | 55 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-22 | N/A | 2024-04-25 | N/A | 2024-04-25 | N/A | 30 days |  | COB | 275000 | 275000 |  | 215520 | 215520 |  | Jen Lin Corporate Giveaways | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298787 | Awarded | Awarded
PSD-24-017 | 24MO-038AC | Supply and Delivery of Fluquadri (Adult) | Goods & Services | RGV | 2024-02-19 | 2024-03-06 | 4:15PM | 2024-04-18 | 43 | PSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-16 | N/A | 2024-04-18 | N/A | 2024-04-23 | N/A | 15 days |  | COB | 85000 | 85000 |  | 61456 | 61456 |  | Pharma Quest Co. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298786 | Awarded | Awarded
PRM-24-018 | 24MO-03A2 | Supply and Delivery of Consolidated Office Forms for CY2024 | Goods & Services | GSM | 2024-02-29 | 2024-03-07 | 10:50AM |  | -45358 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 401287.7 | 401287.7 | [5 empty] | N/A | N/A | N/A | N/A | N/A | [13 empty] | Returned to End-User
PRM-24-019 | 24MO-03A1 | Supply and Delivery of Consolidated Computer Supplies for January-February 2024 | Goods & Services | GSM | 2024-02-12 | 2024-03-07 | 10:58AM |  | -45358 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 734811.81 | 734811.81 | [5 empty] | N/A | N/A | N/A | N/A | N/A | [13 empty] | For Rebidding
PRM-24-020 | 24MO-03A1 | Supply and Delivery of Consolidated Commonly-Use Supplies for January-February 2024 | Goods & Services | GSM | 2024-03-20 | 2024-03-11 | 2:30PM |  | -45362 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 333058.99 | 333058.99 | [5 empty] | N/A | N/A | N/A | N/A | N/A | [13 empty] | For Rebidding
PIP-24-021 | 24MO-07C5D | Hauling, Transport, Treatment and Disposal of Generated Hazardous wastes of PIP | Goods & Services | RGV | 2024-01-23 | 2024-03-14 | 9:16AM |  | -45365 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 137917 | 137917 | [5 empty] | N/A | N/A | N/A | N/A | N/A | [13 empty] | For Rebidding
SMO-24-022 | 24MO-09C1 | Supply, Delivery and Installation of Rental units of Multi-Functional Printers for PNOC Offices | Goods & Services | CFCM |  | 2024-03-18 | 10:03AM |  | -45369 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 800000 | 800000 | [23 empty] | Returned to End-User
PIP-24-023 | 24MO-06B6 | 2024 Environmental Monitoring (Waste Water-Effluent and Marine, Raw Water, Ambient Air Sampling and Laboratory Analysis) | Goods & Services | RGv | 2023-09-06 | 2024-03-22 | 10:09AM |  | -45373 | PIP | N | PB |  |  | 2024-04-11 | 2024-04-25 | 2024-04-25 | [8 empty] | COB | 825000 | 825000 | [23 empty] | Ongoing
SMO-24-024 | 24MO-03A8A3 | Supply and Delivery of Bamboo Stainless Cup | Goods & Services | CFCM |  | 2024-03-25 | 1:58PM | 2024-04-25 | 31 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-23 | N/A |  | N/A |  | N/A | 30 days | COB | COB | 90000 | 90000 | [23 empty] | Awarded
PIP-24-025 | 24MO-03A7C/08D1L | Supply and Delivery of Electrical Items(Batteries for Genset and Fire Engine) | Goods & Services | GSM | 2024-01-15 | 2024-03-25 | 2:37PM |  | -45376 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 195600 | FALSE | [23 empty] | Awarded
GSD-24-026 | 24MO-04A3 | 2024 Supply and Delivery of Drinking Water | Goods & Services | GSM | 2024-03-12 | 2024-04-04 | 9:03AM | 2024-04-23 | 19 | GSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A | 2024-04-19 | N/A | 2024-04-23 |  |  |  | May-December |  | COB | 212000 | 212000 |  | 176320 | 176320 |  | MSDR Water Refilling Station | [18 empty] | Awarded
SMO-24-027 | 24MO-09D15 | Supply and Delivery of Barcode Scanner | Goods & Services | GSM | 2024-04-04 | 2024-04-05 | 11:50AM |  | -45387 | SMO | N | NP-SVP | N/A | 2024-04-12 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 211000 | 211000 | [23 empty] | For Award
PSD-24-028 | 24MO-07C2 | 2024 Temporary Office Services | Goods & Services | RGV |  | 2024-04-11 |  | 2024-04-11 | 0 | PSD | N | AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-04-11 | 2024-04-11 |  |  | May-December |  | COB | 9500000 | 9500000 |  | 7464399.68 | 7464399.68 |  | LBP Resources Development Corporation | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Awarded
SMO-24-029 | 24MO-09D6 | Email Hosting Service Subscription | Goods & Services | RGV |  |  |  |  | 0 | SMO | N | PB | 2024-04-25 | [12 empty] | COB | 1800000 | 1800000 | [23 empty] | Ongoing
PSD-24-030 | 24CA-04A6 | Supply, Delivery, Installation and Implementation of Time and Attendance Monitoring System w/ 3 Biometric devices (facial recognition/finger scan) | Goods & Services | RGV | 2024-03-25 | 2024-04-19 | 1:08PM |  | -45401 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 800000 | 800000 | [23 empty] | Ongoing
GSD-24-031 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at G/Fr. Zone #1 Compressor#2 of PNOC Bldg.5 | Goods & Services | GSM | 2024-02-29 | 2024-04-18 | 11:17AM |  | -45400 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 161760 | 161760 | [23 empty] | Ongoing
GSD-24-032 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at 2nd/Flr. Zone #1 Compressor#2 of PNOC Bldg.5 | Goods & Services | GSM | 2024-01-25 | 2024-04-23 | 11:35AM |  | -45405 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 162720 | 162720 | [23 empty] | Ongoing
GSD-24-033 | 24MO-08D1AB | Rewind and Overhauling of 1 unit Aircon Compressor 10TR at 3rd/Flr. Zone #2 of PNOC Bldg.5 | Goods & Services | GSM | 2024-04-17 | 2024-04-23 | 9:20AM |  | -45405 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 161760 | 161760 | [23 empty] | Ongoing
CS-24-034 | Memo Realignment | Corporate Retreat and Planning of Board of Directors | Goods & Services | CFCM | 2024-04-22 | 2024-04-24 | 2:43PM |  | -45406 | CORSEC | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 400000 | 400000 | [23 empty] | Ongoing
GSD-24-035 | 24MO-08C2C | 2024 Pest Control Services for PNOC Building at Fort Bonifacio and PNOC Property in Tagaytay | Goods & Services | GSM | 2024-03-11 | 2024-04-05 | 9:41AM |  | -45387 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 81000 | 81000 | [23 empty] | Ongoing
PIP-24-036 | 24MO-08D1Q | Supply and Delivery of Lighting Panel Board | Goods & Services |  | 2024-01-31 | 2024-04-18 | 9:45AM |  | -45400 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 120000 | 120000 | [23 empty] | Ongoing
GSD-24-037 | 24MO-08D1X | Reconditioning /Rehabilitation of 900kW Caterpillar Genset Alternator at PNOC Bldg.5 | Goods & Services | CFCM | 2024-03-12 | 2024-04-19 | 2:33PM |  | -45401 | GSD | N | PB | [13 empty] | COB | 1755291.67 | 1755291.67 | [23 empty] | Ongoing
GSD-24-038 | 24CA-04D | Supply and Delivery of Interactive Flat Panel Display | Goods & Services |  | 2024-04-04 | 2024-04-23 | 9:52AM |  | -45405 | GSD | N | PB | [13 empty] | COB | 2300000 | 2300000 | [23 empty] | Ongoing
PRM-24-039 | 2MO-03A1 | Supply and Delivery of Consolidated Computer Supplies for January-February 2024 | Goods & Services |  | 2024-04-22 | 2024-04-26 | 1:15PM |  | -45408 | PRM | N | NP-SVP | [13 empty] | COB | 192335.62 | 192335.62 | [23 empty] | Ongoing
ESB-24-040 | 24MO-08D1D | 2024 PMS of Truck Scale (Quarterly Check-up and Calibration with ITDI Certificate) | Goods & Services |  | 2024-01-31 | 2024-04-25 | 4:31PM |  | -45407 | ESB | N | NP-SVP | [13 empty] | COB | 83000 | 83000 | [23 empty] | Ongoing
PIP-24-041 | 24MO-08D1S | Supply and Delivery of Consumables for Painting and Repair | Goods & Services |  | 2024-02-01 | 2024-04-26 | 11:30PM |  | -45408 | PIP | N | NP-SVP | [13 empty] | COB | 125472 | 125472 | [23 empty] | Ongoing
CANCELLED
PMD-24-010 | 24MO-08D1A | Repair of Printer - Epson L210 | Goods & Services | GSM | 2024-02-08 | 2024-02-13 | 1:30PM |  | -45335 | PMD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 2500 | [15 empty] | N/A | No bid | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
OP-24-008 | 24MO-08E1D | Repair of Expander NGS-5802 | Goods & Services | RGV | 2024-01-30 | 2024-02-08 | 9:00AM |  | -45330 | OP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 10000 | [22 empty] | Cancelled by proponent
PIP-24-011 | 24MO-09E10 | Supply and Delivery of Materials for 2024 Parkwide Coastal Clean Up | Goods & Services | GSM | 2024-01-29 | 2024-02-13 | 10:30AM |  | -45335 | PIP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 12000 | [16 empty] | Non Compliance | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
Formulas:
Date of BAC Reso Reco Award = [Date PR Awarded]

## PMR 2024 (2) (hidden)
| COMPANY: PHILIPPINE NATIONAL OIL COMPANY LOCATION: Bldg.6 Energy Center, Rizal Drive, BGC, Taguig SUBJECT: Procurement Monitoring |  |  |  |  | NOTE: 1.
[16 empty] | FAILED |  |  |  | ONGOING
[16 empty] | COMPLETED |  |  |  | AWARDED
#REF!
| AS OF: | 2024-10-16
PR NO. | Code (PAP) *from APP | Procurement Program/Project | Classification *Goods and Services, Infrastructure or Cosnulting Services | Account Officer *Initials | Date of PR | Date PR Received | Time Received | Date PR Awarded | TAT (days) | PMO/ End-User | Is this an Early Procurement Activity? Y/N | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Winning Bidder | List of Invited Observers | Date of Receipt of Invitation | [7 empty] | Submitted to COA |  | Reason of Failure |  |  |  |  | Payment Oder No./Contract No. | STATUS / REMARKS *Ongoing / Completed | STATUS as of today
[13 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf / Negotiation | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Reso Reco Award | Notice of Award | Contract Signing/ PO | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/Acceptance (if applicable) | Submission to IAO | Submission to OGC |  | Rebid |  | Date of Failure of Bidding | Date of Memo to Proponent (Failure of Bid) | Date Received Memo by Proponent | Date of Submitted CSS Form
ONGOING
SMO-24-001 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Energy Supply Base | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | February-December |  | COB | 608000 | 608000 |  | 555397.33 |  | 555397.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [11 empty] | Completed | Transmitted to End-User 2/20/24
SMO-24-002 | 24MO-05B1 | Internet Leased/Line Upgrade for PNOC Industrial Park | Goods & Services | RGV |  | 2023-11-21 | 1:48PM | 2024-01-16 | 56 | SMO | Y | PB | 2023-11-23 | 2023-11-28 | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-21 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-02-07 | 2024-01-29 | February-December |  | COB | 735000 | 735000 |  | 673647.33 |  | 673647.33 | Converge Information and Communicationsb Technology Solutions, Inc. | MBC, COA, PCCI | 2023-12-05 | 2023-12-19 | 2023-12-19 | 2023-12-20 | 2023-12-28 | [11 empty] | Completed | Transmitted to End-User 2/20/24
SMO-24-003 | 24MO-04A3 | PNOC Network Rehabilitation and Reconfiguration Project | Goods & Services | CFCM |  | 2024-01-15 | 2:53PM | 2024-03-14 | 59 | SMO | N | PB | 2024-01-23 | 2024-01-25 | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 2024-02-29 | 2024-03-14 | 2024-03-14 |  | 2024-04-05 | 90 days |  | COB | 4900000 | 4900000 |  | 4792565 |  | 4792565 | Pronet Systems Integrated Network Solution, Inc. | MBC, COA, PCCI | 2024-02-01 | 2024-02-15 | 2024-02-15 | 2024-02-16 | 2024-02-22 | [11 empty] | Awarded | Received Signed 3.15.24
SMO-24-004 | 24MO-04A2 | Supply and Delivery of Laptop Computers | Goods & Services | CFCM | 2023-12-18 | 2024-01-15 | 2:53PM | 2024-04-01 | 77 | SMO | N | NP-SVP | N/A | 2024-02-01 | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-28 | 2024-04-01 | 2024-04-01 | N/A | 2024-04-04 | N/A | 90 days |  | COB | 706000 | 706000 |  | 626690 |  | 626690 | Joneco Tech Marketing Corporation | MBC, COA, PCCI | 2024-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-29 | 2024-03-12 | [10 empty] | PO#298785 | Awarded | PO for Sign
GSD-24-005 |  | 2024 Security Services for PNOC Head Office | Goods & Services | RGV | 2024-01-09 | 2024-01-25 | 11:00AM |  | -45316 | GSD | N | PB | 2024-01-31 | 2024-02-06 | 2024-02-13 | 2024-03-07 | 2024-03-07 | 2024-03-26 | [7 empty] | COB | 10400000
SMO-24-006 | 24MO-06A1 | Consulting Services for the Digital Transformation Initiative of PNOC | Consulting Services | CFCM | 2024-01-22 | 2024-01-26 | 8:30AM | 2024-01-31 | 5 | SMO | N | AA | 2024-01-30 | N/A | N/A | N/A | N/A | N/A | N/A | 2024-01-31 | 2024-02-02 | 2024-03-11 | 2024-03-01 |  |  | COB | 4950000 | 4950000 |  | 4912969.56 | 4912969.56 |  | University of the Philippines | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded
PIP-24-007 | 24MO-08D1U | 2024 Preventive Maintenance of PNOC Gym Equipment | Goods & Services | GSM | 2024-01-31 | 2024-02-20 | 11:09AM | 2024-03-14 | -45342 | PRM | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-13 | N/A | 2024-03-14 | N/A | 2024-03-18 | N/A | Jan-Dec | COB | COB | 48000 | 48000 |  | 48000 | 48000 |  | The FitCo, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298783 | Awarded | Transmitted to End-User/04/01/24
GSD-24-009 | 24MO-03A9AN | Purchase of Materials for Fabrication of of Bed Frame | Goods & Services | GSM | 2024-01-25 | 2024-02-08 | 1:35PM | 2024-03-19 | 40 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4665 | 4665 |  | 3120 | 3120 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Transmitted to End-User/04/01/24
GSD-24-012 | 24MO-03A9AN | Carpentry Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 7145 | 7145 |  | 4940 | 4940 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Transmitted to End-User/04/01/24
GSD-24-013 | 24MO-03A9AN | Plumbing Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 12196 | 12196 |  | 9650 | 9650 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Transmitted to End-User/04/01/24
GSD-24-014 | 24MO-03A9AN | Electrical Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 4133.75 | 4133.75 |  | 3231 | 3231 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Transmitted to End-User/04/01/24
GSD-24-015 | 24MO-08D1W | Aircon Supplies | Goods & Services | GSM | 2024-02-12 | 2024-02-20 | 9:10AM | 2024-03-19 | 28 | GSD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A | 2024-03-15 | N/A | 2024-03-19 | N/A | 2024-03-25 | N/A | 30 days |  | COB | 34490.57 | 34490.57 |  | 33892 | 33892 |  | Viva Sales Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298784 | Awarded | Transmitted to End-User/04/01/24
SMO-24-016 | 24MO-03A8A3 | Supply and Delivery of Corporate Give-Aways/Token | Goods & Services | GSM |  | 2024-03-01 | 4:15PM |  | -45352 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 275000 | 275000
PSD-24-017 | 24MO-038AC | Supply and Delivery of Fluquadri (Adult) | Goods & Services | RGV | 2024-02-19 | 2024-03-06 | 4:15PM |  | -45357 | PSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 85000 | 85000
PRM-24-018 | 24MO-03A2 | Supply and Delivery of Consolidated Office Forms for CY2024 | Goods & Services | GSM | 2024-02-29 | 2024-03-07 | 10:50AM |  | -45358 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 401287.7 | 401287.7
PRM-24-019 | 24MO-03A1 | Supply and Delivery of Consolidated Computer Supplies for January-February 2024 | Goods & Services | GSM | 2024-02-12 | 2024-03-07 | 10:58AM |  | -45358 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 734811.81 | 734811.81
PRM-24-020 | 24MO-03A1 | Supply and Delivery of Consolidated Commonly-Use Supplies for January-February 2024 | Goods & Services | GSM | 2024-03-20 | 2024-03-11 | 2:30PM |  | -45362 | PRM | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 333058.99 | 333058.99
PIP-24-021 | 24MO-07C5D | Hauling, Transport, Treatment and Disposal of Generated Hazardous wastes of PIP | Goods & Services | RGV | 2024-01-23 | 2024-03-14 | 9:16AM |  | -45365 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 137917 | 137917
SMO-24-022 | 24MO-09C1 | Supply, Delivery and Installation of Rental units of Multi-Functional Printers for PNOC Offices | Goods & Services | CFCM |  | 2024-03-18 | 10:03AM |  | -45369 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 800000 | 800000
PIP-24-023 | 24MO-06B6 | 2024 Environmental Monitoring (Waste Water-Effluent and Marine, Raw Water, Ambient Air Sampling and Laboratory Analysis) | Goods & Services | RGv | 2023-09-06 | 2024-03-22 | 10:09AM |  | -45373 | PIP | N | PB | [13 empty] | COB | 825000 | 825000
SMO-24-024 | 24MO-03A8A3 | Supply and Delivery of Bamboo Stainless Cup | Goods & Services | CFCM |  | 2024-03-25 | 1:58PM |  | -45376 | SMO | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 90000 | 90000
PIP-24-025 | 24MO-03A7C/08D1L | Supply and Delivery of Electrical Items(Batteries for Genset and Fire Engine) | Goods & Services | GSM | 2024-01-15 | 2024-03-25 | 2:37PM |  | -45376 | PIP | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 195600 | 195600
GSD-24-026 | 24MO-04A3 | 2024 Supply and Delivery of Drinking Water | Goods & Services | GSM | 2024-03-12 | 2024-04-04 | 9:03AM |  | -45386 | GSD | N | NP-SVP | N/A | 2024-04-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 212000 | 212000
SMO-24-027 | 24MO-09D15 | Supply and Delivery of Barcode Scanner | Goods & Services |  | 2024-04-04 | 2024-04-05 | 11:50AM |  | -45387 | SMO | N | NP-SVP | N/A
0
0
AWARDED
CANCELLED
PMD-24-010 | 24MO-08D1A | Repair of Printer - Epson L210 | Goods & Services | GSM | 2024-02-08 | 2024-02-13 | 1:30PM |  | -45335 | PMD | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 2500 | [15 empty] | N/A | No bid | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
OP-24-008 | 24MO-08E1D | Repair of Expander NGS-5802 | Goods & Services | RGV | 2024-01-30 | 2024-02-08 | 9:00AM |  | -45330 | OP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 10000 | 10000 | [21 empty] | Cancelled by proponent
PIP-24-011 | 24MO-09E10 | Supply and Delivery of Materials for 2024 Parkwide Coastal Clean Up | Goods & Services | GSM | 2024-01-29 | 2024-02-13 | 10:30AM |  | -45335 | PIP | N | NP-SVP | N/A | 2024-03-05 | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  | COB | COB | 12000 | [16 empty] | Non Compliance | 2024-03-11 | 2024-03-11 | 2024-03-12 |  |  | Cancelled by proponent
Formulas:
Date of BAC Reso Reco Award = [Date PR Awarded]

## PMR 2023(3rdQTR) (hidden)
| COMPANY: PHILIPPINE NATIONAL OIL COMPANY LOCATION: Bldg.6 Energy Center, Rizal Drive, BGC, Taguig SUBJECT: Procurement Monitoring |  |  |  |  | NOTE: 1.
[16 empty] | FAILED |  |  |  | ONGOING
[16 empty] | COMPLETED |  |  |  | AWARDED
#REF!
| AS OF: | 2024-10-16
PR NO. | Code (PAP) *from APP | Procurement Program/Project | Classification *Goods and Services, Infrastructure or Cosnulting Services | Account Officer *Initials | Date of PR | Date PR Received | Time Received | Date PR Awarded | TAT (days) | PMO/ End-User | Is this an Early Procurement Activity? Y/N | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | Winning Bidder | List of Invited Observers | Date of Receipt of Invitation | [7 empty] | Submitted to COA |  | Reason of Failure |  |  |  |  | Payment Oder No./Contract No. | STATUS / REMARKS *Ongoing / Completed | STATUS as of today
[13 empty] | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf / Negotiation | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Reso Reco Award | Notice of Award | Contract Signing/ PO | Notice to Proceed | Delivery/ Completion | Acceptance/ Turnover |  | Total | MOOE | CO | Total | MOOE | CO |  |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/Acceptance (if applicable) | Submission to IAO | Submission to OGC |  | Rebid |  | Date of Failure of Bidding | Date of Memo to Proponent (Failure of Bid) | Date Received Memo by Proponent | Date of Submitted CSS Form
GSD-23-001 | 23MO-06B14 | Contract Services for the Preventive Maintenance of Two (2) Units Passenger Elevator at PNOC Bldg.6 for 2023 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-30 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | 2023-01-03 |  | 2023-02-23 | Mar-Dec |  | COB | 185327.09 |  |  | 192757.8 | 192757.8 |  | KPI Elevators,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st - Over ABC | 2022-11-28 | 2022-11-28 | 2022-11-29 | 2023-01-31 | Contract #23-047 | Awarded | Contract for Notary
GSD-23-002 | 23MO-06B18 | Contract Services for the Preventive Maintenance of CCTV Surveillance System at PNOC Bldg.6, 5, Computer Bldg. & Compound Perimeter | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-27 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | N/A | 2023-01-03 | N/A |  |  | COB | 89888.04 | 89888.04 |  | 66666.67 | 66666.67 |  | Comparts Computer Sales | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | 2023-01-31 | PO#298646 | Awarded | Completed/Delivered
GSD-23-003 | 23MO-06B16 | Contract Services for the Maintenance of Fire Protection System at PNOC Bldg. 5&6 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-27 | N/A | N/A | N/A | 2022-12-13 | N/A | 2022-12-15 | 2023-01-03 |  | 2023-02-20 |  |  | COB | 333900 |  |  | 310000 | 310000 |  | Lubricks Maintenance and Construction | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | 2023-01-31 | Contract #23-017 | Awarded | Completed/Delivered
GSD-23-004 | 23MO-06B15 | Contract Services for the Preventive Maintenance of Two (2) Units Passenger Elevator at PNOC Bldg.5 | Goods & Services | GSM | 2022-06-30 | 2022-10-18 | 1:36PM | 2022-12-20 | 63 | GSD | Y | NP-SVP | N/A | 2022-10-28 | N/A | N/A | N/A | 2022-12-16 | N/A | 2022-12-20 | 2023-01-03 |  | 2023-02-23 |  |  | COB | 139920 |  |  | 132000 | 132000 |  | Rockspeed Elevator and Escalator Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-005 | 23MO-06B17 | Contract Services for the Water Chemical Treatment for PNOC Bldg. 5&6 | Goods & Services | CDBB | 2022-07-01 | 2022-10-18 | 3:11PM | 2022-12-15 | 58 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-12-15 | 2023-01-10 |  | 2023-01-30 | Jan-Dec |  | COB | 400898.8 |  |  | 308040 | 308040 |  | Impact One Nation Industrial Corp. | [7 empty] | 2023-02-08 | 2023-02-08 | 2023-02-08 |  | 1st - Non Compliance | 2022-11-15 | 2022-11-15 | 2022-11-15 | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-006 | 23MO-05C13 | Rental of Photocopying Machines for the year 2023 for PNOC Offices @ BGC, Taguig City, ESB & PIP | Goods & Services | GSM | 2022-07-07 | 2022-10-18 | 1:00PM | 2022-11-29 | 42 | GSD | Y | NP-SVP | N/A | 2022-11-27 | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-11-29 | 2023-01-03 | 2023-03-15 | 2023-02-23 | Jan-Dec |  | COB | 680000 | 680000 |  | 639000 | 639000 |  | Photopro Trading & General Merchandise Co. | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-04-12 | [5 empty] | 2023-01-31 | Contract #23-018 | Awarded | Completed/Delivered
GSD-23-007 | 23MO-02A | Supply and Delivery of Drinking Water | Goods & Services | HDVE | 2022-06-25 | 2022-10-18 | 2:51PM | 2022-11-22 | 35 | GSD | Y | NP-SVP | N/A | 2022-10-29 | N/A | N/A | N/A | 2022-11-08 | N/A | 2022-11-22 | 2023-01-04 | 2023-01-25 | 2023-01-18 | Mar-Dec |  | COB | 360000 | 360000 |  | 278400 | 278400 |  | MSDR Water Refilling Station | [9 empty] | 2023-01-26 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-008 | 23MO-07D8 | 2023 Web Hosting and Maintenance for Document Tracking System | Goods & Services | CDBB | - | 2022-10-18 | 2:51PM | 2022-11-08 | 21 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-04 | N/A | 2022-11-08 | 2023-01-09 | 2023-01-30 | 2023-01-24 | Mar-Dec |  | COB | 239000 | 239000 |  | 238000 | 238000 |  | MYBUSYBEE INC. | N/A | N/A | N/A | N/A | N/A | N/A |  | 2023-02-03 | 2023-02-03 | 2023-02-03 | N/A | N/A | N/A | N/A | N/A | 2023-01-31 | 23-002 | Awarded | Completed/Delivered
GSD-23-009 | WOR | 2023 Messengerial Services | Goods & Services | HDVE | 2022-06-28 | 2022-10-18 | 2:51PM | 2022-12-20 | 63 | GSD | Y | PB | 2022-10-25 | 2022-10-28 | 2022-11-11 | 2022-11-24 | 2022-11-24 | 2022-12-06 | 2022-12-20 | 2022-12-20 | 2022-01-09 | 2023-01-24 | 2023-01-18 | Jan-Dec |  | COB | 2666000 | 2666000 |  | 2592831.24 | 2592831.24 |  | PRC Couirier & Maintenance Services | MBC, COA, PCCI | [7 empty] | 2023-01-25 | 2023-01-27 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-010 | 23MO-06H2 | Pest Control Services | Goods & Services | CDBB |  | 2022-10-18 |  | 2022-11-08 | 21 | GSD | Y | NP-SVP | N/A | 2022-10-25 | N/A | N/A | N/A | 2022-11-02 | N/A | 2022-11-08 | 2023-01-09 | N/A | N/A | Jan-Dec |  | COB | 103824 | 103824 |  | 100800 | 100800 |  | Rampest Control Services and Supplies Company | [9 empty] | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298647 | Awarded | Completed/Delivered
ESB-23-011 | 23MO-05C12 | Preventive Maintenance of Truck Scale (Quarterly Check up and Calibration with ITDI Certificate) | Goods & Services | CDBB | 2022-07-11 | 2022-10-18 |  | 2022-11-22 | 35 | ESB | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-21 | N/A | 2022-11-22 | N/A | 2023-01-10 | N/A | 30 days |  | COB | 83000 | 83000 |  | 83000 | 83000 |  | GCH International Mercantile, Inc. | [9 empty] | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298650 | Awarded | Completed/Delivered
GSD-23-012 | 23MO-05A | Janitorial Services | Goods & Services | CFCM | 2022-07-06 | 2022-10-18 | 8:55AM | 2023-01-17 | 91 | GSD | Y | PB | 2022-11-08 | 2022-11-15 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2022-12-21 | 2023-01-12 | 2023-01-17 | 2023-01-18 |  | 2023-02-27 | Jan-Dec |  | COB | 8680000 | 8680000 |  | 8453970.56 | 8453970.56 |  | Starcom Manpower and Allied Services | MBC, COA, PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 |  |  |  | 2023-05-08 | [7 empty] | Awarded | Completed/Delivered
GSD-23-013 | 23MO-05C7 | Maintenance Services | Goods & Services | CFCM | 2022-07-22 | 2022-10-18 | 3:50PM | 2023-01-17 | 91 | GSD | Y | PB | 2022-11-08 | 2022-11-16 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2022-12-21 | 2023-01-12 | 2023-01-17 | 2023-01-18 |  |  | Jan-Dec |  | COB | 3627000 | 3627000 |  | 3605545.91 | 3605545.91 |  | Servicio Filipino,Inc. | MBC, COA, PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [5 empty] | N/A | N/A | N/A | N/A | 2023-01-31 |  | Awarded | Completed/Delivered
ESB-23-014 | 23MO-04A3 | Engagement of 3rd party Laboratory Service provider to conduct Quarterly Ambient Air Monitoring And Raw Water Testing | Goods & Services | HDVE | 2022-08-10 | 2022-10-18 | 2:10PM | 2022-11-14 | 27 | ESB | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-07 | N/A | 2022-11-14 | 2023-01-06 | Contract draft |  | Mar-Dec |  | COB | 228000 |  |  | 221760 | 221760 |  | Berkman Systems,Inc. | [9 empty] | 2023-03-06 | [5 empty] | 2023-01-31 |  | Awarded | Completed/Delivered
GSD-23-015 | Awaiting APP | 2023 Caretaker Services- Tagaytay Property | Goods & Services | GSM | 2022-07-22 | 2023-03-07 | 9:20AM |  | -44992 | GSD | Y | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A | Jan-Dec |  | COB | 527000 | [6 empty] | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | 2023-03-07 | 1st - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 | 2nd - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 | 3rd - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 | 4th - 11/21/23 ,2nd- 3/27/23,3rd-4/27/23 |  |  |  | Cancelled
AM-23-016 | 23MO-06H2 | 2023 Pest Control Services - PNOC Staffhouse, Lamo,Limay, Bataan | Goods & Services | CDBB | 2022-08-23 | 2022-10-18 | 9:05AM | 2022-11-14 | 27 | AMD | Y | NP-SVP | N/A | 2022-10-26 | N/A | N/A | N/A | 2022-11-08 | N/A | 2022-11-14 | N/A | 2023-01-09 | N/A | Jan-Dec |  | COB | 45000 | 45000 |  | 34000 | 34000 |  | RAM Pest Control Services & Supplies Phils. Co. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-10 | [5 empty] | 2023-01-31 | PO#298648 | Awarded | Completed/Delivered
AM-23-017 | Awaiting APP | 2023 Caretaker Services- Staffhouse, Lamao, Limay, Bataan | Goods & Services | HDVE | 2022-09-02 | 2022-10-18 | 9:05AM | 2023-01-05 | 79 | AMD |  | NP-SVP | N/A | 2022-12-16 | N/A | N/A | N/A | [8 empty] | COB | 322700 | 322700 | [23 empty] | Cancelled
PIP-23-018 | 23MO-05C7 | Provision for Manpower for 2023 Custodial Services/Other General Services at PIP | Goods & Services | CFCM | 2022-08-23 | 2022-10-18 | 1:21PM | 2023-02-06 | 111 | PIP | Y | PB | 2022-11-22 | 2022-11-15 | 2022-11-22 | 2022-12-06 | 2022-12-06 | 2023-12-27 | 2023-01-31 | 2023-02-06 | 2023-02-14 |  | 2023-02-27 | Mar-Dec |  | COB | 3794718.27 | 3794718.27 |  | 3794718.27 | 3794718.27 |  | Servicio Filipino, Inc. | MBC,COA,PCCI | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 | [11 empty] | Awarded | Completed/Delivered
AM-23-019 | Awaiting APP | Security Services for PNOC Provincial Properties | Goods & Services | RGV | 2022-08-31 | 2022-10-18 | 2:19PM | 2022-12-20 | 63 | AMD | Y | PB | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-11-15 | 2022-11-15 | 2022-12-19 | 2022-12-19 | 2022-12-20 | 2023-01-26 | 2023-02-20 | 2023-02-15 | Jan-Dec |  | COB | 6188770.36 | 6188770.36 |  | 5941511.28 | 5941511.28 |  | Eliteblue Security Specialists | MBC,COA,PCCI | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 |  | 2023-02-20 | 2023-02-20 | 2023-02-20 | [5 empty] | 2023-01-31 | Contract#23-012 | Awarded | Completed/Delivered
GSD-23-020 | 23MO-05B | Security Services for Head Office, PIP &ESB | Goods & Services | RGV | 2022-08-15 | 2022-10-18 | 9:16PM | 2023-01-12 | 86 | GSD | Y | PB | 2022-10-20 | 2022-10-27 | 2022-11-03 | 2022-11-15 | 2022-11-15 | 2022-12-06 | 2023-01-05 | 2023-01-12 | 2023-01-26 | 2023-02-20 | 2023-02-20 | Jan-Dec |  | COB | 48611344.64 | 48611344.64 |  | 47781296.28 | 47781296.28 |  | Eliteblue Security Specialists | MBC,COA,PCCI | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 | 2022-10-24 |  | 2023-03-20 | 2023-03-20 | 2023-03-20 | [5 empty] | 2023-01-31 | Contract #23-007/008/009 | Awarded | Completed/Delivered
ESB-23-021 | 23MO-05A | 2023 Custodial and Janitorial Services | Goods & Services | CFCM | 2022-09-14 | 2022-10-18 | 3:40PM | 2023-01-12 | 86 | ESB | Y | PB | 2022-11-03 | 2022-11-08 | 2022-11-15 | 2022-11-29 | 2022-11-29 | 2022-12-21 | 2023-01-12 | 2023-01-12 | 2023-01-31 |  | 2023-02-20 | Jan-Dec |  | COB | 7530000 | 7530000 |  | 7451165.35 | 7451165.35 |  | Stewards Manpower Supply and Services | MBC,COA,PCCI | 2022-10-15 | 2022-10-15 | 2022-10-15 | 2022-10-15 | 2022-10-15 |  | 2023-05-05 | 2023-05-05 | 2023-05-05 | [5 empty] | 2023-01-31 | Contract #23-014 | Awarded | Abstract Routing 1.12.23
PIP-23-022 | 23MO-05A | Supply of Manpower,Equipment and Supplies for Janitorial Services at PIP | Goods & Services | CFCM | 2022-08-23 | 2022-10-18 | 3:25PM | 2023-02-13 | 118 | PIP | Y | PB | 2022-11-17 | 2022-11-22 | 2022-11-29 | 2022-12-13 | 2022-12-13 | 2022-12-27 | 2023-01-31 | 2023-02-13 | 2023-02-20 | 2023-02-28 | 2023-02-28 | Mar-Dec |  | COB | 4304703.82 |  |  | 3263405.9 | 3263405.9 |  | Servicio Filipino,Inc. | MBC,COA,PCCI | [15 empty] | Contract#23-021 | Awarded | Completed/Delivered
PIP-23-023 | 23CA-06A | Supply,Delivery, Testing and Commissioning of Brand New Fire Truck | Goods & Services | CFCM | 2022-10-05 | 2023-01-13 | 9:21AM | 2023-04-20 | 97 | PIP | Y | PB | 2023-01-19 | 2023-01-24 | 2023-01-31 | 2023-02-14 | 2023-02-14 | 2023-02-20 | 2023-03-30 | 2023-03-30 | 2023-04-27 | 2023-06-22 | 2023-06-19 | 180 days |  | COB | 29200000 |  | 29200000 | 28888888 |  | 28888888 | Boston Home Incorporated | MBC,COA,PCCI | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-01-31 | [5 empty] | 1st - Non Compliance | 2023-01-10 | 2023-01-11 | 2023-01-12 |  | Contract#23-039 | Awarded | Completed/Delivered
PIP-23-024 | 23MO-04A3 | Environmental Monitoring for 2023 (Waste Water-Effluent and Marine, Raw Water, Ambient Air Sampling and Laboratory Analysis | Goods & Services | CDBB | 2022-10-20 | 2023-01-19 | 5:01PM | 2023-03-16 | 56 | PIP | Y | PB |  |  | 2022-11-15 | 2023-01-05 | 2023-01-05 | 2023-01-09 |  | 2023-03-16 | 2023-03-16 | 2023-05-12 | 2023-03-21 | 1st -4th QTR |  | COB | 1032026.6 | 1032026.6 |  | 1002400 | 1002400 |  | CRL Environmental Corporation | [7 empty] | 2023-05-19 | 2023-05-19 | 2023-05-19 | 2022-12-12 | 1st-Non Comliance in Philgeps/2nd-Non-compliant in tech specs | 1st -12/2/2022/ 2nd- 1/17/2023 | 1st-12/2/2022 | 1st-12/5/22 |  | Contract #23-023 | Awarded | Completed/Delivered
PP-23-025 | Awaiting APP | Preventive Maintenance of PNOC Gym Equipment | Goods & Services | CDBB | 2022-10-17 | 2022-11-03 | 11:27AM |  | -44868 | PP | Y | NP-SVP | N/A |  | N/A | N/A | N/A | N/A | N/A |  | N/A |  | N/A |  |  | COB | 59000 | [17 empty] | 1st&2nd- Non receipt of quotation/ | 1st- 11/15/222nd -12/1/2022 | 1st- 11/15/222nd -12/1/2022 | 1st- 11/15/222nd -12/2/2022 |  |  |  | Failed/Returned to End user 11.15.22
AM-23-026 | Awaiting APP | 2023 Caretaker Services- Staffhouse, Lamao, Limay, Bataan | Goods & Services | HDVE | 2022-11-23 | 2022-11-28 | 8:55AM | 2023-01-05 | 38 | AMD | Y | NP-SVP | N/A | 2022-12-16 | N/A | N/A | N/A |  | 2022-12-21 | 2023-01-05 | 2023-01-10 | 2023-02-14 | 2023-01-25 |  |  | COB | 322700 | 322700 |  | 320612.06 | 320612.06 |  | MMA Competent Manpower and General Services | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-02-23 | 2023-02-23 | 2023-02-23 | [5 empty] | 2023-01-31 | Contract#23-006 | Awarded` | Completed/Delivered
SM-23-027 | 23MO-03AA | 2023 PNOC Internet/Leased Line Connection Upgrade | Goods & Services | CFCM | 2022-11-18 | 2022-11-28 | 8:45AM | 2023-01-26 | 59 | SMO | Y | PB |  | 2022-12-06 | 2022-12-13 | 2022-12-27 | 2022-12-27 | 2023-01-05 | 2023-01-24 | 2023-01-26 | 2023-01-31 | 2023-02-17 | 2023-02-13 | Mar-Dec |  | COB | 1300000 | 1300000 |  | 610980 | 610980 |  | Source Telecommunications, Inc. | MBC,PCCI, COA | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 |  | 2023-05-17 | 2023-05-17 | 2023-05-17 | [5 empty] | 2023-01-31 | Contract #23-013 | Awarded | Completed/Delivered
PP-23-028 | 23MO-06C10 | Preventive Maintenance of PNOC Gym Equipment | Goods & Services | CDBB | 2022-12-07 | 2022-12-07 | 4:25PM | 2022-12-22 | 15 | PP | Y | NP-SVP | N/A | 2022-12-14 | N/A | N/A | N/A | 2022-12-20 | N/A | 2022-12-22 | N/A | 2023-01-09 | N/A | Jan-Dec |  | COB | 65000 | 65000 |  | 28800 | 28800 |  | The FITCO Inc (Stark Fitness) | [9 empty] | 2023-01-10 |  | Superceded of PP-22-025 |  |  |  | 2023-01-31 | PO#298649 | Awarded | Completed/Delivered
PIP-23-029 | 23MO-01F131 | Supply and Delivery of 2023 Vehicle Sticker for PIP | Goods & Services | GSM | 2022-12-22 | 2022-01-03 | 1:30PM | 2023-02-14 | 407 | PIP | N | NP-SVP | N/A | 2023-01-23 | N/A | N/A | N/A | 2023-02-07 | N/A | 2023-02-14 | N/A | 2023-02-15 | N/A | 30 Days |  | COB | 9000 | 9000 |  | 6712.5 | 6712.5 |  | Forms International Enterprises,Corp. | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-03-27 | [6 empty] | PO#298654 | Awarded | Completed/Delivered
ESB-23-030 | Awaiting APP | Supply and Delivery of Various Tires for ESB | Goods & Services |  | 2023-01-03 | 2023-01-05 | 9:20AM |  | -44931 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 66000 | [24 empty] | returned to end-user 1.9.22 thru memo - Emailed by RGV/ over ABC
PSD-23-031 | 23MO-07EB | Supply and Delivery of PNOC's 50th Anniversary T-shirt | Goods & Services | GSM | 2023-12-21 | 2023-01-11 | 10:41AM | 2023-02-09 | 29 | PSD | N | NP-SVP | N/A | 2023-01-17 | N/A | N/A | N/A | 2023-01-31 | N/A | 2023-02-09 | N/A | 2023-02-14 | N/A | 30 days |  | COB | 84000 | 84000 |  | 73500 | 73500 |  | Topsol Enterprises | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-08-31 | [6 empty] | PO#298652 | Awarded | Completed/Delivered
SM-23-032 | 23MO-041D | Hiring of Certifying Body for PNOC QMS and Recertification | Consulting Services | CDBB | 2023-01-16 | 2023-01-12 | 10:55AM | 2023-05-16 | 124 | SMO | N | NP-SVP | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-05-12 | N/A | 2023-05-16 | N/A | 2023-05-18 | N/A |  |  | COB | 300000 | 300000 |  | 748440 | 748440 |  | SOCOTEC Certification Philippines,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st -2nd - Non Receipt of Quotation | 2nd : 4/19/2023 | 2nd : 4/19/2023 | 2nd : 4/19/2023 |  | Contract#23-036 | Awarded | Completed/Delivered
ESB-23-090 | 23MO-04B1C | Hiring of Certifying Body for PNOC ESB ISO 9001:2015 and ISO 45001:2018 and Recertification | Consulting Services | CDBB | 2023-01-16 | 2023-03-03 | 3:20PM | 2023-05-16 | 74 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | 2023-05-16 | N/A |  | N/A |  |  | COB | 500000 | 500000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Completed/Delivered
ESB-23-033 | 23MO-06D5 | Supply and Delivery of Various Tires for ESB | Goods & Services | GSM | 2023-01-03 | 2023-01-13 | 9:26AM | 2023-02-06 | 24 | ESB | N | NP-SVP | N/A | 2023-01-17 | N/A | N/A | N/A | 2023-01-25 | N/A | 2023-02-06 | N/A | 2023-02-08 | N/A | 30 days |  | COB | 66000 | 66000 |  | 55300 | 55300 |  | Fleetserv Inc. | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-03-03 | [6 empty] | PO#298651 | Awarded | Completed/Delivered
PIP-23-034 | 23CA-03C2 | Replacement of Fire Engine for Jetty and Controls - 1 Unit | Goods & Services | CDBB | 2023-01-05 | 2023-05-31 | 10:01AM |  | -45077 | PIP | N | PB | 2023-01-19 | 2023-01-24 | 2023-01-31 | 2023-02-14 | 2023-02-14 | [8 empty] | COB | 22150000 |  | 22150000 | [15 empty] | 1st-Non-submission of bid | 2023-02-14 | 2023-02-14 |  |  |  |  | Waiting for Update from PIP
PIP-23-035 | 23MO-04A2 | Hiring of EIA Report Consultant | Consulting Services | HDVE | 2023-01-11 | 2023-01-16 | 9:08AM | 2023-01-24 | 8 | PIP | N | NP-HT | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-25 | 2023-04-13 | 2023-03-31 |  |  | COB | 170000 | 170000 |  | 170000 | 170000 |  | Engr.Aldwin Camance | [7 empty] | 2023-04-13 | 2023-04-13 | 2023-04-13 | [5 empty] | 2023-01-31 | Contract #23-011 | Awarded | Completed/Delivered
ESB-23-036 | 23CA-01C | Upgrade and Improvement of Drainage System | Infrastructure | RGV | 2023-01-10 | 2023-01-17 | 1:23PM | 2023-03-14 | 56 | ESB | N | PB | 2023-01-24 | 2023-01-26 | 2023-02-02 | 2023-02-16 | 2023-02-16 | 2023-02-21 | 2023-03-13 | 2023-03-14 | 2023-03-15 |  | 2023-05-04 | 180 days |  | COB | 4550000 |  | 4550000 | 4532619.06 |  | 4532619.06 | RM Joyce Construction | [16 empty] | Contract #23-022 | Awarded | Completed/Delivered
SM-23-037 | 23MO-07E11 | Publication of the 50th Commemorative Book | Goods & Services | CFCM | 2023-01-18 | 2023-01-18 | 3:40PM | 2023-02-14 | 27 | SMO | N | NP-SVP | N/A | 2023-01-27 | N/A | N/A | N/A | 2023-02-08 | N/A | 2023-02-14 | 2023-02-15 | 2023-03-13 | 2023-03-08 | September |  | COB | 1000000 | 1000000 |  | 978000 | 978000 |  | VJ Graphics Arts,Inc. | [7 empty] | 2023-05-22 | 2023-05-22 | 2023-05-22 |  |  | n |  |  |  |  | Awarded
PIP-23-038 | 23MO-04A6 | Assessment of Jetty Facility and Hydrographic Survey | Consulting Services | RGV | 2023-01-19 | 2023-01-19 | 2:08PM | 2023-03-28 | 68 | PIP | N | PB |  | 2023-02-21 | 2023-02-28 | 2023-03-09 | 2023-03-09 | 2023-03-20 | n/A | 2023-03-28 | 2023-03-28 | 2023-05-10 | 2023-05-03 | 120 days |  | COB | 4800000 | 4800000 |  | 4799984 | 4799984 |  | A.C. Ong Consulting. Inc. | [7 empty] | 2023-05-12 | 2023-05-12 | [7 empty] | Contract #23-026 | Awarded | Completed/Delivered
PIP-23-039 | 23MO-05C9 | Annual Physical Examination (APE) for PIP | Goods & Services | GSM | 2023-01-19 | 2023-01-23 | 10:12AM | 2023-02-21 | 29 | PIP | N | NP-SVP | N/A | 2023-01-26 | N/A | N/A | N/A | 2023-02-15 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 95000 | 95000 |  | 44227.5 | 44227.5 |  | EDGT-LAB-Tech Diagnostic Center | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-03-07 | [6 empty] | PO#298658 | Awarded | Completed/Delivered
AS-23-040 | 23MO-041B1U | Hiring of Musical Director for 2023 | Goods & Services | HDVE |  | 2023-01-24 |  | 2023-01-24 | 0 | ASD | N | NP-SVP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-01-24 | 2023-01-26 | 2023-03-10 | 2023-01-31 | Feb-Dec |  | COB | 420000 | 420000 |  | 385000 | 385000 |  | Anthony Go Villanueva | [9 empty] | 2023-03-13 | [5 empty] | 2023-01-31 | #23-015 | Awarded | Completed/Delivered
PIP-23-041 | 23CA-01B | Fencing of Alberba Area (250m Length) | Infrastructure | CDBB | 2023-01-04 | 2023-01-24 | 3:14PM | 2023-04-25 | 91 | PIP | N | PB | N/A | 2023-01-31 | 2023-02-07 | 2023-02-21 | 2023-02-21 | 2023-04-04 | 2023-04-25 | 2023-04-25 | 2023-04-26 | 2023-05-30 | 2023-05-29 | 30 days |  | COB | 3460000 |  | 3460000 | 3074702.15 | 3074702.15 |  | AR. Esbi Construction | MBC,COA,PCCI | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | [10 empty] | 23-032 | Awarded | For Signing of NOA/Contract Draft
ESB-23-042 | 23MO-01H2A | Supply, Delivery and Printing of Calling Cards (CBP) | Goods & Services | GSM | 2023-01-16 | 2023-01-31 | 2:30PM | 2023-02-21 | 21 | ESB | N | NP-SVP | N/A | 2023-02-06 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 3000 | 3000 |  | 2550 | 2550 |  | Forms International Enterprises Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298659 | Awarded | Completed/Delivered
PIP-23-043 | 23CA-04B3 | Supply, Delivery and Installation of Load Break Switch | Goods & Services | GSM | 2023-01-10 | 2023-01-30 | 8:49AM | 2023-02-28 | 29 | PIP | N | NP-SVP | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-02-21 | N/A | 2023-02-28 | 2023-03-01 |  | 2023-04-26 |  |  | COB | 489000 |  | 489000 | 439000 |  | 439000 | Pablo S. Labasbas Construction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #23-028 | Awarded | Completed/Delivered
PSD-23-044 | 23MO-01D | Supply and Delivery of COVID Supplies (Face Mask) for MAR-JUN | Goods & Services | CDBB | 2023-01-30 | 2023-01-31 | 2:30PM | 2023-02-14 | 14 | PSD | N | NP-SVP | N/A | 2023-02-01 | N/A | N/A | N/A | 2023-02-09 | N/A | 2023-02-14 | N/A | 2023-02-15 | N/A |  |  | COB | 40000 | 40000 |  | 37584 | 37584 |  | SGS Healthcare Co. | [9 empty] | 2023-02-17 | [6 empty] | PO#298653 | Awarded | Completed/Delivered
PP-23-045 | 23MO-01H2B | Supply and Delivery Various Tissue | Goods & Services | CDBB | 2023-02-01 | 2023-02-02 | 11:03AM | 2023-02-16 | 14 | PRM | N | NP-SVP | N/A | 2023-02-03 | N/A | N/A | N/A | 2023-02-14 | N/A | 2023-02-16 | N/A | 2023-02-17 | N/A |  |  | COB | 19076 | 19076 |  | 18600 | 18600 |  | Eco-Hygiene Institutional Sals Corp/Sanitary Care Products Asia,Inc. | [9 empty] | 2023-02-20 | [6 empty] | PO#298656/PO#298657 | Awarded | Completed/Delivered
ESB-23-046 | 23CA-MYB1A | Flattening of the Hilly Area | Infrastructure | RGV | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | 2023-06-15 | 2023-06-20 | 2023-06-27 | 2023-07-11 | 2023-07-11 | [8 empty] | COB | 53540000 |  | 53540000 |  |  |  |  | COA,MBC,PCCI, PCA | 2023-06-19 | 2023-06-19 | 2023-06-19 | 2023-06-19 | [13 empty] | For Rebidding
ESB-23-047 | 23CA-MYB3A1 | Construction of New Pier | Infrastructure | RGV | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | 2023-03-14 | 2023-04-20 | 2023-04-27 | 2023-06-01 | 2023-06-01 | [8 empty] | COB | 1492039036 |  | 1492039036.17 |  |  |  |  | COA,MBC,PCCI, PCA | 2023-04-22 | 2023-04-22 | 2023-04-22 | 2023-04-22 | [13 empty] | Ongoing - Post Qualification
ESB-23-048 | 23CA-MYB3A2 | Consulting Serviices for the Construction Management of the Construction of New Pier (ESB Port Dev't Option 1-Scheme B) and Flattening of the Hilly Area (Phase 1) | Consulting Services | CFCM | 2023-02-01 | 2023-02-02 | 12:00PM |  | -44959 | ESB | N | PB | 2023-03-14 | 2023-03-21 | 2023-04-25 | 2023-03-28 | 2023-05-18 | 2023-05-18 | [7 empty] | COB | 43951025 |  | 43951025 |  |  |  |  | COA,MBC,PCCI, PICPA | 2023-04-17 | 2023-04-17 | 2023-04-17 | 2023-04-17 | [13 empty] | Ongoing - Post Qualification
BR-23-049 | 23MO-01H2A | Supply, Delivery and Printing of Calling Cards (MRCR) | Goods & Services | GSM | 2023-02-02 | 2023-02-02 | 3:20PM | 2023-02-21 | 19 | BRDD | N | NP-SVP | N/A | 2023-02-06 | N/A | N/A | N/A | 2023-02-17 | N/A | 2023-02-21 | N/A | 2023-02-22 | N/A | 30 days |  | COB | 1000 | 1000 |  | 850 | 850 |  | Forms International Enterprises Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298659 | Awarded | Completed/Delivered
PIP-23-050 | 23MO-01D | Anti-Venom | Goods & Services | CDBB | 2023-01-25 | 2023-02-16 | 1:06PM |  | -44973 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 9600 | 9600 | [16 empty] | 1st-non receipt quotation | 2023-02-14 | 2023-02-14 | 2023-02-14 |  |  |  | Emailed to EGC 3:30PM
GSD-23-051 | 23MO-01E1 | Supply and Delivery of Biometric Scanner | Goods & Services | CDBB | 2023-02-01 | 2023-02-03 | 1:37PM | 2023-02-16 | 13 | GSD | N | NP-SVP | N/A | 2023-02-07 | N/A | N/A | N/A | 2023-02-15 | N/A | 2023-02-16 | N/A | 2/17/23 | N/A | 30 days |  | COB | 20000 | 20000 |  | 20000 | 20000 |  | Comparts Computer Sales | [9 empty] | 2023-02-20 | [6 empty] | PO#298655 | Awarded | Completed/Delivered
PIP-23-052 | 23MO-01H2J | Supply and Delivery of Various Fire Extinguisher | Goods & Services | CDBB | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-03-07 | 32 | PIP | N | NP-SVP | N/A | 2023-02-10 | N/A | N/A | N/A | 2023-03-03 | N/A | 2023-03-07 | N/A | 2023-03-08 | N/A | 30 days |  | COB | 100000 | 100000 |  | 41750 | 41750 |  | A.D. Ramos Building Construction & Engineering Services | [9 empty] | 2023-03-13 | [6 empty] | PO#298667 | Awarded | Completed/Delivered
PIP-23-053 | 23MO-05C3 | Hauling and Disposal of Generated Non-hazardous Solid Wastes by PNOC Industrial Park | Goods & Services | GSM | 2023-01-31 | 2023-03-03 | 3:00PM |  | -44988 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 60000 | 60000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st-non-receipt of bids/ 2nd-Over ABC | 2/15/2023 _3/22/23 | 2/21/2023_3/24/23 | 2023-02-23 |  |  |  | Re-Processing
PIP-23-054 | 23MO-01H2I | Life Ring | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 16000 | 16000 |  | 33317.5 | 33317.5 |  | Safetyko Industrial Supplies | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-05-19 | [6 empty] | PO#298666 | Awarded | Completed/Delivered
PIP-23-055 | 23MO-01H2F | Cotton Gloves | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 2000 | 2000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | Completed/Delivered
PIP-23-056 | 23MO-01H2G | Hi-Visibility Vest/ Reflective Vest |  | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 3000 | 3000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | Completed/Delivered
PIP-23-057 | 23MO-01H2E | Safety Shoes | Goods & Services | GSM | 2023-01-25 | 2023-02-03 | 11:47AM | 2023-02-28 | 25 | PIP | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-16 | N/A | 2023-02-28 | N/A |  | N/A |  |  | COB | 25000 | 25000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | Completed/Delivered
BR-23-058 | Approved Budget Realignment | Engagement of an individual consultant for the development of decentralized energy systems (DES)- solar PV Rooftop system in PNOC (ESB) | Consulting Services | CFCM | 2023-02-03 | 2023-02-06 | 8:38AM | 2023-03-24 | 46 | BRDD | N | NP-SVP | N/A | 2023-03-08 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-03-24 | 2023-03-24 |  | 2023-04-18 | 30 days |  | COB | 500000 | 500000 |  | 421000 | 421000 |  | Engr. Adrian L. Rey | [9 empty] | 2023-04-27 |  | 1st-Non Receipt of Quotation | 2023-03-01 | 2023-03-01 | 2023-03-01 |  | Contract #23-024 | Awarded | Completed/Delivered
GSD-23-059 | 23MO-01E4 | Supply and Delivery of Compressor Motor for Aircon at PNOC Records Bldg. | Goods & Services | GSM | 2023-02-02 | 2023-02-07 | 1:33PM | 2023-02-28 | 21 | GSD | N | NP-SVP | N/A | 2023-02-08 | N/A | N/A | N/A | 2023-02-20 | N/A | 2023-02-28 | N/A | 2023-03-03 | N/A |  |  | COB | 32000 | 32000 |  | 24990 | 24990 |  | Pumpcraft Industrial Sales | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-05-04 | [6 empty] | PO#298665 | Awarded | Completed/Delivered
IA-23-060 | 23MO-01 | Supply and Delivery of 1 unit Maintenance Box for Epson Printer L6160 | Goods & Services |  | 2023-02-02 | 2023-02-08 | 2:31PM |  | -44965 | IAO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 1000 | 1000 | [23 empty] | Returned to End - user
SM-23-061 | 23MO-07D4 | Cloud Based Email Hosting | Goods & Services | CDBB |  | 2023-02-09 | 10:00AM |  | -44966 | SMO | N | NP-SVP | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-04-11 | 2023-04-12 | 2023-04-26 | 2023-04-25 | 29 days |  | COB | 330000 | 330000 |  | 298000 | 298000 |  | Tierra Networks Technologies Inc. | [11 empty] | 1st-Non Receipt of quotations | 2023-02-21 | 2023-02-22 |  |  | Contract#23-025 | Awarded | Completed/Delivered
PIP-23-062 | 23MO-06C1 | Calibration of Various Meters | Goods & Services | GSM | 2023-02-08 | 2023-02-10 | 1:15PM | 2023-03-02 | 20 | PIP | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-23 | N/A | 2023-03-02 | N/A | 2023-03-03 | N/A | 30 days |  | COB | 49000 | 49000 |  | 48300 | 48300 |  | Premier Physic Metrologie Co. | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-03-16 | [6 empty] | PO#298664 | Awarded | Completed/Delivered
PIP-23-063 | 23MO-04B1N | Conduct of Work Measure Environment | Goods & Services | GSM | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-02 | 20 | PIP | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-28 | N/A | 2023-03-02 | N/A | 2023-03-03 | N/A |  |  | COB | 30000 | 30000 |  | 29456 | 29456 |  | CRL Calabarquez Corp. | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-03-10 | [5 empty] | 2023-06-06 | PO#298663 | Awarded | Completed/Delivered
PIP-23-064 | 23MO-01H2H | Supply and Delivery of Dust Mask | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-09 | 27 | PIP | N | NP-SVP | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-09 | N/A | 2023-03-13 | N/A |  |  | COB | 3000 | 3000 |  | 2040 | 2040 |  | See More Enterprise Co | [9 empty] | 2023-03-14 | [6 empty] | PO#298670 | Awarded | Completed/Delivered
PIP-23-065 | 23MO-01H2M | Supply and Delivery of various Other Supplies for Safety | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-09 | 27 | PIP | N | NP-SVP | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-09 | N/A | 2023-03-13 | N/A |  |  | COB | 68000 | 68000 |  | 32125 | 32125 |  | See More Enterprise Co/Villaflores Industrial Supply | [9 empty] | 2023-03-14 | [6 empty] | PO#298670/298671 | Awarded | Completed/Delivered
PIP-23-066 | 23MO-07E5 | Supply and Delivery of Materials for the Coastal Clean-Up 2023 | Goods & Services | GSM | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-02-28 | 18 | PIP | N | NP-SVP | N/A | 2023-02-16 | N/A | N/A | N/A | 2023-02-23 | N/A | 2023-02-28 | N/A | 2023-03-01 | N/A | 30 Days |  | COB | 35000 | 35000 |  | 29820 | 29820 |  | Ceboom Enterprises/Syner Graphics Co./ Safetyko | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298660/298661 | Awarded | Completed/Delivered
PIP-23-067 | 23MO-06C10 | Supply and Delivery of 100Watts LED Street Light | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-07 | 25 | PIP | N | NP-SVP | N/A | 2023-02-15 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-07 | N/A | 2023-03-08 | N/A | 30 Days |  | COB | 200000 | 200000 |  | 140000 | 140000 |  | West Point Engineering Supplies Incorporated | [9 empty] | 2023-03-10 | [6 empty] | PO#298668 | Awarded | Completed/Delivered
PIP-23-068 | 23MO-01H2L | Supply and Delivery of Safety Hazards | Goods & Services | CDBB | 2023-02-09 | 2023-02-10 | 1:15PM | 2023-03-09 | 27 | PIP | N | NP-SVP | N/A | 2023-02-21 | N/A | N/A | N/A | 2023-03-06 | N/A | 2023-03-09 | N/A | 2023-03-13 | N/A |  |  | COB | 22000 | 22000 |  | 16100 | 16100 |  | Villaflores Industrial Supply | [9 empty] | 2023-03-14 | [6 empty] | PO#298671 | Awarded | Completed/Delivered
PSD-23-069 | 23MO-01H1C | Supply and Delivery of CY 2023 Token for Loyalty Service Awardees | Goods & Services | GSM | 2023-02-08 | 2023-02-13 | 10:31AM | 2023-03-23 | 38 | PSD | N | NP-SVP | N/A | 2023-02-28 | N/A | N/A | N/A | 2023-03-20 | N/A | 2023-03-23 | N/A | 2023-03-27 | N/A | 30 Days |  | COB | 160000 | 160000 |  | 88000 | 88000 |  | 3D Image Works and Design House | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298675 | Awarded | Completed/Delivered
PIP-23-070 | 23MO-06C12 | Preventive Maintenance Services of CCTV System for PIP | Goods & Services | GSM | 2023-02-22 | 2023-03-03 | 2:00PM | 2023-03-21 | 18 | PIP | N | NP-SVP | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-03-21 | 2023-03-27 | 2023-05-22 | 2023-03-28 | 30 days |  | COB | 171000 | 171000 |  | 112500 | 112500 |  | Compass Integrated Solutions,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#23-070 | Awarded | Completed/Delivered
PSD-23-071 | 23MO-01H1F/01H1D/01H1G | Supply and Delivery of CY 2023 Token for Loyalty Service Awardees & Retirees | Goods & Services | GSM | 2023-02-08 | 2023-02-15 | 3:57PM | 2023-03-21 | 34 | PSD | N | NP-SVP | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-03-17 | N/A | 2023-03-21 | N/A | 2023-03-27 | N/A | 30 Days |  | COB | 48000 | 48000 |  | 46000 | 46000 |  | Ad-Man Resources Inc. / Suarez Brothers Metal Arts, Inc. | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-09-06 | [6 empty] | PO#298678/677 | Awarded | Completed/Delivered | 2 Tube Trophy/ 5 Plaque Retirees
PSD-23-072 | 23MO-01D | Supply and Delivery of Fluquadri Vaccine (Adult) | Goods & Services | CDBB | 2023-02-13 | 2023-02-14 | 4:07PM | 2023-03-02 | 16 | PSD | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-28 | N/A | 2023-03-02 | N/A | 2023-03-03 | N/A | 30 days |  | COB | 90000 | 90000 |  | 71003 | 71003 |  | Pharma Quest Co. | [9 empty] | 2023-03-06 | [6 empty] | PO#298662 | Awarded | Completed/Delivered
GAD-23-073 | 23MO-07E2 | Supply and Delivery of T-shirts for 2023 National Women's Month Celebration | Goods & Services | GSM |  | 2023-02-15 | 7:50AM | 2023-03-14 | 27 | GAD | N | NP-SVP | N/A | 2023-02-17 | N/A | N/A | N/A | 2023-02-27 | N/A | 2023-03-14 | N/A | 2023-03-14 | N/A |  |  | COB | 39300 | 39300 |  | 29260 | 29260 |  | Ceboom Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | 2023-05-25 | PO#298672 | Awarded | Completed/Delivered
SM-23-074 | 23MO-01A | Supply and Delivery of Stamp with Inscription | Goods & Services | GSM |  | 2023-02-16 |  | 2023-03-09 | 21 | SMO | N | NP-SVP | N/A | 2023-02-23 | N/A | N/A | N/A | 2023-03-08 | N/A | 2023-03-09 | N/A | 2023-03-10 | N/A | 30 days |  | COB | 3500 | 3500 |  | 3500 | 3500 |  | ZAB Enterprises Inc. | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-04-28 | [6 empty] | PO#298669 | Awarded | Completed/Delivered
GSD-23-075 | 23CA-03D | Exterior Repainting of Bldg.5 | Infrastructure | CFCM | 2023-02-10 | 2023-02-16 | 2:40PM | 2023-05-02 | 75 | GSD | N | PB | 2023-02-28 | 2023-03-02 | 2023-03-09 | 2023-03-23 | 2023-03-23 | 2023-03-30 | 2023-04-28 | 2023-05-02 | 2023-05-03 | 2023-06-05 | 2023-05-30 | 60 days |  | COB | 4500000 |  | 4500000 | 4217025 |  | 4217025 | Pablo S. Labasbas Construction Corporation | MBC,PCCI, COA | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-02-28 | 2023-02-28 |  | 2023-06-23 | 2023-06-23 | 2023-06-23 | [6 empty] | Contract#23-034 | Awarded | Completed/Delivered
PP-23-076 | 23MO-01A | Supply and Delivery of Consolidated Computer Supplies, for 1st QTR year 2023 | Goods & Services | GSM | 2023-02-17 | 2023-02-17 | 3:05PM | 2023-05-02 | 74 | PRM | N | NP-SVP | N/A | 2023-03-25 | N/A | N/A | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-05-08 | N/A |  |  | COB | 907538.92 | 907538.92 |  | 700234.96 | 700234.96 |  | Accessories & Supplies Depot,Inc (ASDI)/PBT Technology Solutions,Inc/Philcopy Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298685/686/687 | Awarded | Completed/Delivered
SM-23-077 | 23MO-06E1 | Repair of Printer HP Laser Printer M451NW | Goods & Services | GSM |  | 2023-02-23 | 10:10AM |  | -44980 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 2500 | 2500
PP-23-078 | 23MO-01A | Supply and Delivery of Consolidated Commonly Used Supplies, 1st QTR | Goods & Services | GSM | 2023-02-22 | 2023-02-23 | 3:10PM | 2023-06-27 | 124 | PRM | N | NP-SVP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | N/A | 2023-07-06 | N/A | 30 dyas |  | COB | 265541.82 | 265541.82 |  | 432060.59 | 432060.59 |  | ZAB Enterprises Inc./ Halden General Merchandise/Oriental School and office Supply | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-09-06 | [6 empty] | PO#298711/712/713 | Awarded | Completed/Delivered
PIP-23-079 | 23MO-01A | Supply and Delivery of Laserjet Ink | Goods & Services | GSM | 2023-02-17 | 2023-02-27 | 9:30PM | 2023-04-11 | 43 | PIP | N | NP-SVP | N/A | 2023-03-15 | N/A | N/A | N/A | 2023-03-29 | N/A | 2023-04-11 | N/A | 2023-04-13 | N/A | 30 Days |  | COB | 30000 | 30000 |  | 23664 | 23664 |  | Accessories & Supplies Depot,Inc (ASDI) | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298682 | Awarded | Completed/Delivered
PSD-23-080 | Approved Budget Realignment | Supply and Delivery of 2023 Wellness Tshirts | Goods & Services | GSM | 2023-02-16 | 2023-02-27 | 3:40PM | 2023-03-21 | 22 | PSD | N | NP-SVP | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-15 | N/A | 2023-03-21 | N/A | 2023-03-27 | N/A | 30 days |  | COB | 45900 | 45900 |  | 26010 | 26010 |  | Ceboom Enterprises | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298679 | Awarded | PENDING APPROVAL FROM OP
GAD-23-081 | 23MO-07E2 | Supply and Delivery of Tote Bags for 2023 National Womens Month Celebration | Goods & Services | GSM | 2023-02-27 | 2023-02-27 | 3:58PM | 2023-03-14 | 15 | GAD | N | NP-SVP | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-09 | N/A | 2023-03-14 | N/A | 2023-03-14 | N/A | 30 days |  | COB | 16000 | 16000 |  | 13440 | 13440 |  | King of Kings Trading | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | 2023-05-25 | PO#298673 | Awarded | Completed/Delivered
PIP-23-082 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station | Goods & Services | CDBB | 2023-01-17 | 2023-03-02 | 9:30AM |  | -44987 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 142200 |  | 142200 | [15 empty] | 1st- non-receipt | 2023-03-14 | 2023-03-14 | 2023-03-14 |  |  |  | Cancelled
PIP-23-083 | 23MO-06D2 | Supply and Delivery of Tires and Windshield Wipers | Goods & Services | CDBB | 2023-02-22 | 2023-03-02 | 9:30AM | 2023-03-16 | 14 | PIP | N | NP-SVP | N/A | 2023-03-03 | N/A | N/A | N/A | 2023-03-15 | N/A | 2023-03-16 | N/A | 2023-03-17 | N/A | 30 days |  | COB | 166800 | 166800 |  | 115800 | 115800 |  | MENDO Enterprises | [9 empty] | 2023-03-23 | [6 empty] | PO#298674 | Awarded | Completed/Delivered
PSD-23-084 | 23M0 -01H1A | Supply and Delivery of CY2023 Token For 30 Years Loyalty Service Awardees(Wrist Watch) | Goods & Services | GSM | 2023-02-28 | 2023-03-02 | 11:30AM | 2023-05-11 | 70 | PSD | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-11 | N/A | 2023-05-19 | N/A | 30 days |  | COB | 600000 | 600000 |  | 598080 | 598080 |  | Neuchatel, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298688 | Awarded | Completed/Delivered
PIP-23-085 | 23MO-01E6 | Supply and Delivery of Heavy Duty Battery Charger | Goods & Services | CDBB | 2023-02-17 | 2023-03-03 | 9:08AM |  | -44988 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 14420 | 14420 | [15 empty] | 2023-03-27 | 1st & 2nd- non receipt/3rd-non compliance/4th | 3/14/2023 & 4/28/23/5/23 | 3/14/2023 & 4/28/23-5/23 | 3/14/2023 & 4/28/23 | 0 |  |  | Cancelled
PIP-23-086 | 23MO-01H2D | Supply and Delivery of Flags & Accessories | Goods & Services | GSM | 2023-02-27 | 2023-03-03 | 9:08AM | 2023-03-21 | 18 | PIP | N | NP-SVP | N/A | 2023-03-07 | N/A | N/A | N/A | 2023-03-07 | N/A | 2023-03-21 | N/A | 2023-03-27 | N/A | 30days |  | COB | 30000 | 30000 |  | 14070 | 14070 |  | Flags of All Nations | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298676 | Awarded | Completed/Delivered
SM-23-087 | 23MO-07D4 | Cloud Based Email Hosting | Goods & Services | CDBB |  | 2023-03-03 | 3:50PM | 2023-04-11 | 39 | SMO | N | NP-SVP | N/A | 2023-03-28 | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-04-11 | 2023-04-12 | 2023-04-26 | 2023-04-25 | 29 days |  | COB | 330000 | 330000 |  | 298000 | 298000 |  | Tierra Networks Technologies Inc. | [9 empty] | 2023-04-26 |  |  |  | Superceded by SM-23-061 |  |  | Contract#23-025 | Awarded | Completed/Delivered
PSD-23-088 | 23MO-05C6 | Temporary Office Services | Goods & Services | CDBB | 2023-03-02 | 2023-03-06 | 9:25PM | 2023-03-21 | 15 | PSD | N | NP-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-21 | 2023-03-21 | Contract draft | 2023-03-27 | April- December |  | COB | 5000000 | 5000000 |  | 4812586.65 | 4812586.65 |  | LBP Resources and Development Corporation | [16 empty] | Contract#23-042 | Awarded | Completed/Delivered
GSD-23-089 | 23MO-01E3 | Audio/Video Player w/ Wireless Microphone | Goods & Services | GSM | 2023-03-03 | 2023-03-07 | 11:20PM | 2023-03-30 | 23 | GSD | N | NP-SVP | N/A | 2023-03-15 | N/A | N/A | N/A | 2023-03-28 | N/A | 2023-03-30 | N/A | 2023-04-03 | N/A | 30 days |  | COB | 28000 | 28000 |  | 27995 | 27995 |  | Uly Tech Trading | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-04-13 | [6 empty] | PO#29861 | Awarded | Completed/Delivered
ESB-23-091 | Approved Budget Realignment | Engagement of Consultancy Firm for the Preparation of Engineering Geological and Geohazard Assessment Report | Consulting Services | CFCM | 2023-02-01 | 2023-04-18 | 10:55PM | 2023-05-23 | 35 | ESB | N | NP-SVP | N/A | 2023-04-20 | N/A | N/A | N/A | 2023-05-18 | N/A | 2023-05-23 | 2023-05-24 |  |  | 30 days |  | COB | 200000 | 200000 |  | 199200 | 199200 |  | Woodfields Consultants, Inc. | [11 empty] | 1st&2nd -Non Receipt/3rd - deferred lack of detailed Presentation | 3/28/2023- 4/17/23 | 3/28/2023- 4/17/23 | 3/28/2023- 4/17/23 |  |  | Awarded | Completed/Delivered
PIP-23-092 | 23MO-06C16 | Supply and Delivery of Various Paints | Goods & Services | GSM | 2023-01-24 | 2023-03-10 | 3:40PM | 2023-05-25 | 76 | PIP | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-19 | N/A | 2023-05-25 | N/A | 2023-05-29 | N/A | 30 days |  | COB | 99555 | 99555 |  | 99376.1 | 99376.1 |  | Shigan Construction Supplies Trading | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st - Over ABC | 2023-03-27 | 2023-03-27 | 2023-03-28 |  | PO#298693 | Awarded | Completed/Delivered
PIP-23-093 | 23MO-06C9 | Supply and Delivery of Mechanical Consumables for Booster Pumps | Goods & Services | GSM | 2023-01-24 | 2023-03-10 | 3:40PM | 2023-05-30 | 81 | PIP | N | NP-SVP | N/A | 2023-03-18 | N/A | N/A | N/A | 2023-05-26 | N/A | 2023-05-30 | N/A | 2023-06-01 | N/A | 30 days |  | COB | 324632.79 | 324632.79 |  | 157718 | 157718 |  | Manara Marketing | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298696 | Awarded | Completed/Delivered
GSD-23-094 | 23MO-06C16 | Supply and Replacement of 1125kva Caterpillar Genset Motor Starter at PNOC Bldg.5 | Goods & Services | GSM | 2023-02-27 | 2023-03-15 | 3:30PM | 2023-04-13 | 29 | GSD | N | NP-SVP | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-04-05 | N/A | 2023-04-13 | 2023-04-17 | 2023-05-31 | 2023-05-18 | 30 days |  | COB | 482000 | 482000 |  | 399764.46 | 399764.46 |  | Tabuko Energy Network Corp. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #23-029 | Awarded | Completed/Delivered
AM-23-095 | 23MO-04B1E/04B1G/04B1I | Land Surveying Consultancy (Relocation,Subdivision,Leased Area Surveys,As-built survey of PNOC Properties located in Kananga ,Leyte, Limay and Mariveles | Consulting Services | CFCM | 2023-03-14 | 2023-03-16 | 3:30PM | 2023-08-08 | 145 | AMD | N | PB | 2023-04-06 | 2023-04-11 | 2023-05-25 | 2023-04-18 | 2023-06-08 | 2023-06-29 | 2023-08-04 | 2023-08-08 | 2023-08-31 |  |  | 65 Days |  | COB | 1130000 | 1130000 |  | 868000 | 868000 |  | SmartGeo Surveying and Geomatics | COA,MBC,PCCI | 2023-05-17 | 2023-05-17 | 2023-05-17 | 2023-05-17 | [12 empty] | Awarded | For Contract Finalization
PP-23-096 | 23CA-04A10 | Supply, Design, Develop and Installation of PNOC Asset Inventory Management System | Goods & Services | CDBB | 2023-03-13 | 2023-03-16 | 1:27PM | 2023-03-23 | 7 | PRM | N | PB-AA | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-23 | 2023-03-24 | Contract draft |  |  |  | COB | 3640000 | 3640000 |  | 28000000 |  | 28000000 | DBP DATA Center Inc. | [17 empty] | Awarded | PENDING APPROVAL FROM OP
PSD -23-097 | 23MO-04B1R | Engagement of Retainer Physician for PNOC Head Office | Goods & Services | GSM | 2023-03-13 | 2023-03-21 | 9:30AM | 2023-03-30 | 9 | PSD | N | NP-SVP | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-03-30 | N/A | 2023-03-30 | 2023-03-30 | 2023-05-08 | 2023-03-31 | April- December |  | COB | 399999.78 | 399999.78 |  | 399000 | 399000 |  | Dra. Marie Yvette Soriano-Jarmillo,MD,FPCOM | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract #23-028 | Awarded | Completed/Delivered
PIP-23-098 | 23CA-05B | Purchase, Supply and Delivery of Three Wheel Electric Motorcycle | Goods & Services | GSM | 2023-03-17 | 2023-03-22 | 9:43AM | 2023-04-11 | 20 | PIP | N | NP-SVP | N/A | 2023-03-24 | N/A | N/A | N/A | 2023-04-04 | N/A | 2023-04-11 | N/A | 2023-04-13 | N/A | 30 days |  | COB | 195000 | 195000 |  | 194640 |  | 194640 | Marquay Trading OPC | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-05-08 | [6 empty] | PO#298683 | Awarded | Completed/Delivered
AM-23-099 | 23CA-03T | PNOC Staffhouse Buildings Repair (Re-roofing and re-painting | Infrastructure | CDBB | 2023-03-21 | 2023-03-24 | 11:29AM | 2023-05-30 | 67 | AMD | N | PB |  | 2023-04-11 | 2023-04-18 | 2023-05-04 | 2023-05-04 | 2023-05-17 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-23 | 2023-06-20 | 30 days |  | COB | 1499099.77 | 1499099.77 |  | 1472193.8 |  | 1472193.8 | De Jesus Construction | 2023-04-30 | [15 empty] | Contract # 23-040 | Awarded | Completed/Delivered
PIP-23-100 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station | Goods & Services | CDBB | 2023-03-15 | 2023-04-11 | 4:42PM | 2023-05-11 | 30 | PIP | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-02 | N/A | 2023-05-02 | N/A |  | N/A |  |  | COB | 142200 |  | 142200 | 39132.5 |  | 39132.5 | RBC (Mariveles)hardware, Inc./UpTown Industrial Sales, Inc, | [10 empty] | Superceded by PIP-23-082 | 2nd- Non receipt | 2023-04-05 | 2023-04-05 | 2023-04-11 | 2023-06-06 | PO#298689/690 | Awarded | Not all Items are Awarded
PSD-23-101 | Approved Budget Reallocation | Conduct of QMS Appreciation Tranings | Goods & Services | GSM | 2023-03-22 | 2023-03-27 | 3:40pm | 2023-05-02 | 36 | PSD | N | NP-SVP | N/A | 2023-04-01 | N/A | N/A | N/A | 2023-04-24 | N/A | 2023-05-02 | 2023-05-04 | 2023-05-22 | 2023-05-19 | 3 days |  | COB | 151200 | 151200 |  | 120000 | 120000 |  | JBDC Occupational Health Safety and Environmental Consultancy | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract # 23-031 | Awarded | Completed/Delivered
SM-23-102 | 23CA-04A2 | Supply and Delivery of Desktop Computer | Goods & Services | CDBB |  | 2023-03-29 | 3:31PM | 2023-03-30 | 1 | SMO | N | NP-SVP | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2023-03-30 | N/A | 2023-03-31 | N/A | 30 days |  | COB | 689000 |  | 689000 | 689000 |  | 689000 | Columbia Technologies Inc. | [9 empty] | 2023-04-20 |  |  | REPEAT ORDER |  |  |  | PO#298680 | Awarded | Completed/Delivered
PSD-23-103 | 23MO-07E10 | Venue Rental for PNOC 50th Anniversary | Goods & Services | CDBB | 2023-03-29 | 2023-04-03 | 4:14PM | 2023-05-16 | 43 | PSD | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-10 | N/A | 2023-05-16 | 2023-05-19 | 2023-08-03 | 2023-06-29 | 1 day |  | COB | 703000 | 703000 |  | 702744 | 702744 |  | The Marquiz Events Place | [16 empty] | Contract#23-035 | Awarded | Completed/Delivered
ESB-23-104 | 23MO-06D5 | Preventive Maintenance Services of Forklift (JAC CPCD 50H | Goods & Services | GSM | 2023-03-29 | 2023-06-07 | 1:54PM | 2023-07-04 | 27 | ESB | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-07-03 | N/A | 2023-07-04 | N/A | 2023-07-07 | N/A | 30 Days |  | COB | 26650 | 26650 |  | 29068 | 29068 |  | JAC Automobile Int'l Phils. Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st - TOR rev & 2nd - Over ABC | 1ST-April 26 / 2ND - May 09 | 1ST-April 26 / 2ND - May 09 | 1ST-April 26 / 2ND - May 09 |  | PO#298716 | Awarded | Completed/Delivered
AM-23-105 | 23MO-01E7 | Supply and Delivery of Electronic Typewriter | Goods & Services | GSM | 2023-03-30 | 2023-06-13 | 10:05AM | 2023-07-04 | 21 | AMD | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-06-27 | N/A | 2023-07-04 | N/A | 2023-07-12 | N/A | 30 days |  | COB | 45000 | 45000 |  | 82380 | 82380 |  | Business Machines Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | 1st -Over ABC | 2023-06-06 | 2023-06-06 | 2023-06-06 |  | PO#298717 | Awarded | Completed/Delivered
TD-23-150 | Approved Budget Realignment | Supply and Delivery of Electronic Typewriter and its comsumable | Goods & Services | GSM | 2023-06-09 | 2023-06-13 | 11:05AM | 2023-07-04 | 21 | TD | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-06-26 | N/A | 2023-07-04 | N/A | 2023-07-12 | N/A | 30 days |  | COB | 45000 | 45000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | Completed/Delivered
ESB-23-106 | 23MO-O1H2 | Supply and Delivery of PPE's and Other Safety Equipments | Goods & Services | GSM | 2023-03-29 | 2023-04-04 | 9:30AM | 2023-06-06 | 63 | ESB | N | NP-SVP | N/A | 2023-05-11 | N/A | N/A | N/A | 2023-06-01 | N/A | 2023-06-06 | N/A | 2023-06-08 | N/A | 30 days |  | COB | 79000 | 79000 |  | 64919.1 | 64919.1 |  | Safetyko Industrial Supplies /Glim Diversified Sales and Services Corp./B2B Non-Specialized Wholesale Trading/Villaflores Trading | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298697/698/699/731 | Awarded | Completed/Delivered
ESB-23-107 | 23MO-01H2C | Supply and Delivery of Safety Signages and Vehicle Sticker | Goods & Services | GSM | 2023-03-31 | 2023-04-04 |  | 2023-07-25 | 112 | ESB | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 55517 | 55517 | [23 empty] | Awaiting for Evaluation of Sample from ESB
PSD-23-108 | 23MO-07E12 | Supply and Delivery of PNOC 50th Anniversary T-shirt with Collar/with cuff | Goods & Services | CDBB | 2023-03-31 | 2023-04-04 | 2:53PM | 2023-05-04 | 30 | PSD | N | NP-SVP | N/A | 2023-04-14 | N/A | N/A | N/A | 2023-05-03 | N/A | 2023-05-04 | N/A | 2023-05-05 | N/A | 30 days |  | COB | 75250 | 75250 |  | 70520 | 70520 |  | King of Kings Trading | [16 empty] | PO#298684 | Awarded | Completed/Delivered
SM-23-109 | 23MO-0782 | Printing of 2024 Wall and Desk Calendars | Goods & Services | CFCM | 2023-04-23 | 2023-04-04 | 3:24PM | 2023-11-05 | 215 | SMO | N | NP-SVP | N/A | 2023-04-21 | N/A | N/A | N/A | 2023-10-05 | N/A | 2023-05-11 | 2023-05-12 |  | 2023-06-01 |  |  | COB | 650000 | 650000 |  | 418845 | 418845 |  | VJ Graphic Arts, inc. | [16 empty] | Contract#23-033 | Awarded
PP-23-110 | 23MO-01C/01B | Supply and Delivery of Consolidated Office Forms (Accountable/Non-Accountable Forms) | Goods & Services | GSM | 2023-04-05 | 2023-04-11 | 9:09AM | 2023-06-20 | 70 | PRM | N | NP-SVP | N/A | 2023-06-10 | N/A | N/A | N/A | N/A | N/A | 2023-06-20 | [5 empty] | COB | 198420.48 | 198420.48 |  | 144444 | 144444 |  | Grandsmart Enterprise | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded
ESB-23-111 | 23MO-061A/06A2/06B2-06B5/06B8-06B12/06C15/06f1/06f2 | Supply and Delivery of Materials for 2023 ESB Annual Maintenance Plan | Goods & Services | GSM | 2023-04-11 | 2023-04-13 | 8:49PM | 2023-06-27 | 75 | ESB | N | NP-SVP | N/A | 2023-04-29 | N/A | N/A | N/A | N/A | N/A | 2023-06-27 | N/A | 2023-07-07 | N/A | 30 days |  | COB | 593536 | 593536 |  | 329529.1 | 329529.1 |  | Greatphil Enterprises Inc./Up-Town Industrial Sales, Inc/United Hardware & General Merchandise / ECM Hardware and Equipments Corp. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298714/715 | Awarded | Completed/Delivered
GSD-23-112 | 23CA-03B | Replacement of Ceiling Mounted ACU at server room | Goods & Services | GSM | 2023-03-30 | 2023-04-14 | 8:18AM | 2023-05-16 | 32 | GSD | N | NP-SVP | N/A | 2023-04-25 | N/A | N/A | N/A | 2023-05-11 | N/A | 2023-05-16 | 2023-05-17 | 2023-09-11 | 2023-08-11 | 21 days |  | COB | 355806 | 355806 |  | 300000 |  | 300000 | Caresystem Technology Solution Co | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#23-037 | Awarded | Completed/Delivered
PIP-23-113 | 23CA-02A2 | Supply, Delivery, Installation, testing and Commissioning of Level Sensors | Goods & Services | CDBB | 2023-03-10 | 2023-04-14 | 8:40AM |  | -45030 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 849500 |  | 849500 | [15 empty] | 1st -Non Receipt | 2023-05-16 | 2023-05-16 | 2023-05-18
AM-23-114 | 23MO-04B1F | Third Party Appraisal of Various PNOC Properties | Consulting Services | CFCM | 2023-04-14 |  | 4:30PM |  | #VALUE! | AMD | N | PB | 2023-06-13 |  | 2023-07-27 | 2023-08-10 | 2023-08-10 | 2023-08-22 | 2023-09-20 | 2023-09-21 | [5 empty] | COB | 1600000 | 1600000 |  | 1405000 | 1405000 |  | Value Metric Inc. | COA,MBC,PICPA,PCCI | 2023-07-27 | 8/10&17/23 | 8/10&17/23 | 2023-08-18 | 2023-09-20 | [5 empty] | 1sT- Ineligible | 2023-05-30 | 2023-05-30 | 2023-05-30 |  |  | Awarded | For Award Recommendation
GSD-23-115 | 23CA-03A/23CA-03G | Waterproofing of PNOC Bldg.5 & 6 | Goods & Services | CDBB | 2023-04-17 | 2023-06-08 | 4:05PM | 2023-09-07 | 91 | GSD | N | PB | 2023-06-13 | 2023-06-15 | 2023-06-22 | 2023-07-06 | 2023-07-06 | 2023-07-17 | 2023-09-06 | 2023-09-07 | 2023-09-07 |  | 2023-09-28 |  |  | COB | 4200000 |  | 4200000 | 4150000 | 4150000 |  | Isometric Enterprises | COA,MBC,PCCI | 2023-06-22 | 2023-07-06 | 2023-07-06 | 2023-07-13 | 2023-07-25 | [5 empty] | 1st- Non-compliance | 2023-06-06 | 2023-06-06 | 2023-06-06 |  | Contract#23-050 | Awarded | NTP Signed/Contract is with OP
GSD-23-116 | 23CA-03I | Preventive Maintenance of 500kw and 2x900kw Stand-by Generator Sets at PNOC Building 5 and 6 | Goods & Services | GSM | 2023-04-13 | 2023-04-25 | 8:35AM | 2023-06-07 | 43 | GSD | N | NP-SVP | N/A | 2023-05-16 | N/A | N/A | N/A | 2023-05-24 | N/A | 2023-06-07 | 2023-06-07 | 2023-06-07 |  |  |  | COB | 550145.47 |  | 550145.47 | 444000 |  | 444000 | 3J Power Contruction Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Contract#23-045 | Awarded | For Signing of Contract by Supplier
ESB-23-117 | 23CA-03V | Supply and Delivery of Foam-Filled Rubber Fender without Tire Net | Goods & Services | RGV | 2023-04-24 | 2023-04-25 | 1:36PM | 2023-07-13 | 79 | ESB | N | PB | 2023-05-25 | 2023-05-30 | 2023-06-06 | 2023-06-20 | 2023-06-20 | 2023-06-27 | 2023-07-13 | 2023-07-13 | N/A | 2023-07-17 | N/A | 90 days |  | COB | 980000 |  | 980000 | 769800 |  | 769800 | First & Finest Technology Corporation | COA,MBC,PCCI | 2023-06-06 | 2023-06-20 | 2023-06-20 | 2023-06-21 | 2023-06-28 | [10 empty] | PO#298719 | Awarded | Completed/ Delivered
GSD-23-118 | 23MO-04B15/04B1T | Fleet Monitoring System for PNOC Pooled Vehicle | Goods & Services | CDBB | 2023-04-14 | 2023-04-27 | 8:35AM | 2023-05-23 | 26 | GSD | N | NP-SVP | N/A | 2023-05-09 | N/A | N/A | N/A | 2023-05-17 | N/A | 2023-05-23 | N/A | 2023-05-24 | N/A | 30 days |  | COB | 90000 | 90000 |  | 89936 | 89936 |  | Cartrack Technologies Phl Inc. | [16 empty] | PO#298692 | Awarded | Completed/ Delivered
PIP-23-119 | 23MO-05C5 | Servicing of Genset | Goods & Services | GSM | 2023-04-20 | 2023-07-14 | 9:49AM | 2023-08-10 | 27 | PIP | N | NP-SVP | N/A | 2023-07-21 | N/A | N/A | N/A | 2023-08-09 | N/A | 2023-08-10 | N/A | 2023-08-31 | N/A | 30 days |  | COB | 64685 | 64685 |  | 60000 | 60000 |  | Mabuhay FOXTROTTrading Supply Wholesaling | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-09-06 |  | 1st-non Compliance- | 2023-07-04 | 2023-07-07 | 2023-07-07 |  | PO#298734 | Awarded | Completed/ Delivered
GSD-23-120 | 23CA-03G | Repair/Repainting of Compound Perimeter fence | Goods & Services | RGV | 2023-04-13 | 2023-05-02 | 2:14PM | 2023-07-06 | 65 | GSD | N | PB | 2023-05-11 | 2023-05-16 | 2023-05-23 | 2023-06-08 | 2023-06-08 | 2023-06-13 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-08-07 | 2023-08-04 | 60 days |  | COB | 2800000 |  | 2800000 | 2377650 |  | 2377650 | Jayterkiel Builders | COA,MBC,PCCI | 2023-05-31 | 2023-06-08 | 2023-06-08 | 2023-06-09 | 2023-06-16 |  | 2023-08-10 | 2023-08-10 | 2023-08-10 | [6 empty] | Contract #23-046 | Awarded | Completed/ Delivered
GSD-23-121 | Approved Budget Realignment | Dismantling and Repair of Transfer Pump at PNOC Bldg 6 | Goods & Services | CDBB | 2023-02-27 | 2023-05-02 | 2:14PM | 2023-05-23 | 21 | GSD | N | NP-SVP | N/A | 2023-05-09 | N/A | N/A | N/A | 2023-05-24 | N/A | 2023-05-25 | 2023-06-02 | 2023-06-21 | 2023-06-21 | 30 days |  | COB | 240000 |  | 240000 | 200000 | 200000 |  | Pablo S. Labasbas Construction Corporation | [9 empty] | 2023-06-22 | [6 empty] | Contract #23-041 | Awarded | Completed/ Delivered
GSD-23-122 | Approved Budget Realignment | Replacement of Various Defective Parts of Passenger Elevators at PNOC Bldg.6 | Goods & Services | GSM | 2023-04-13 | 2023-05-02 | 2:14PM |  | -45048 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 137321.42 |  | 137321.42 | [22 empty] | Cancelled
GSD-23-123 | Approved Budget Realignment | De-sludging of PNOC Bldg.6,5.3 and Motorpool Septic Tanks | Goods & Services | GSM | 2023-03-16 | 2023-05-24 | 2:14PM |  | -45070 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 357000 |  | 357000 | [15 empty] | 1st -over ABC /2nd-Non Compliance | 05/17/2023 / 07/28/23 | 05/17/2023 / 07/28/23 | 05/17/2023 / 07/28/23 |  |  |  | Cancelled
GSD-23-124 | 23MO-01H2V | Supply and Delivery of Microfiber Washable PPE | Goods & Services | GSM | 2023-05-04 | 2023-05-05 | 8:40PM | 2023-05-23 | 18 | GSD | N | NP-SVP | N/A | 2023-05-10 | N/A | N/A | N/A | 2023-05-17 | N/A | 2023-05-23 | N/A | 2023-05-23 | N/A | 30 days |  | COB | 5133.3 | 5133.3 |  | 5133.3 | 5133.3 |  | SafetyKo Industrial Supplies | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298691 | Awarded | Completed/ Delivered
PSD-23-125 | Approved Budget Realignment | Engagement of a Training Provider for the Conduct of an IQMS Audit Training | Goods & Services | GSM | 2023-05-02 | 2023-05-05 | 2:19PM | 2023-05-30 | 25 | PSD | N | NP-SVP | N/A | 2023-05-11 | N/A | N/A | N/A | 2023-05-25 | N/A | 2023-05-30 | N/A | 2023-05-31 | N/A | 30 days |  | COB | 200000 |  | 200000 | 60000 |  | 60000 | RPM Methods, Strategies and Documentation Services | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | 2023-06-07 | PO#298695 | Awarded | Completed/ Delivered
PSD-23-126 | Approved Budget Realignment | Advanced Training on the use, Application and Writeshop on the Harmonized GAD Guidelines | Goods & Services | CDBB | 2023-04-27 | 2023-05-05 | 2:19PM | 2023-07-18 | 74 | PSD | N | NP-SVP | N/A | 2023-06-23 | N/A | N/A | N/A | 2023-07-13 | N/A | 2023-07-18 | N/A | 2023-08-17 | N/A | Nov.20-21 |  | COB | 38500 | 38500 |  | 49000 | 49000 |  | R.P. Olivar Development Consultancy & Services | [11 empty] | 1st- Change in TOR/2nd-Non-Compliance | 2nd- 6/13/23 | 2023-06-13 | 2023-06-13 |  | PO#298725 | Awarded | Completed/ Delivered
PIP-23-127 | 23MO-01H2M | Supply and Delivery of Consumables for AED | Goods & Services | CDBB | 2023-04-13 | 2023-05-05 | 3:25PM | 2023-05-25 | 20 | PIP | N | NP-SVP | N/A | 2023-05-10 | N/A | N/A | N/A | 2023-05-19 | N/A | 2023-05-25 | N/A | 2023-05-30 | N/A | 30 days |  | COB | 20000 | 20000 |  | 20000 | 20000 |  | Sy Medical Training Corp. | [16 empty] | PO#298694 | Awarded | Completed/Delivered
PIP-23-128 | 23MO-05C3 | Hauling Transport, Treatment and Disposal of Generated Wastes (Non-hazardous Solid Wastes | Goods & Services | GSM |  | 2023-05-05 | 3:25PM | 2023-06-07 | 33 | PIP | N | NP-SVP | N/A | 2023-05-16 | N/A | N/A | N/A | 2023-05-31 | N/A | 2023-06-17 | 2023-06-14 |  |  |  |  | COB | 123200 | 123200 |  | 122000 | 122000 |  | Clean Leaf International Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | Superceded by PIP-23-053 |  |  |  | Awarded | Contract for signing of Supplier
SM-23-129 | 23MO-06E1 | Diagnostic/Check-up of Defective Printer MFP M180N | Goods & Services | GSM |  | 2023-05-08 | 10:35AM |  | -45054 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 2500 | 2500 | [23 empty] | Irrepairable
SM-23-130 | 23CA-04A3 | Supply and Delivery of Rack/Computer Server | Goods & Services | CDBB |  | 2023-05-11 | 9:04AM | 2023-07-11 | 61 | SMO | N | PB | N/A | 2023-05-23 | 2023-05-30 | 2023-06-13 | 2023-06-13 | 2023-06-23 | 2023-07-11 | 2023-07-11 | N/A | 2023-07-13 | N/A | 90 days |  | COB | 1002806.67 |  | 1002806.67 | 846000 |  | 846000 | DCI Int'L it Solutions & Services Corp. | MBC,PCCI, COA | 2023-05-30 | 2023-06-13 | 2023-06-13 | 2023-06-14 | 2023-06-21 | [10 empty] | PO#298718 | Awarded | Completed/Delivered
GSD-23-131 | 23MO-01E5 | Supply and Delivery of Various Maintenance Tools | Goods & Services | CDBB | 2023-05-05 | 2023-05-12 | 10:03AM | 2023-06-08 | 27 | GSD | N | NP-SVP | N/A | 2023-05-23 | N/A | N/A | N/A | 2023-06-05 | N/A | 2023-06-08 | N/A | 2023-06-09 | N/A | 30 days |  | COB | 86378.67 | 86378.67 |  | 29465.2 | 29465.2 |  | KOI Industrial Supply/Co Ban Kiat Hardware Inc. | [16 empty] | PO#298700/701 | Awarded | Completed/Delivered
PIP-23-132 | 23MO-06C13 | Supply and Delivery of Material for the Replacement of Existing Submersible Cable of PW6 and PW7 at PIP | Goods & Services | GSM | 2023-04-26 | 2023-05-12 | 11:02AM | 2023-06-20 | 39 | PIP | N | NP-SVP | N/A | 2023-05-23 | N/A | N/A | N/A | 2023-06-19 | N/A | 2023-06-20 | N/A | 2023-06-22 | N/A | 30 Days |  | COB | 370333 | 370333 |  | 265000 | 265000 |  | Pumpcraft Industrial Sales | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298703 | Awarded | Completed/ Delivered
PIP-23-133 | 23MO-01G | Supply and Delivery of Materials for the Replacement of Damaged Feeder line of R1 | Goods & Services | GSM | 2023-05-14 | 2023-05-12 | 11:02AM | 2023-07-20 | 69 | PIP | N | NP-SVP | N/A | 2023-05-22 | N/A | N/A | N/A | 2023-06-23 | N/A | 2023-07-20 | N/A | 2023-08-31 | N/A | 30 days |  | COB | 83484 | 83484 |  | 77760 | 77760 |  | Up-Town Industrial Sales,Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298735 | Awarded | Completed/ Delivered
PIP-23-134 | 23MO-01H2M | Supply and Delivery of Conference Chair | Goods & Services | GSM | 2023-04-27 | 2023-05-22 | 8:55AM | 2023-06-22 | 31 | PIP | N | NP-SVP | N/A | 2023-05-27 | N/A | N/A | N/A | 2023-06-21 | N/A | 2023-06-22 | N/A | 2023-06-30 | N/A | 30 days |  | COB | 64000 | 64000 |  | 55192 | 55192 |  | IKF Home Furnishing & office Furniture | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298709 | Awarded | Completed/ Delivered
PIP-23-135 | 23MO-06C2/06C3 | Calibration of Pressure Gauge,UFM abd Flow Totalizer | Goods & Services | GSM | 2023-05-18 | 2023-05-23 | 8:55AM | 2023-06-22 | 30 | PIP | N | NP-SVP | N/A | 2023-05-27 | N/A | N/A | N/A | 2023-06-14 | N/A | 2023-06-22 | N/A | 2023-06-30 | N/A | 30 days |  | COB | 153800 | 153800 |  | 142240 | 142240 |  | Senze Calibration and Measurement Laboratory, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298708 | Awarded | Completed/ Delivered
BR-23-136 | 23MO-04A1 | Engagement of Project Consultant for the Development of the PNOC Bunker Fuel Refilling Station | Consulting Services | CFCM | 2023-05-17 | 2023-05-23 | 3:52PM |  | -45069 | BRDD | N | PB | [13 empty] | COB | 9500000 | 9500000 | [23 empty] | Back to Proponent
GSD-23-137 | 23CA-03K | Supply and Installation of Concrete Pole at Records Center | Goods & Services | CDBB | 2023-05-15 | 2023-05-23 | 9:15AM | 2023-06-13 | 21 | GSD | N | NP-SVP | N/A | 2023-05-27 | N/A | N/A | N/A | 2023-06-09 | N/A | 2023-06-13 | 2023-06-15 | 2023-07-04 | 2023-06-29 | 7 days |  | COB | 515833.4 |  | 515833.4 | 470000 |  | 470000 | Pablo S. Labasbas Construction Corporation | [16 empty] | Contract#23-043 | Awarded | Completed/ Delivered
PSD-23-138 | Approved Budget Inclusion | 2023 PNOC Health and Wellness Program Dance Instructor | Goods & Services | CDBB | 2023-05-22 | 2023-06-20 | 4:55PM |  | -45097 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 265000 | 265000 | [16 empty] | 1st-Non receipt Quotation | 2023-06-19 | 2023-06-19 | 2023-06-19 |  |  |  | PENDING APPROVAL FROM OP
ESB-23-139 | 23MO-06G1 | Supply and Delivery of Screw Pin Anchor Shackle, Galvanized | Goods & Services | CDBB | 2023-05-22 | 2023-05-24 | 2:58PM | 2023-06-20 | 27 | ESB | N | NP-SVP | N/A | 2023-05-30 | N/A | N/A | N/A | 2023-06-09 | N/A | 2023-06-20 | N/A | 2023-06-22 | N/A | 30 Days |  | COB | 18800 | 18800 |  | 10880 | 10880 |  | Villaflores Industrial Supply | [16 empty] | PO#298702 | Awarded | Completed/ Delivered
PIP-23-140 | 23MO-07E8 | CSR Support for Schools of Brgy. Batangas Dos | Goods & Services | GSM | 2023-05-22 | 2023-05-29 | 9:03AM | 2023-07-13 | 45 | PIP | N | NP-SVP | N/A | 2023-06-07 | N/A | N/A | N/A | 2023-07-14 | N/A | 2023-07-13 | N/A | 2023-09-05 | N/A | 30 Days |  | COB | 29236 | 29236 |  | 23990 | 23990 |  | ZAB Enterprises Inc. /ShiganConstruction Supplies Trading | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298736/298737 | Awarded | Completed/ Delivered
PIP-23-141 | 23MO-01G | Supply and Delivery of Torque Wrench | Goods & Services | CDBB | 2023-05-18 | 2023-05-29 | 9:03AM |  | -45075 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 9784 | 9784 | [22 empty] | Awarded
PIP-23-142 | 23MO-01G | Supply and Delivery of Inverter Welding Machine | Goods & Services | CDBB | 2023-05-05 | 2023-05-29 | 9:03AM |  | -45075 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 24505 | 24505 | [22 empty] | Awarded
PIP-23-143 | 23MO-01H2M | Purchase, Supply and Delivery of Foldable platform Truck Trolley and Vacuum Cleaner | Goods & Services | CDBB | 2023-05-22 | 2023-07-03 | 9:03AM | 2023-07-20 | 17 | PIP | N | NP-SVP | N/A | 2023-07-06 | N/A | N/A | N/A | 2023-07-17 | N/A | 2023-07-20 | N/A | 2023-08-29 | N/A | 30 days |  | COB | 11000 | 11000 |  | 9900 | 9900 |  | Co Ban Kiat Hardware Inc. | [9 empty] | 2023-07-05 | [6 empty] | PO#298706/727 | Awarded | Completed/ Delivered
PIP-23-144 | 23MO-01G | Purchase of Electrical Materials, Consumables and Supplies | Goods & Services | CDBB | 2023-05-26 | 2023-05-31 | 11:30AM |  | -45077 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 78025 | 78025 |  | 32695 | 32695 |  | Ecoshift Corporation | [17 empty] | Awarded
SM-23-145 | 23MO-03A1 | 2023 internet/Leased Line Connection for ESB |  | RGV |  | 2023-05-31 | 2:05PM |  | -45077 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 300000 | 300000
PP-23-146 | 23MO-06C18 | Repair/Refurbishing of Furniture | Goods & Services | GSM | 2023-06-01 | 2023-06-06 | 2:40PM | 2023-06-27 | 21 | PRM | N | NP-SVP | N/A | 2023-06-15 | N/A | N/A | N/A | 2023-06-22 | N/A | 2023-06-27 | N/A | 2023-06-30 | N/A | 30 days |  | COB | 110000 | 110000 |  | 69680.2 | 69680.2 |  | Dargo Design Component Builders Corp. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298707 | Awarded | Completed/ Delivered
PSD-23-147 | 23MO-07E10 | Engagement of a Service Provider for the Overall Event Management for the 50th Anniversary Gala of PNOC | Goods & Services | CFCM | 2023-06-06 | 2023-07-03 | 2:05PM |  | -45110 | PSD | N | PB | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 1600000 | 1600000 | [23 empty] | On hold
PSD-23-148 | 23MO-07E108 | Supply and Delivery of PNOC 50th Anniversary Token (Wrist Watch) | Goods & Services | CDBB | 2023-05-16 | 2023-06-07 | 3:00PM |  | -45084 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 160000 | 160000 | [16 empty] | 1st - Non Compliance | [6 empty] | Cancelled
PSD-23-149 | 23MO-01D | Supply and Delivery of COVID Response Disinfectant Supplies (Face Mask) for JUL-OCT 2023) | Goods & Services | CDBB | 2023-06-06 | 2023-06-07 | 3:00PM | 2023-06-29 | 22 | PSD | N | NP-SVP | N/A | 2023-06-09 | N/A | N/A | N/A | 2023-06-20 | N/A | 2023-06-29 | N/A | 2023-07-05 | N/A | 30 days |  | COB | 54250 | 54250 |  | 34650 | 34650 |  | Ban Bee Commercial Co | [16 empty] | PO#298710 | Awarded | Completed/Delivered
PSD-23-151 | 23MO-07F2 | CY2023 Annual Physical Examination(APE) for PNOC Employees | Goods & Services | CDBB | 2023-06-06 | 2023-06-13 | 11:51AM | 2023-08-22 | 70 | PSD | N | NP-SVP | N/A | 2023-06-17 | N/A | N/A | N/A | 2023-08-17 | N/A | 2023-08-22 | 2023-08-22 |  |  | 1 month |  | COB | 465000 | 465000 |  | 282612 | 282612 |  | Christian Medical Clinic, Inc. | [17 empty] | Awarded | For Justification Memo
PIP-23-152 | 23CA-03S | Supply and Delivery of Materials for the Construction of Charging Station (part II) | Goods & Services | CDBB | 2023-06-05 | 2023-06-14 | 8:42AM | 2023-07-11 | 27 | PIP | N | NP-SVP | N/A | 2023-06-17 | N/A | N/A | N/A | 2023-07-03 | N/A | 2023-07-11 | N/A | 2023-07-17 | N/A | 30 days | 30 days | COB | 87057 |  | 87057 | 79166 |  | 79166 | RBC(Mariveles) Hardware,Inc./Up-Town Industrial Sales, Inc. | [9 empty] | 2023-07-20 | [6 empty] | PO#298720/721 | Awarded | Completed/Delivered
PIP-23-153 | 23MO-01E6 | Supply and Delivery of Heavy Duty Battery Charger | Goods & Services | CDBB | 2023-06-09 | 2023-06-14 | 8:42AM |  | -45091 | PIP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 14700 | 14700 | [23 empty] | Superceded by PIP-23-085
PIP-23-154 | 23MO-06C1 | Calibration of Alcohol Breath Analyzer | Goods & Services | GSM | 2023-06-02 | 2023-06-14 | 8:42AM | 2023-07-13 | 29 | PIP | N | NP-SVP | N/A | 2023-06-20 | N/A | N/A | N/A | 2023-07-04 | N/A | 2023-07-13 | N/A | 2023-07-17 | N/A | 30 days |  | COB | 5200 | 5200 |  | 4704 | 4704 |  | GLJM Diversified Sales and Services Corp. | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298722 | Awarded | Ongoing
PIP-23-155 | 23CA-030 | Rehabilitation of Maingate Security Guard Buillding and Guard House | Infrastructure | CFCM | 2023-06-01 | 2023-06-15 | 2:12PM |  | -45092 | PIP | N | PB | [13 empty] | COB | 2740000 |  | 2740000
GSD-23-156 | 23CA-03L | Technical Evaluation, Diagnosis and Analysis of Building 5 & 6 Electrical System | Goods & Services | CDBB | 2023-05-25 | 2023-06-16 | 8:32AM |  | -45093 | GSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 761280 |  | 761280 | [21 empty] | Awarded | Pending at OP
SM-23-157 | 23MO-01E10 | Supply and Delivery of Essential ICT Supplies | Goods & Services | GSM |  | 2023-06-16 | 2:38PM | 2023-08-08 | 53 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A | 2023-08-30 | N/A | 30 days |  | COB | 36240 | 36240 |  | 800 | 800 |  | Agile Techfrontier Corporation | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-09-06 | [6 empty] | PO#298732 | Awarded | incomplete/ Not All Awarded
ESB-23-158 | 23CA-03U | Rehabilitation of Warehouse 1,2,3, and 4 (Concrete Walls and Roof Drainage) | Infrastructure | CFCM | 2023-06-14 | 2023-06-16 | 4:25PM |  | -45093 | ESB | N | PB | [13 empty] | COB | 4975000 |  | 4975000
PIP-23-159 | 23MO-07E7 | Supply and Delivery of Materials for the 2023 Tree Planting Activity | Goods & Services | CDBB | 2023-06-14 | 2023-06-20 | 8:45AM | 2023-06-29 | 9 | PIP | N | NP-SVP | N/A | 2023-06-23 | N/A | N/A | N/A | 2023-06-26 | N/A | 2023-06-29 | N/A | 2023-06-29 | N/A | 30 days |  | COB | 38200 | 38200 |  | 30332 | 30332 |  | Ceboom Enterprises | [9 empty] | 2023-07-05 | [6 empty] | PO#298705 | Awarded
PSD-23-160 | 23MO-481Q | PNOC Scholarship Program for SY 2023-2024 (Conduct of Testing Exam) | Goods & Services | CDBB | 2023-06-20 | 2023-06-23 | 10:05AM | 2023-07-27 | 34 | PSD | N | NP-SVP | N/A | 2023-06-30 | N/A | N/A | N/A | 2023-07-26 | N/A | 2023-07-27 | N/A |  | N/A | 30 days |  | COB | 21200 | 21200 |  | 7200 | 7200 |  | Asian Psychological Servces & Assessment Inc. | [16 empty] | PO#298738 | Awarded | Completed/Delivered
OP-23-161 | 23MO-01H1H | Supply and Delivery of Corporate Tokens for 2023 | Goods & Services | GSM |  | 2023-06-23 | 11:30AM |  | -45100 | OP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 310000 | 310000 | [23 empty] | Pending At OP
PP-23-162 | 23MO-01A | Supply and Delivery of Consolidated Computer Supplies, for 2nd & 3rd QTR year 2023 | Goods & Services | GSM | 2023-06-22 | 2023-06-26 | 9:40AM | 2023-08-22 | 57 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 982687 | 982687 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Pending At OP
GSD-23-163 | Approved Budget Realignment | Replacement of Two Broken Window Glass at PNOC Bldg.6 | Goods & Services | GSM | 2023-06-20 | 2023-07-03 | 2:30PM | 2023-08-01 | 29 | GSD | N | NP-SVP | N/A | 2023-07-11 | N/A | N/A | N/A | 2023-08-01 | N/A | 2023-08-01 | N/A | 2023-08-07 | N/A | 30 days |  | COB | 50160 | 50160 |  | 48350 | 48350 |  | G.C. Sales Builders | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  | 2023-08-23 | [6 empty] | PO#298724 | Awarded | Completed/Delivered
PIP-23-164 | 23MO-01H2K | Supply and Delivery Safety Signages | Goods & Services | GSM | 2023-06-30 | 2023-07-04 | 10:25AM | 2023-07-25 | 21 | PIP | N | NP-SVP | N/A | 2023-07-11 | N/A | N/A | N/A | 2023-07-20 | N/A | 2023-07-27 | N/A | 2023-08-30 | N/A | 30 days |  | COB | 10000 | 10000 |  | 8682 | 8682 |  | PBOX Creative Advertising Corporation | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | PO#298733 | Awarded | Completed/Delivered
PSD-23-165 | 23MO-07E10C | Supply and Delivery of PNOC 2023 Anniversary Raffle Items | Goods & Services | CDBB | 2023-06-30 | 2023-07-04 | 10:10PM | 2023-08-01 | 28 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 448500 | 448500
PP-23-166 | 23MO-04B1S | Appraisal of PNOC,PAFC,PSTC & PDMC Vehicles and Unserviceable Properties for Disposal | Goods & Services | GSM | 2023-06-30 | 2023-07-10 | 9:42AM | 2023-08-08 | 29 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | 2023-08-08 | [5 empty] | COB | 100000 | 100000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | Pending At OP
SMO-23-167 | 23MO-06E1 | Repair of Printer Epson L385 | Goods & Services | GSM |  | 2023-07-11 | 1:42PM |  | -45118 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 2500 | 2500 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | Ongoing
PIP-23-168 | 23CA-03R | Supply and Delivery of 1500 Liters Diesel (Mother Tank/Supply) Tank at R2 | Goods & Services | CDBB | 2023-07-11 | 2023-07-17 | 8:51AM | 2023-08-22 | 36 | PIP | N | NP-SVP | N/A | 2023-08-01 | N/A | N/A | N/A | 2023-08-16 | N/A | 2023-08-22 | 2023-08-22 |  | 2023-10-02 |  |  | COB | 247500 |  | 247500 | 218000 | 218000 |  | Pumpcraft Industrial Sales | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [9 empty] | Contract#23-048 | Awarded | NTP/Contract @ OP \for Approval
PRM-23-169 | 23MO-01 | Supply and Delivery of Various Tissue(3rd&4th QTR) | Goods & Services | GSM | 2023-07-18 | 2023-07-19 | 9:06AM | 2023-08-22 | 34 | PRM | N | NP-SVP | N/A | 2023-07-31 | N/A | N/A | N/A | 2023-08-14 | N/A | 2023-08-22 | N/A |  | N/A |  |  | COB | 20678.81 | 20678.81 |  | 20104.5 | 20104.5 |  | Eco-Hygiene Institutional Sales Corp./ Sanitary Care Products Asia, Inc. | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [10 empty] | Awarded | Pending At OP
PRM-23-170 | 23MO-01A | Supply and Delivery of Consolidated Commonly Used Supplies, 2nd & 3rd QTR | Goods & Services | GSM | 2023-07-17 | 2023-07-20 | 10:30AM |  | -45127 | PRM | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 556990.38 | 556990.38 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For Award
PSD-23-171 | Approved Budget Realignment | Supply and Delivery of Costumes for the Members of PNOC Voices | Goods & Services | CDBB | 2023-06-29 | 2023-07-26 | 9:19AM | 2023-08-24 | 29 | PSD | N | NP-SVP | N/A | 2023-08-01 | N/A | N/A | N/A | 2023-08-23 | N/A | 2023-08-24 | 2023-08-31 | 2023-09-14 | 2023-09-14 | 45 days |  | COB | 142000 | 142000 |  | 136500 | 136500 |  | JEM Tangco Fashion House | [16 empty] | Contract#23-049 | Awarded | Completed/Delivered
PIP-23-172 | 23MO-06C5 | Pullout, Repair, and Reinstallation of Submersible Pumps and Motors and/or PMS of Production Wells | Goods & Services | CDBB | 2023-07-03 | 2023-08-07 | 9:13AM | 2023-09-05 | 29 | PIP | N | NP-SVP | N/A | 2023-08-25 | N/A | N/A | N/A | 2023-09-04 | N/A | 2023-09-05 | 2023-09-07 |  | 2023-09-13 | 30 days |  | COB | 875000 | 875000 |  | 868795.2 | 868795.2 |  | E.J.U. Trading | [16 empty] | Contract#23-052 | Awarded | Contract @Supplier for Signature
PSD-23-173 | Approved Budget Realignment | Conduct of Values Orientation Workshop (VOW) | Goods & Services | CDBB | 2023-08-03 | 2023-08-07 | 3:34PM |  | -45145 | PSD | Y | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A | [6 empty] | COB | 180000 | 180000 | [23 empty] | On Hold
SMO-23-174 | 23CA-04A5 | PNOC Network Rehabilitation and Reconfiguration Project | Goods & Services | RGV |  | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 4000000 |  | 4000000 | [22 empty] | For Opening of Bids\
SMO-23-175 | 23CA-04A9 | MS Office Upgrade (Home & Business 2021) | Goods & Services | RGV |  | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 1112500 |  | 1112500
SMO-23-176 | 23-CA04A7 | Laptop Computers | Goods & Services | RGV |  | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 426000 |  | 426000
SMO-23-177 | 23CA-04A6 | Desktop Computer Set | Goods & Services | RGV | 2023-08-22 | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 340000 |  | 340000
SMO-23-178 | 23CA-04A8 | Network Attached Storage (NAS) with Installed 4x4TB SATA SSD | Goods & Services | RGV |  | 2023-08-30 | 9:00AM |  | -45168 | SMO | Y | PB | [13 empty] | COB | 555020 |  | 555020
SMO-23-179 | 23CA-04A4 | POE Switch 24-Ports | Goods & Services | RGV | 2023-06-16 | 2023-09-04 | 1:30PM |  | -45173 | SMO | Y | PB | [13 empty] | COB | 914326.67 |  | 914326.67
GSD-23-180 | 23MO-06C16 | Instrumentation Testing of 3508 caterpillar Genset at PNOC Bldg.5 | Goods & Services | GSM | 2023-07-20 | 2023-09-05 | 1:45PM | 2023-09-21 | 16 | GSD | N | NP-SVP |  |  | N/A | N/A | N/A |  | N/A | 2023-09-21 | N/A |  | N/A |  |  | COB | 65300 | 65300 |  | 56500 | 56500 |  | Tabuko Energy Network Corp. | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Awarded | Pending At OP
CS-23-181 | 23MO-01H2A | Supply and Delivery of Calling Cards for Directors | Goods & Services | RACC | 2023-09-11 | 2023-09-19 | 3:05PM |  | -45188 | CORSEC | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 2000 | 2000 | [23 empty] | For Technical Evaluation
SMO-23-182 | 23MO-01E10 | Supply and Delivery of Essential ICT Supplies Part II | Goods & Services | GSM | 2023-09-19 | 2023-09-19 | 4:05PM |  | -45188 | SMO | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 40200 | 40200 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [12 empty] | For Technical Evaluation
PSD-23-183 | 23MO-07E108 | Supply and Delivery of PNOC 50th Anniversary Token (Tumbler) | Goods & Services | CDBB | 2023-09-14 | 2023-09-21 | 1:15PM |  | -45190 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 160000 | 160000 | [23 empty] | For Technical Evaluation
OP-23-184 | Approved Budget Inclusion | Supply and Delivery of PNOC 50th Anniversary Souvenir ( USB- Adapter) | Goods & Services | RACC |  | 2023-09-26 |  |  | -45195 | OP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 368000 | 368000 | [23 empty] | On Process
OP-23-185 | Approved Budget Realignment | Supply and Delivery of Tablet Computer | Goods & Services | RGV | 2023-08-23 | 2023-09-27 | 2:35PM |  | -45196 | OP | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 189000 | 189000 | [23 empty] | Returned to OP with Memo
PSD-23-186 | 23MO-01H1G | Supply and Delivery of Wood Plaque (For Retiree) | Goods & Services | GSM | 2023-09-21 | 2023-09-27 | 2:50PM |  | -45196 | PSD | N | NP-SVP | N/A |  | N/A | N/A | N/A |  | N/A |  | N/A |  | N/A |  |  | COB | 4000 | 4000 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | [11 empty] | Superseded by PSD-23-071 | ongoing
|  | PP-22-084 | 2022-05-11
51
Formulas:
Date PR Awarded = [Date of BAC Reso Reco Award]
Sub/Open of Bids = [Eligibility Check]
Date of BAC Reso Reco Award = [Date PR Awarded]
Eligibility Check = [Sub/Open of Bids]
Contract Signing/ PO = [Date PR Awarded]